## Sectional Completion
SCHEDULE OF SECTIONAL COMPLETION AND DELAY DAMAGES
Polaris DC-1 · PDC-SC-001 Rev C · as executed (Rev C of the Particular Conditions)
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Section | Scope | Time for Completion (months) | Completion date | Delay damages (EUR/day) | Delay damages (EUR/week) | Notes
1 | Data Hall 1, primary substation, generator compound, shared cooling spine sized for the full 10 MW, site access, gatehouse | 14 | 2027-05-02 | 18000 | 126000 | Taking Over requires the occupancy inspection (käyttöönottotarkastus) and Tenant technical acceptance
2 | Data Hall 2 and associated plant | 16 | 2027-07-02 | 12000 | 84000 | Taking Over requires the occupancy inspection (käyttöönottotarkastus) and Tenant technical acceptance
3 | Data Hall 3 and associated plant | 19 | 2027-10-02 | 12000 | 84000 | Taking Over requires the occupancy inspection (käyttöönottotarkastus) and Tenant technical acceptance
4 | Data Hall 4, administration and NOC block, external works, landscaping | 22 | 2028-01-02 | 10000 | 70000 | Taking Over requires the occupancy inspection (käyttöönottotarkastus) and Tenant technical acceptance
Commencement Date |  | 2026-03-02
Time for Completion (whole of the Works) |  | 22 months
Accepted Contract Amount |  | EUR 92,400,000
Maximum delay damages (Rev C) |  | 10% of the Accepted Contract Amount
Maximum delay damages (value) |  | EUR 9,240,000
Accrual across concurrently delayed Sections |  | Cumulative, subject to the 10% aggregate cap
Sole remedy for delay (Rev C SP-8) |  | Delay damages
Concurrent delay (Rev C SP-7) |  | Apportionment by the Engineer; no Cost for concurrent periods