## Calendar Basis
WORKING CALENDAR AND CONSTRAINTS
Polaris DC-1 · PDC-CAL-001 Rev A · basis for the baseline programme
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Parameter | Value | Unit | Notes
Working week | Mon-Fri | days | 5-day week assumed for planning
Site working hours | 06:00-22:00 |  | Building permit condition
Deliveries | 06:00-22:00 Mon-Fri |  | Shared access with an operating logistics neighbour
Blasting hours | 08:00-18:00 Mon-Fri |  | Building permit condition
Generator testing hours | 09:00-16:00 Mon-Fri |  | Building permit condition
Night noise limit | 45 | dB(A) | At the north-east residential boundary
Winter working | Dec-Mar |  | Concrete and external works productivity allowance applied
Summer shutdown | Weeks 28-30 |  | Finnish construction holiday period, reduced resources
Public holidays 2026-2028 | 28 | days | Listed on the Holidays sheet
Heating season (district heating) | Oct-Apr |  | Waste-heat connection can only be accepted in this window
110 kV outage windows | Spring and autumn |  | Two per year; 16 weeks' notice required

## Holidays
FINNISH PUBLIC HOLIDAYS
Non-working days
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Date | Day | Holiday
2026-01-01 | Thu | Uudenvuodenpäivä (New Year's Day)
2026-01-06 | Tue | Loppiainen (Epiphany)
2026-04-03 | Fri | Pitkäperjantai (Good Friday)
2026-04-06 | Mon | Toinen pääsiäispäivä (Easter Monday)
2026-05-01 | Fri | Vappu (May Day)
2026-05-14 | Thu | Helatorstai (Ascension)
2026-06-19 | Fri | Juhannusaatto (Midsummer Eve)
2026-06-20 | Sat | Juhannuspäivä (Midsummer Day)
2026-10-31 | Sat | Pyhäinpäivä (All Saints' Day)
2026-12-06 | Sun | Itsenäisyyspäivä (Independence Day)
2026-12-24 | Thu | Jouluaatto (Christmas Eve)
2026-12-25 | Fri | Joulupäivä (Christmas Day)
2026-12-26 | Sat | Tapaninpäivä (Boxing Day)
2027-01-01 | Fri | Uudenvuodenpäivä
2027-01-06 | Wed | Loppiainen
2027-03-26 | Fri | Pitkäperjantai
2027-03-29 | Mon | Toinen pääsiäispäivä
2027-05-01 | Sat | Vappu
2027-05-06 | Thu | Helatorstai
2027-06-25 | Fri | Juhannusaatto
2027-06-26 | Sat | Juhannuspäivä
2027-11-06 | Sat | Pyhäinpäivä
2027-12-06 | Mon | Itsenäisyyspäivä
2027-12-24 | Fri | Jouluaatto
2027-12-25 | Sat | Joulupäivä
2027-12-26 | Sun | Tapaninpäivä
2028-01-01 | Sat | Uudenvuodenpäivä
2028-01-06 | Thu | Loppiainen