# NORDBUILD OY — SITE LOGISTICS PLAN

## Company Standard PDC-LOG-001 Rev C

Issued by: Head of Logistics, Nordbuild Oy

Applies to: every Nordbuild project over EUR 10 million or 50 operatives at peak

Status: mandatory. Departures require the Head of Logistics' written agreement.

*SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT*

____________________________________________________________

## 1. Purpose and status of this document

This is the company standard, not a site plan. It sets out what every Nordbuild site logistics plan must contain, the rules it must satisfy, and the numbers to size facilities with. The site logistics manager applies it to their own site and produces the project's own logistics plan.

Where this standard gives a number, use it. Where it gives a rule, satisfy it or record a departure. Where it is silent, the site logistics manager decides and records the reasoning — a decision recorded is acceptable, a decision left implicit is not.

Two things this standard will not do for you. It cannot tell you where anything goes on YOUR site: that comes from the drawings, the programme and the site's own constraints. And it cannot tell you when something has to move: that comes from reading the subcontractors' programmes against each other.

____________________________________________________________

## 2. Roles

| Role | Responsibility |
| --- | --- |
| Site logistics manager | Owns the plan. Issues it monthly. Chairs the weekly logistics meeting |
| Project manager | Approves the plan and any departure from this standard |
| HSE manager | Approves pedestrian routes, segregation and exclusion zones |
| Subcontractor's site manager | Requests storage, books deliveries, keeps their allocated area |

____________________________________________________________

## 3. The deliverable

The site logistics plan is a drawn document. Text alone is not a logistics plan — the people who use it are looking for where to put something or where to walk, and they read a drawing.

Minimum content, every issue:

One plan per month for the full construction period, on the project's

general arrangement or site plan as the base.

Every facility in Section 4 shown to scale, in the correct position, with

its area or dimension labelled.

A legend identifying each subcontractor by a distinct colour or hatch,

used consistently across all months.

Changes from the previous month called out — what moves, what appears,

what is removed. A month that is identical to the one before it says so.

A schedule of areas listing each allocated facility, its size, its occupant

and the months it exists for.

### 3.1 The base drawing — mark up what was issued

Start from the issued drawing and annotate it. Do not redraw the site.

The site plan, the general arrangement and the logistics base plan are controlled documents. They carry the grid, the setting-out dimensions, the title block, the revision and the scale, and every other trade is working to them. A logistics plan drawn on top of the issued sheet stays tied to all of that. A fresh sketch that merely resembles the site is tied to nothing: its dimensions are invented, its scale cannot be trusted, nothing on it can be checked against another drawing, and the first question in the meeting — "is that where the wall actually is?" — has no answer.

So take the issued sheet as the canvas, and put the logistics facilities on top of it. Keep what is already there — the building outlines, the grid, the boundary, the title block. Add only what Section 4 requires.

### 3.2 Sheet layout

One month per sheet, with the whole site on it, unless there is a reason to do otherwise.

Use the whole sheet. Every sheet carries, in fixed positions:

| Band | Contents |
| --- | --- |
| Top | Month and headcount |
| Middle — the largest band | The marked-up drawing |
| Bottom | Legend, changes from last month, and the issues list |

Nothing overlaps the drawing. Notes, issue lists and conflict callouts belong in the bottom band with a leader line to the place they refer to — never stacked on top of the plan or on each other. If a label will not fit at the scale drawn, number it and put the text in the bottom band.

If the sheet still reads badly, the usual cause is a site much longer than it is deep on a sheet that is not. Two remedies are permitted, in this order: put two consecutive months on one sheet, one above the other, so each fills half the height; or, only if that still will not read, split the site along its length and give each part its own sheet. Neither is required. Do not split the site as a first move — a reader wants the whole site in one view.

Check it as a reader would. Before issuing, render each sheet to an image and look at it. Confirm: no text sits on other text, no band is empty, the plan occupies most of the sheet, and every marked facility sits ON the drawing rather than beside it. A plan that is correct but unreadable has not been issued.

____________________________________________________________

## 4. Facilities to be planned

Every logistics plan shows all of the following, for every month:

### 4.1 Staff and operative parking

### 4.2 Site accommodation — offices, welfare, canteen

### 4.3 Material storage compounds, allocated by subcontractor

### 4.4 Pedestrian routes and crossing points

### 4.5 Vehicle routes, gates and delivery/turning areas

### 4.6 Craneage positions, radii and exclusion zones

### 4.7 Material lifting points into the structure

____________________________________________________________

## 5. Parking — sizing rules

| Parameter | Value |
| --- | --- |
| Provision | 1 space per 2.5 operatives at peak (car-sharing assumed) |
| Standard bay | 2.5 m × 5.0 m |
| Accessible bays | 2 per 50 spaces, 3.6 m × 5.0 m, nearest the welfare entrance |
| Aisle width | 6.0 m two-way, 3.5 m one-way |
| Allowance including circulation | 25 m² per space |
| Visitor parking | 6 spaces minimum, outside the secure line |
| Surface | Compacted hardstanding, drained, lit to 20 lux |

Parking sits outside the working area and connects to welfare by a segregated footpath. Operatives must not cross a vehicle route to reach the welfare block; if the geometry forces a crossing, it is a controlled crossing under 8.3.

____________________________________________________________

## 6. Site accommodation — sizing rules

Modular units are 12.0 m × 3.0 m (36 m²), stackable two storeys. Sizing at

250 operatives and 28 staff peak:

| Facility | Rule | At 250/28 |
| --- | --- | --- |
| Offices | 8 m² per staff member | 224 m² |
| Canteen seating | 50% of peak seated in one sitting, 1.2 m² per seat | 150 m² |
| Drying and changing | 0.5 m² per operative | 125 m² |
| WCs | 1 per 25 operatives | 10 |
| Wash basins | 1 per 20 operatives | 13 |
| First aid and meeting | 40 m² minimum | 40 m² |
| Net internal total |  | ≈ 600 m² |
| Footprint if stacked two storeys | net ÷ 2, plus 25% circulation and stairs | ≈ 380 m² |

Show the accommodation as a single labelled block with its footprint dimensions. The internal layout is the accommodation supplier's design and is not required in this plan.

Accommodation must be within 200 m walking distance of the working face, or a satellite welfare unit is provided.

____________________________________________________________

## 7. Storage compounds

| Parameter | Rule |
| --- | --- |
| Allocation | Each subcontractor gets a named, bounded compound. Shared compounds are not permitted |
| Sizing | From the subcontractor's own stated laydown requirement in their baseline programme |
| Surface | Hardstanding and drained. Weather-sensitive materials on raised bearers |
| Enclosure | Fenced and signed with the subcontractor's name |
| Stack height | 2.0 m maximum unless racked and designed |
| Separation from the building | 3.0 m clear where mast-climbers or scaffold are in use |
| Gas cylinders and flammables | Segregated compound, 6 m from any other storage, 15 m from hot works, bunded and signed |
| Review | Re-planned at every milestone that changes demand — in particular at weathertight, when interior packages move their materials inside and their external compound is released |

A compound that exists for the whole project is planned once and shown on every month. A compound that moves is shown in both positions in the month it moves, with the move called out.

____________________________________________________________

## 8. Pedestrian routes

| Parameter | Rule |
| --- | --- |
| Minimum width | 1.2 m, or 2.0 m where it is the primary route to welfare |
| Segregation | Physically separated from vehicle routes by barrier, not by paint alone |
| Surface | Firm, drained, free of trip hazards, lit to 20 lux in hours of darkness |
| Crossings | Controlled points only, marked, with clear sight lines both ways |
| Under craneage | No pedestrian route inside a crane's operating radius unless protected by a designed cover |
| Continuity | Every route runs gate → parking → welfare → working face without a break |

Routes are drawn as a continuous line from end to end. A route drawn only in fragments is not a route.

____________________________________________________________

## 9. Vehicle routes, gates and deliveries

| Parameter | Rule |
| --- | --- |
| Route direction | One-way circulation wherever the geometry allows |
| Carriageway width | 6.0 m two-way, 3.5 m one-way, 7.5 m at turning and unloading areas |
| Reversing | Maximum 15 m, and only with a banksman. Otherwise provide a turning head |
| Turning head | 25 m diameter, or a designed banked reversing bay for articulated deliveries |
| Delivery booking | All deliveries booked through the logistics manager. No unbooked vehicle enters |
| Waiting | No queueing on the public highway. Provide a holding area inside the gate |
| Wheel wash | At the exit of any earthworks or concrete operation |

Where the project has only one gate, the plan must show how the peak movements of all concurrent packages pass through it, and say what is done in the months where they conflict.

____________________________________________________________

## 10. Craneage and lifting

| Parameter | Rule |
| --- | --- |
| Crane position | Shown with its operating radius drawn to scale |
| Exclusion zone | Radius plus 10%. No accommodation, parking, storage or pedestrian route inside it unless protected |
| Oversail | No load carried over an occupied area, a public highway or a neighbouring property |
| Overhead services | Statutory clearance to any overhead line. Where a lift falls within a network operator's exclusion zone, the plan must record the written permission required |
| Lifting into the structure | Every project provides at least one designated material lifting point per building where materials are raised to upper floors or roof — a hardstanding for the lifting appliance, a clear drop zone, and a receiving platform at the level served |
| Availability | The lifting point is planned from the month the receiving level exists until the month the last material is lifted, and shown on every plan in between |

____________________________________________________________

## 11. Monthly review

The plan is reissued monthly. It is re-planned, not re-dated: each issue is checked against the current subcontractor programmes and the facilities moved where the work has moved.

Trigger points that always force a re-plan:

A new subcontractor arrives on site

A package reaches weathertight in any area

A crane moves, arrives or leaves

The permanent works begin on ground occupied by a temporary facility

Any change to the site access or gate arrangement

____________________________________________________________

## 12. Departures

Departures from this standard are permitted where the site makes compliance impossible. Record the departure, the reason and the mitigation on the plan itself. An unrecorded departure is a non-conformance. A plan that quietly omits a facility it could not place is worse than one that shows the problem.

____________________________________________________________

*PDC-LOG-001 Rev C · Nordbuild Oy · Head of Logistics*

*SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT*