## Programme Basis
KALLIO & MAA OY — EARTHWORKS, BLASTING, PILING AND SUBSTRUCTURE — BASELINE PROGRAMME
PDC-SCH-001 Rev 0 · submitted for the Contractor's acceptance
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Project | Polaris DC-1 — Aviapolis Data Campus, Phase 1, Vantaa
Subcontractor | Kallio & Maa Oy
Package | TP-001 — Earthworks, blasting, piling and substructure
Subcontract sum | EUR 14,820,000
Data date | 2026-03-02
Calendar | Mon-Fri per PDC-CAL-001, 28 Finnish public holidays, weeks 28-30 shutdown
Programme start | 2026-03-02
Programme finish | 2026-11-13
Total activities | 19
Zone column | Zone names match the labels on PDC-DWG-002 General Arrangement
Site laydown requirement | 4,200 m2 at peak — the largest demand of any package, and it peaks in the months when there is no building to work around. Bulk excavation arisings are stockpiled on site for re-use as fill; the stockpile is the single biggest area constraint on the plot.
Note on blasting | All eastern-third excavation is gated by the blasting permit and the pre-condition survey (MS-05). Every shot clears the exclusion zone, which stops all other trades on site for its duration.
Note on the gate | GW-1010 establishes the ONLY site access. Until it completes there is no vehicular route onto the plot for any package.
Prepared by | Kallio & Maa Oy planning department

## Activities
ID | Activity Name | Duration (days) | Start | Finish | Predecessors | Zone | Notes
GW-1000 | Instruction to proceed | 0 | 2026-03-02 | 2026-03-02 |  |  | Milestone
GW-1010 | Mobilisation, site hoarding and temporary haul road | 15 | 2026-03-02 | 2026-03-20 |  | SITE WIDE | Establishes the Tikkurilantie gate and the internal haul road — every other package depends on it
GW-1020 | Site compound base — offices, welfare and parking hardstanding | 12 | 2026-03-23 | 2026-04-09 | GW-1010 | SITE WIDE | Hardstanding for the temporary accommodation; approx. 2,400 m2
GW-1030 | Pre-condition survey and blasting permit discharge | 20 | 2026-03-02 | 2026-03-27 |  |  | MS-05 — gates all eastern-third excavation
GW-1100 | Topsoil strip and bulk earthworks — western two-thirds | 40 | 2026-03-23 | 2026-05-21 |  | SITE WIDE | Peak muck-away: 18-22 lorry movements per day through the single gate
GW-1110 | Rock excavation and blasting — eastern third | 55 | 2026-03-30 | 2026-06-18 |  | SITE WIDE | Blasting 08:00-18:00 Mon-Fri only (MS-06). Each shot clears the exclusion zone and stops all other trades
GW-1120 | Made-ground remediation — north-west corner | 15 | 2026-05-22 | 2026-06-11 | GW-1100 | SITE WIDE | Extent unproven — approx. 900 m2 per PDC-DWG-001
GW-1320 | Substructure — shared MEP spine | 25 | 2026-04-27 | 2026-06-02 |  | SHARED MEP SPINE + MEZZANINE OVER | ANCHOR — must complete before IL-1400 spine pipework starts 2026-06-15
GW-1200 | Piling — Hall 1 and Hall 2 | 25 | 2026-05-20 | 2026-06-24 |  | HALL 1 | Piling rig requires a 25 m x 15 m standing area plus casing laydown
GW-1300 | Pile caps and ground beams — Halls 1-2 | 15 | 2026-06-25 | 2026-08-05 | GW-1200 | HALL 1
GW-1400 | Ground-bearing slab — Halls 1-2 | 20 | 2026-08-03 | 2026-08-28 |  | HALL 1 | ANCHOR — must complete before IL-1410 Hall 1 pipework starts 2026-09-01. Slab down releases internal lay-down and internal craneage
GW-1210 | Piling — Hall 3 and Hall 4 | 25 | 2026-06-22 | 2026-08-14 |  | HALL 3 | Follows rock excavation in the eastern third
GW-1310 | Pile caps and ground beams — Halls 3-4 | 15 | 2026-08-17 | 2026-09-04 | GW-1210 | HALL 3
GW-1410 | Ground-bearing slab — Halls 3-4 | 20 | 2026-08-31 | 2026-09-25 |  | HALL 3
GW-1220 | Piling — substation, switchgear and generator compound | 18 | 2026-06-22 | 2026-08-05 |  | 110/20 KV PRIMARY SUBSTATION
GW-1420 | Substructure — generator compound and fuel storage bunds | 20 | 2026-08-04 | 2026-08-31 |  | GENERATOR COMPOUND
GW-1500 | External drainage and below-ground services | 30 | 2026-09-28 | 2026-11-06 |  | SITE WIDE | Open trenches across the internal haul road — the delivery route must divert
GW-1900 | Substructure complete — handover to TP-002 | 0 | 2026-09-28 | 2026-09-28 | GW-1410 |  | Milestone
GW-1950 | Demobilise bulk earthworks plant | 5 | 2026-11-09 | 2026-11-13 | GW-1500 | SITE WIDE | Releases the eastern stockpile area