## Programme Basis
TERÄSRAKENNE POHJOLA OY — STRUCTURAL STEEL AND PRECAST CONCRETE — BASELINE PROGRAMME
PDC-SCH-002 Rev 0 · submitted for the Contractor's acceptance
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Project | Polaris DC-1 — Aviapolis Data Campus, Phase 1, Vantaa
Subcontractor | Teräsrakenne Pohjola Oy
Package | TP-002 — Structural steel and precast concrete
Subcontract sum | EUR 21,340,000
Data date | 2026-04-06
Calendar | Mon-Fri per PDC-CAL-001, 28 Finnish public holidays, weeks 28-30 shutdown
Programme start | 2026-04-06
Programme finish | 2027-02-26
Total activities | 19
Zone column | Zone names match the labels on PDC-DWG-002 General Arrangement
Site laydown requirement | 600-900 m2 during erection only. Steel and precast arrive just-in-time and are lifted straight off the trailer, so the demand is craneage and hardstanding rather than storage. Each hall needs a 30 m x 20 m crane standing with a clear radius.
Note on craneage | A 250 t mobile crane works east along the halls in sequence. ST-1310 places it inside the 110 kV overhead-line exclusion zone and cannot proceed without the network operator's written permission (PDC-DWG-001).
Note on deliveries | Abnormal loads. Steel arrives on 18 m trailers that cannot turn inside the plot — a through route or a banked reversing area is required at the gate.
Prepared by | Teräsrakenne Pohjola Oy planning department

## Activities
ID | Activity Name | Duration (days) | Start | Finish | Predecessors | Zone | Notes
ST-1000 | Instruction to proceed | 0 | 2026-04-06 | 2026-04-07 |  |  | Milestone
ST-1010 | Design development — steel frame and precast connections | 35 | 2026-04-06 | 2026-05-27
ST-1020 | Fabrication drawings and approval | 30 | 2026-05-28 | 2026-07-30 | ST-1010
ST-1100 | Structural steel fabrication — Halls 1-2 | 55 | 2026-06-01 | 2026-09-07 |  |  | Off site — no plot demand
ST-1110 | Structural steel fabrication — Halls 3-4 | 55 | 2026-07-01 | 2026-10-06 |  |  | Off site — no plot demand
ST-1120 | Precast wall and floor unit manufacture | 60 | 2026-06-15 | 2026-09-28 |  |  | Off site — no plot demand
ST-1200 | Steel erection — Hall 1 | 22 | 2026-08-31 | 2026-09-29 |  | HALL 1 | 250 t mobile crane. Steel is lifted from the trailer — 600 m2 of lay-down only
ST-1210 | Steel erection — Hall 2 | 22 | 2026-09-30 | 2026-10-29 | ST-1200 | HALL 2 | Crane relocates east
ST-1220 | Steel erection — Hall 3 | 22 | 2026-09-28 | 2026-10-27 |  | HALL 3 | Crane relocates east
ST-1230 | Steel erection — Hall 4 | 22 | 2026-10-28 | 2026-11-26 | ST-1220 | HALL 4 | Crane relocates east
ST-1400 | Metal decking and structural topping — Halls 1-2 | 20 | 2026-10-12 | 2026-11-06 |  | HALL 1
ST-1410 | Metal decking and structural topping — Halls 3-4 | 20 | 2026-11-09 | 2026-12-04 |  | HALL 3
ST-1300 | Precast erection — shared MEP spine and mezzanine | 30 | 2026-10-05 | 2026-11-13 |  | SHARED MEP SPINE + MEZZANINE OVER | Mezzanine slab complete — first-floor material lifting can begin from this date
ST-1310 | Precast erection — substation and switchgear building | 18 | 2026-11-02 | 2026-11-25 |  | SWITCHGEAR BUILDING | Crane operates within the 110 kV overhead-line exclusion zone — written DNO permission required
ST-1500 | Roof steelwork and plant support frames | 25 | 2026-11-16 | 2026-12-18 |  | SITE WIDE | ANCHOR — must complete before IL-1520 dry-cooler installation starts 2026-12-30. Sets out the roof lifting platform position
ST-1600 | Fire protection to structural steel | 30 | 2027-01-11 | 2027-02-19 |  | SITE WIDE
ST-1900 | Structure complete — Halls 1-2 | 0 | 2026-11-09 | 2026-11-09 | ST-1400 | HALL 1 | Milestone
ST-1910 | Structure complete — Halls 3-4 | 0 | 2026-12-07 | 2026-12-07 | ST-1410 | HALL 3 | Milestone
ST-1950 | Crane demobilisation | 5 | 2027-02-22 | 2027-02-26 | ST-1600 | SITE WIDE | Releases the crane hardstanding