## Programme Basis
JULKISIVU VANTAA OY — ENVELOPE: CLADDING, ROOFING AND LOUVRES — BASELINE PROGRAMME
PDC-SCH-003 Rev 0 · submitted for the Contractor's acceptance
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Project | Polaris DC-1 — Aviapolis Data Campus, Phase 1, Vantaa
Subcontractor | Julkisivu Vantaa Oy
Package | TP-003 — Envelope: cladding, roofing and louvres
Subcontract sum | EUR 11,650,000
Data date | 2026-08-03
Calendar | Mon-Fri per PDC-CAL-001, 28 Finnish public holidays, weeks 28-30 shutdown
Programme start | 2026-08-03
Programme finish | 2027-04-15
Total activities | 13
Zone column | Zone names match the labels on PDC-DWG-002 General Arrangement
Site laydown requirement | 1,100 m2 while cladding, falling to almost nothing afterwards. Cassettes arrive in hall-sized batches and are weather-sensitive, so the stack must be on drained hardstanding. Roofing needs only a few days of buffer beside the lifting platform.
Note on weathertightness | EN-1500 and EN-1510 are the pivot for every interior package: before them interior materials must be stored externally, after them they move inside and the external lay-down is released. This is the largest single change in site area demand.
Note on access | Mast-climbers need a clear 3 m strip to both long elevations throughout EN-1200 and EN-1210 — this conflicts with any perimeter storage.
Prepared by | Julkisivu Vantaa Oy planning department

## Activities
ID | Activity Name | Duration (days) | Start | Finish | Predecessors | Zone | Notes
EN-1000 | Instruction to proceed | 0 | 2026-08-03 | 2026-08-03 |  |  | Milestone
EN-1010 | Design development — cladding, acoustic and fire-rated build-ups | 30 | 2026-08-03 | 2026-09-11
EN-1020 | Cladding fabrication and delivery to site | 55 | 2026-09-07 | 2026-11-20 |  |  | Off site
EN-1100 | Roofing — Halls 1-2 | 30 | 2026-11-09 | 2026-12-18 |  | HALL 1 | Roof materials lifted by telehandler from the lifting platform
EN-1110 | Roofing — Halls 3-4 | 30 | 2026-12-07 | 2027-01-21 |  | HALL 3
EN-1200 | Wall cladding — Halls 1-2 | 30 | 2026-11-16 | 2026-12-29 |  | HALL 1 | Mast-climbers to both elevations — a clear 3 m working strip is required
EN-1210 | Wall cladding — Halls 3-4 | 30 | 2026-12-14 | 2027-01-28 |  | HALL 3
EN-1500 | WEATHERTIGHT — Halls 1-2 | 0 | 2026-12-30 | 2026-12-30 | EN-1200 | HALL 1 | ANCHOR — must precede IL-1531 CRAH Hall 1 (2027-01-05). Interior packages may store materials inside from this date and their external lay-down is released
EN-1510 | WEATHERTIGHT — Halls 3-4 | 0 | 2027-01-29 | 2027-01-29 | EN-1210 | HALL 3 | ANCHOR — must precede IL-1533 CRAH Hall 3 (2027-02-03). As EN-1500, eastern halls
EN-1400 | Roof plant screens and walkways | 25 | 2027-01-26 | 2027-03-01 |  | SITE WIDE
EN-1300 | Louvres, doors and external openings | 30 | 2027-02-02 | 2027-03-15 |  | SITE WIDE
EN-1600 | Envelope snagging and sealant inspection | 20 | 2027-03-16 | 2027-04-14 |  | SITE WIDE
EN-1900 | Envelope complete | 0 | 2027-04-15 | 2027-04-15 | EN-1600 |  | Milestone