## Programme Basis
SISÄRAKENNE HELSINKI OY — ARCHITECTURAL FINISHES AND DATA-HALL CONTAINMENT — BASELINE PROGRAMME
PDC-SCH-004 Rev 0 · submitted for the Contractor's acceptance
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Project | Polaris DC-1 — Aviapolis Data Campus, Phase 1, Vantaa
Subcontractor | Sisärakenne Helsinki Oy
Package | TP-004 — Architectural finishes and data-hall containment
Subcontract sum | EUR 9,480,000
Data date | 2026-11-02
Calendar | Mon-Fri per PDC-CAL-001, 28 Finnish public holidays, weeks 28-30 shutdown
Programme start | 2026-11-02
Programme finish | 2027-06-28
Total activities | 17
Zone column | Zone names match the labels on PDC-DWG-002 General Arrangement
Site laydown requirement | 1,600 m2 externally until the halls are weathertight, then close to nothing. Raised-floor pallets and containment steel are bulky but move inside as soon as EN-1500/EN-1510 allow — the largest release of external space in the whole programme.
Note on storage | External demand is entirely a function of the weathertight dates. Plan the external area for the months BEFORE EN-1500/EN-1510 and release it after.
Prepared by | Sisärakenne Helsinki Oy planning department

## Activities
ID | Activity Name | Duration (days) | Start | Finish | Predecessors | Zone | Notes
FI-1000 | Instruction to proceed | 0 | 2026-11-02 | 2026-11-02 |  |  | Milestone
FI-1010 | Design development — white-space containment and finishes | 30 | 2026-11-02 | 2026-12-11
FI-1100 | Internal blockwork and partitions — Halls 1-2 | 30 | 2027-01-18 | 2027-02-26 |  | HALL 1
FI-1110 | Internal blockwork and partitions — Halls 3-4 | 30 | 2027-02-01 | 2027-03-12 |  | HALL 3
FI-1200 | Raised access floor — Hall 1 | 20 | 2027-02-01 | 2027-02-26 |  | HALL 1 | Pallets lifted to the slab and stored internally — external lay-down no longer needed
FI-1210 | Raised access floor — Hall 2 | 20 | 2027-03-01 | 2027-03-30 | FI-1200 | HALL 2
FI-1220 | Raised access floor — Hall 3 | 20 | 2027-02-08 | 2027-03-05 |  | HALL 3
FI-1230 | Raised access floor — Hall 4 | 20 | 2027-03-08 | 2027-04-06 | FI-1220 | HALL 4
FI-1300 | Hot/cold aisle containment — Halls 1-2 | 25 | 2027-03-29 | 2027-05-03 |  | HALL 1
FI-1310 | Hot/cold aisle containment — Halls 3-4 | 25 | 2027-04-05 | 2027-05-10 |  | HALL 3
FI-1400 | Administration and NOC block fit-out | 40 | 2027-03-15 | 2027-05-12 |  | ADMINISTRATION & NOC BLOCK
FI-1500 | Painting, sealing and final finishes — Halls 1-2 | 20 | 2027-05-04 | 2027-06-01 |  | HALL 1
FI-1510 | Painting, sealing and final finishes — Halls 3-4 | 20 | 2027-05-11 | 2027-06-07 |  | HALL 3
FI-1600 | White-space cleaning to data-centre standard — Halls 1-2 | 12 | 2027-06-01 | 2027-06-16 |  | HALL 1
FI-1610 | White-space cleaning to data-centre standard — Halls 3-4 | 12 | 2027-06-09 | 2027-06-24 |  | HALL 3
FI-1900 | Finishes complete — Section 1 | 0 | 2027-06-17 | 2027-06-17 | FI-1600 | HALL 1 | Milestone
FI-1910 | Finishes complete — Sections 3-4 | 0 | 2027-06-28 | 2027-06-28 | FI-1610 | HALL 3 | Milestone