## Programme Basis
TIETOVERKKO SYSTEMS OY — ELV, BMS/DCIM, FIRE DETECTION AND SUPPRESSION — BASELINE PROGRAMME
PDC-SCH-007 Rev 0 · submitted for the Contractor's acceptance
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Project | Polaris DC-1 — Aviapolis Data Campus, Phase 1, Vantaa
Subcontractor | Tietoverkko Systems Oy
Package | TP-007 — ELV, BMS/DCIM, fire detection and suppression
Subcontract sum | EUR 7,220,000
Data date | 2026-12-01
Calendar | Mon-Fri per PDC-CAL-001, 28 Finnish public holidays, weeks 28-30 shutdown
Programme start | 2026-12-01
Programme finish | 2027-10-07
Total activities | 16
Zone column | Zone names match the labels on PDC-DWG-002 General Arrangement
Site laydown requirement | 400 m2, plus a segregated compound for suppression cylinders. Small in area, but the cylinder store carries a separation distance and cannot share a compound with general materials or hot works.
Note on suppression cylinders | Delivered pressurised. A segregated, signed and bunded compound is required, away from hot works and site traffic.
Prepared by | Tietoverkko Systems Oy planning department

## Activities
ID | Activity Name | Duration (days) | Start | Finish | Predecessors | Zone | Notes
EL-1000 | Instruction to proceed | 0 | 2026-12-01 | 2026-12-01 |  |  | Milestone
EL-1010 | Design development — BMS/DCIM, fire detection and suppression | 40 | 2026-12-01 | 2027-01-29
EL-1100 | Containment and cable pulling — Halls 1-2 | 30 | 2027-03-01 | 2027-04-13 |  | HALL 1
EL-1110 | Containment and cable pulling — Halls 3-4 | 30 | 2027-03-15 | 2027-04-27 |  | HALL 3
EL-1200 | Fire detection installation — Halls 1-2 | 25 | 2027-04-13 | 2027-05-18 |  | HALL 1
EL-1210 | Fire detection installation — Halls 3-4 | 25 | 2027-04-27 | 2027-06-01 |  | HALL 3
EL-1300 | Gas suppression installation — Halls 1-2 | 25 | 2027-05-19 | 2027-06-22 |  | HALL 1 | Cylinder delivery and storage — a segregated compound is required
EL-1310 | Gas suppression installation — Halls 3-4 | 25 | 2027-06-02 | 2027-07-07 |  | HALL 3
EL-1400 | BMS/DCIM head-end and field devices | 40 | 2027-05-03 | 2027-06-29 |  | ADMINISTRATION & NOC BLOCK
EL-1500 | Security, access control and CCTV — internal | 30 | 2027-06-29 | 2027-08-30 |  | SITE WIDE
EL-1600 | L3 point-to-point testing — Section 1 | 20 | 2027-06-24 | 2027-08-12 |  | HALL 1
EL-1610 | L3 point-to-point testing — Sections 2-4 | 25 | 2027-07-08 | 2027-09-01 |  | HALL 3
EL-1700 | L4 integrated systems testing support — Section 1 | 15 | 2027-08-13 | 2027-09-02 | EL-1600 | HALL 1
EL-1710 | L4 integrated systems testing support — Sections 2-4 | 25 | 2027-09-02 | 2027-10-06 | EL-1610 | HALL 3
EL-1900 | ELV complete — Section 1 | 0 | 2027-09-03 | 2027-09-03 | EL-1700 | HALL 1 | Milestone
EL-1910 | ELV complete — Sections 2-4 | 0 | 2027-10-07 | 2027-10-07 | EL-1710 | HALL 3 | Milestone