## Programme Basis
ULKOALUE UUSIMAA OY — EXTERNAL WORKS, SECURITY AND FIBRE ENTRY — BASELINE PROGRAMME
PDC-SCH-008 Rev 0 · submitted for the Contractor's acceptance
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Project | Polaris DC-1 — Aviapolis Data Campus, Phase 1, Vantaa
Subcontractor | Ulkoalue Uusimaa Oy
Package | TP-008 — External works, security and fibre entry
Subcontract sum | EUR 6,910,000
Data date | 2026-03-16
Calendar | Mon-Fri per PDC-CAL-001, 28 Finnish public holidays, weeks 28-30 shutdown
Programme start | 2026-03-16
Programme finish | 2027-11-22
Total activities | 11
Zone column | Zone names match the labels on PDC-DWG-002 General Arrangement
Site laydown requirement | 800 m2, and unusually it is needed at BOTH ends of the programme — early for ducting and fencing materials, late for paving, columns and planting. The late phase directly conflicts with the temporary compound it is meant to replace.
Note on the compound conflict | EX-1500 builds the permanent car park on ground occupied by the temporary staff parking, and EX-1600 cannot start until the compound has gone. The logistics plan must say where parking and offices move to, and when.
Note on fibre diversity | Routes A and B must be physically separate for the whole run (PDC-ER-001) — two trenches and two windows of disruption to the approach.
Prepared by | Ulkoalue Uusimaa Oy planning department

## Activities
ID | Activity Name | Duration (days) | Start | Finish | Predecessors | Zone | Notes
EX-1000 | Instruction to proceed | 0 | 2026-03-16 | 2026-03-16 |  |  | Milestone
EX-1010 | Temporary site fencing and gate installation | 10 | 2026-03-16 | 2026-03-27 |  | SITE WIDE | Runs with TP-001 mobilisation — defines the secure perimeter
EX-1100 | Fibre entry — route A ducting and chambers | 30 | 2026-06-01 | 2026-08-03 |  | SITE WIDE | Diverse route from the north-west; open trench across the approach road
EX-1110 | Fibre entry — route B ducting and chambers | 30 | 2026-08-03 | 2026-09-11 |  | SITE WIDE | Diverse route from the south-east — must not share a trench with route A
EX-1200 | Permanent site roads and hardstanding — phase 1 | 35 | 2027-04-05 | 2027-05-24 |  | SITE WIDE | Replaces the temporary haul road — the delivery route changes on completion
EX-1300 | Perimeter security fence and gates | 30 | 2027-05-25 | 2027-07-06 |  | SITE WIDE | Permanent line — the temporary compound must sit inside it or be relocated
EX-1400 | External lighting and CCTV columns | 25 | 2027-08-02 | 2027-09-03 |  | SITE WIDE
EX-1700 | Gatehouse and weighbridge commissioning | 20 | 2027-09-06 | 2027-10-01 |  | GATEHOUSE & LOADING
EX-1500 | Car parking, footpaths and hardstanding — permanent | 30 | 2027-09-06 | 2027-10-15 |  | SITE WIDE | Built on the ground occupied by the temporary staff parking — the compound must have moved
EX-1600 | Landscaping and reinstatement | 25 | 2027-10-18 | 2027-11-19 |  | SITE WIDE | Cannot start until the temporary compound has been removed
EX-1900 | External works complete | 0 | 2027-11-22 | 2027-11-22 | EX-1600 |  | Milestone