# TENDER OFFER — TP-001 EARTHWORKS, BLASTING, PILING & SUBSTRUCTURE

From: Pohjola Infra Oy

Our reference: PI-7742

To: NordBuild Oy

Project: Polaris DC-1 — Aviapolis Data Campus, Phase 1, Vantaa

Date: 19 March 2026

Validity: 90 days

Synthetic demonstration data. All parties and values are fictional.

____________________________________________________________

## 1. OFFER

We are pleased to offer for the above package on the basis of the documents issued with your enquiry.

| Item | Value |
| --- | --- |
| Tender sum (excluding VAT) | EUR 6,370,980 |
| Currency | EUR |
| Programme, instruction to completion | 31 weeks |
| Validity | 90 days from the date of this offer |
| Form of subcontract | YSE 1998, subject to section 4 below |

## 2. INCLUSIONS

Site clearance, topsoil strip and disposal

Bulk excavation in glacial till and cart away

Rock excavation by blasting in the eastern third of the plot, including vibration monitoring and pre-condition surveys

Pad, strip, direct-to-rock and rock-socketed foundations

Ground beams, pile caps and ground-bearing slab (25 kN/m2, FM2)

Dewatering of perched water in the till

Substation cable basement waterproofing

## 3. EXCLUSIONS

The following are excluded from our tender sum:

Archaeology watching brief excluded

## 4. QUALIFICATIONS

Rock volumes measured from the geotechnical report; boulder horizon between BH-07 and BH-09 included as a lump sum risk allowance

Includes vibration monitoring, pre-condition surveys and neighbour notification

## 5. EXCEPTIONS TO THE FLOW-DOWN TERMS

| Item | Our position | Note |
| --- | --- | --- |
| Liability cap | Subcontract sum | Acceptable |
| Delay damages | Accepted, capped at 10% of subcontract sum | Back-to-back with the main contract cap |
| Payment | 30 days from invoice | Acceptable |

## 6. PROGRAMME AND LEAD TIMES

We require 31 weeks from instruction to completion of our works, sequenced to suit your sectional completion dates.

Long-lead items are stated in our qualifications above where relevant.

## 7. SIGNATURE

For and on behalf of Pohjola Infra Oy

Signed: ..............................  Date: 19 March 2026

____________________________________________________________

*Note: this offer contains exclusions. Please refer to section 3 when comparing it with other returns.*