# TENDER OFFER — TP-002 STRUCTURAL STEEL & PRECAST CONCRETE

From: Nordisk Stål & Element AB

Our reference: NSE-4471

To: NordBuild Oy

Project: Polaris DC-1 — Aviapolis Data Campus, Phase 1, Vantaa

Date: 19 March 2026

Validity: 90 days

Synthetic demonstration data. All parties and values are fictional.

____________________________________________________________

## 1. OFFER

We are pleased to offer for the above package on the basis of the documents issued with your enquiry.

| Item | Value |
| --- | --- |
| Tender sum (excluding VAT) | EUR 8,953,560 |
| Currency | EUR |
| Programme, instruction to completion | 38 weeks |
| Validity | 90 days from the date of this offer |
| Form of subcontract | YSE 1998, subject to section 4 below |

## 2. INCLUSIONS

Design, fabrication, supply and erection of the structural steel frame on the 18 m x 12 m primary grid

Steelwork to the MEP spine, mezzanine and plant support

Precast concrete wall panels including 2-hour fire rating between halls

Metal deck, roof purlins and side rails

Applied fire protection to steel

Temporary works, connections and erection engineering

## 3. EXCLUSIONS

None. Our tender sum covers the full scope of the enquiry.

## 4. QUALIFICATIONS

Includes applied fire protection and erection engineering

Precast panels manufactured in Sweden; assumes ferry logistics unaffected by winter restrictions

## 5. EXCEPTIONS TO THE FLOW-DOWN TERMS

| Item | Our position | Note |
| --- | --- | --- |
| Fluctuation | Fixed price to Base Date + 12 months | Better than the main contract position |
| Liability cap | Subcontract sum | Acceptable |
| Payment | 45 days | Matches our main contract inflow |

## 6. PROGRAMME AND LEAD TIMES

We require 38 weeks from instruction to completion of our works, sequenced to suit your sectional completion dates.

Long-lead items are stated in our qualifications above where relevant.

## 7. SIGNATURE

For and on behalf of Nordisk Stål & Element AB

Signed: ..............................  Date: 19 March 2026