# TENDER OFFER — TP-003 ENVELOPE — CLADDING, ROOFING & LOUVRES

From: Salo Julkisivu Oy

Our reference: SJ-1187

To: NordBuild Oy

Project: Polaris DC-1 — Aviapolis Data Campus, Phase 1, Vantaa

Date: 19 March 2026

Validity: 90 days

Synthetic demonstration data. All parties and values are fictional.

____________________________________________________________

## 1. OFFER

We are pleased to offer for the above package on the basis of the documents issued with your enquiry.

| Item | Value |
| --- | --- |
| Tender sum (excluding VAT) | EUR 5,627,160 |
| Currency | EUR |
| Programme, instruction to completion | 28 weeks |
| Validity | 90 days from the date of this offer |
| Form of subcontract | YSE 1998, subject to section 4 below |

## 2. INCLUSIONS

Insulated composite cladding, U = 0.17 W/m2K

Warm roof build-up, U = 0.09 W/m2K

Acoustic louvres to cooling intake and discharge

Personnel and equipment doors including 3.0 x 3.5 m equipment doors

Rainwater goods and syphonic drainage

Airtightness works and testing to q50 <= 1.0 m3/(h.m2)

Roof safety line, walkways and access hatches

## 3. EXCLUSIONS

None. Our tender sum covers the full scope of the enquiry.

## 4. QUALIFICATIONS

Includes airtightness testing to q50 <= 1.0 and remedial works, and warrants the acoustic performance of the louvres

Winter installation allowance included

## 5. EXCEPTIONS TO THE FLOW-DOWN TERMS

| Item | Our position | Note |
| --- | --- | --- |
| Performance warranty | System warranty, 25 years | Matches the Employer's Requirements |
| Payment | 30 days | Acceptable |
| Delay damages | Accepted back-to-back | Acceptable |

## 6. PROGRAMME AND LEAD TIMES

We require 28 weeks from instruction to completion of our works, sequenced to suit your sectional completion dates.

Long-lead items are stated in our qualifications above where relevant.

## 7. SIGNATURE

For and on behalf of Salo Julkisivu Oy

Signed: ..............................  Date: 19 March 2026