# TENDER OFFER — TP-006 ELECTRICAL — HV/MV, TRANSFORMERS, UPS & GENERATORS

From: Voima Electric Oy

Our reference: VE-9006

To: NordBuild Oy

Project: Polaris DC-1 — Aviapolis Data Campus, Phase 1, Vantaa

Date: 19 March 2026

Validity: 90 days

Synthetic demonstration data. All parties and values are fictional.

____________________________________________________________

## 1. OFFER

We are pleased to offer for the above package on the basis of the documents issued with your enquiry.

| Item | Value |
| --- | --- |
| Tender sum (excluding VAT) | EUR 27,997,200 |
| Currency | EUR |
| Programme, instruction to completion | 54 weeks |
| Validity | 90 days from the date of this offer |
| Form of subcontract | YSE 1998, subject to section 4 below |

## 2. INCLUSIONS

110 kV termination, metering and protection to the DNO interface

110/20 kV transformers (2 nr, 16 MVA, N+1)

20 kV ring main switchboard and protection relays

Hall substations 20/0.4 kV (4 nr, 3.3 MVA)

Standby generators (8 nr, 2.5 MVA) with acoustic enclosures, paralleling, ATS and 48-hour fuel system

UPS modules (16 nr, 1000 kVA, N+1) and battery systems

LV switchboards, overhead busway, containment and small power

Earthing, bonding, lightning protection and energy metering

Electrical commissioning support to L4 and L5

## 3. EXCLUSIONS

None. Our tender sum covers the full scope of the enquiry.

## 4. QUALIFICATIONS

Includes the 110 kV termination, metering and the protection coordination study for DNO approval

Confirms the DNO's earliest firm energisation of 12 March 2027 and has programmed commissioning accordingly

Recommends immediate release of the transformer order

## 5. EXCEPTIONS TO THE FLOW-DOWN TERMS

| Item | Our position | Note |
| --- | --- | --- |
| Delay damages | Accepted, capped at 10% of subcontract sum | Back-to-back with our cap |
| Liability cap | Subcontract sum | Acceptable |
| Payment | 45 days | Matches our inflow |

## 6. PROGRAMME AND LEAD TIMES

We require 54 weeks from instruction to completion of our works, sequenced to suit your sectional completion dates.

Long-lead items are stated in our qualifications above where relevant.

## 7. SIGNATURE

For and on behalf of Voima Electric Oy

Signed: ..............................  Date: 19 March 2026