# Basis of Schedule — Polaris DC-1 Baseline

Generated · 2026-08-01

# 1. 1. Executive Summary

The Polaris DC-1 baseline programme comprises 139 activities across a 335-working-day deterministic makespan (Monte-Carlo P50: 385 working days). This covers the design, procurement, construction, commissioning, and handover of four data halls (DH1–DH4), shared infrastructure (substation, generator farm, cooling spine, gatehouse), an admin/NOC building, and external works at the Aviapolis Data Campus, Vantaa, Finland.

The programme is built on the Critical Path Method (CPM), with all construction durations derived from NordBuild's historical productivity data (ev_1: 990 analogs across 5 projects) and all procurement lead times taken directly from the project's Procurement Lead Time Register (PDC-LT-001).

Contract dates: Commencement 2 March 2026. Sectional completion S1 at 14 months (2 May 2027), S2 at 16 months, S3 at 19 months, S4 / Time for Completion at 22 months (2 January 2028).

Cost loading: €82,970,863 of the €92,400,000 Accepted Contract Amount is loaded onto programme activities (89.8%). The remaining €9,429,137 (10.2%) consists of risk allowances, time-related preliminaries, financial instruments, regulatory appointments, contingency, and BOQ extraction rounding — none of which are attributable to a single construction activity. Every BOQ line item in Sections A through J has been mapped to one or more programme activities. The full reconciliation is in Section 12.

Labour: €12,993,320 loaded at NordBuild's internal resource rates across 22 resource groups. Non-labour (materials, plant, sublet): €70,046,127 loaded as P6 expenses. The S-curve and histogram represent cost to complete — NordBuild's cost, not sell value.