## Agent Outputs
No agent outputs.

## Schedule Table
Schedule
ID | Activity | Duration (wd) | Start | Finish | Total Float | Critical | Predecessors | Resource Group | No. of Crews | Members per Crew | BOQ Quantity | Package Cost
1 | PROJECT COMMENCEMENT | 0 | 2026-03-01 | 2026-03-01 | 0 | Yes
10 | Mobilisation & Site Setup | 8 | 2026-03-01 | 2026-03-10 | 0 | Yes | 1FS | General Labour | 1 | 6 |  | 1470831
12 | Planning Conditions Discharge | 10 | 2026-03-01 | 2026-03-12 | 21 |  | 1FS | Management | 1 | 2 |  | 15000
30 | LT-01 Advance Purchase — Transformer Order | 5 | 2026-03-01 | 2026-03-05 | 88 |  | 1FS | Procurement | 1 | 2 |  | 5000
11 | Site Survey & Setting Out | 5 | 2026-03-11 | 2026-03-17 | 21 |  | 10FS | Surveyor | 1 | 3 |  | 12000
13 | Finavia Crane Permits — Application | 5 | 2026-03-11 | 2026-03-17 | 0 | Yes | 10FS | Management | 1 | 1 |  | 3000
20 | Architectural Design Development | 25 | 2026-03-15 | 2026-04-16 | 21 |  | 12FS | Design Team | 1 | 4 |  | 75000
14 | Finavia Crane Permits — Clearance Period | 21 | 2026-03-18 | 2026-04-15 | 0 | Yes | 13FS | Management | 1 | 1
22 | MEP Design Development | 25 | 2026-03-22 | 2026-04-23 | 83 |  | 20SS+5 | Design Team | 1 | 5 |  | 100000
23 | Electrical & ELV Design | 20 | 2026-03-22 | 2026-04-16 | 126 |  | 20SS+5 | Design Team | 1 | 4 |  | 80000
21 | Structural Design Development | 20 | 2026-03-29 | 2026-04-23 | 21 |  | 20SS+10 | Design Team | 1 | 4 |  | 60000
24 | Civil & External Works Design | 15 | 2026-04-05 | 2026-04-23 | 132 |  | 21SS+5 | Design Team | 1 | 3 |  | 35000
40 | Bulk Earthworks — Site Strip & Cut | 53 | 2026-04-16 | 2026-06-29 | 0 | Yes | 11FS,14FS | Earthworks | 2 | 8 |  | 834747
35 | LT-05 UPS Procurement | 5 | 2026-04-19 | 2026-04-23 | 156 |  | 23FS | Procurement | 1 | 2 |  | 5000
36 | LT-06 Busway Procurement | 5 | 2026-04-19 | 2026-04-23 | 126 |  | 23FS | Procurement | 1 | 2 |  | 5000
25 | Design Gate Review — Engineer (14-day) | 14 | 2026-04-26 | 2026-05-13 | 132 |  | 20FS,21FS,22FS,23FS,24FS | Management | 1 | 1 |  | 5000
33 | LT-04 Chiller & CRAH Procurement | 5 | 2026-04-26 | 2026-04-30 | 174 |  | 22FS | Procurement | 1 | 2 |  | 10000
34 | LT-11 Structural Steel Procurement | 5 | 2026-04-26 | 2026-04-30 | 21 |  | 21FS | Procurement | 1 | 2 |  | 8000
41 | Rock Excavation & Blasting | 31 | 2026-04-30 | 2026-06-11 | 0 | Yes | 40SS+10 | Blasting | 2 | 8 |  | 696881
31 | LT-02 MV Switchgear Procurement | 5 | 2026-05-03 | 2026-05-07 | 83 |  | 22FS+5 | Procurement | 1 | 2 |  | 8000
32 | LT-03 Generator Procurement | 5 | 2026-05-03 | 2026-05-07 | 131 |  | 22FS+5 | Procurement | 1 | 2 |  | 8000
43 | Substation & Gen Pad Foundations | 15 | 2026-06-07 | 2026-06-25 | 87 |  | 41FS-5 | RC Frame | 1 | 8 |  | 213863
45 | Gatehouse & Compound Foundations | 8 | 2026-06-14 | 2026-06-23 | 226 |  | 41FS | RC Frame | 1 | 6 |  | 160397
50 | DH1 — Rock-Socketed Bored Piles | 53 | 2026-06-14 | 2026-08-25 | 0 | Yes | 41FS | Piling | 2 | 6 |  | 356160
42 | Trench Excavation — Site Services | 11 | 2026-06-21 | 2026-07-05 | 196 |  | 41FS+5 | Earthworks | 1 | 8 |  | 85000
103 | Gatehouse Construction | 20 | 2026-06-24 | 2026-07-21 | 226 |  | 45FS | RC Frame | 1 | 4 |  | 275431
44 | Cooling Spine Pipe Rack Fnds | 8 | 2026-06-28 | 2026-07-07 | 87 |  | 43FS | RC Frame | 1 | 6 |  | 160397
100 | Substation Building Construction | 30 | 2026-06-28 | 2026-08-06 | 148 |  | 43FS | RC Frame | 1 | 6 |  | 803479
101 | Gen Compound Civil & Enclosure | 25 | 2026-06-28 | 2026-07-30 | 206 |  | 43FS | RC Frame | 1 | 6 |  | 553611
51 | DH2 — Rock-Socketed Bored Piles | 53 | 2026-07-05 | 2026-09-15 | 0 | Yes | 50SS+15 | Piling | 2 | 6 |  | 356160
104 | Shared Infra — UG Services & Ducts | 15 | 2026-07-06 | 2026-07-26 | 196 |  | 42FS | Earthworks | 1 | 6 |  | 734942
102 | Cooling Spine Structural Frame | 15 | 2026-07-08 | 2026-07-28 | 87 |  | 44FS | Steel Erection | 1 | 6 |  | 1434731
55 | DH2 Pile Caps & Ground Beams | 13 | 2026-07-12 | 2026-07-28 | 0 | Yes | 51SS+5 | RC Frame | 2 | 8 |  | 157679
52 | DH3 — Rock-Socketed Bored Piles | 53 | 2026-07-19 | 2026-09-29 | 22 |  | 51SS+10 | Piling | 2 | 6 |  | 356160
56 | DH3 Pile Caps & Ground Beams | 13 | 2026-07-26 | 2026-08-11 | 27 |  | 52SS+5 | RC Frame | 2 | 8 |  | 157679
200 | Access Roads & Parking Construction | 15 | 2026-07-27 | 2026-08-16 | 196 |  | 104FS | External Works | 2 | 6 |  | 1588778
59 | DH2 Foundation Waterproofing | 11 | 2026-07-29 | 2026-08-12 | 0 | Yes | 55FS | Waterproofing | 1 | 4 |  | 39873
118 | Cooling Spine — Pipework & Distr. | 44 | 2026-07-29 | 2026-09-28 | 87 |  | 102FS | Mech Pipe | 2 | 6 |  | 2400766
53 | DH4 — Rock-Socketed Bored Piles | 53 | 2026-08-02 | 2026-10-13 | 22 |  | 52SS+10 | Piling | 2 | 6 |  | 356160
57 | DH4 Pile Caps & Ground Beams | 13 | 2026-08-09 | 2026-08-25 | 22 |  | 53SS+5 | RC Frame | 2 | 8 |  | 157679
60 | DH3 Foundation Waterproofing | 11 | 2026-08-09 | 2026-08-23 | 27 |  | 56SS+10 | Waterproofing | 1 | 4 |  | 39873
63 | DH2 Ground Floor Slab | 22 | 2026-08-13 | 2026-09-13 | 0 | Yes | 59FS | RC Frame | 2 | 8 |  | 589399
201 | External Lighting & Security | 10 | 2026-08-17 | 2026-08-30 | 198 |  | 200FS | ELV | 1 | 4 |  | 523917
202 | Perimeter Fencing & Gates | 10 | 2026-08-17 | 2026-08-30 | 198 |  | 200FS | External Works | 1 | 4 |  | 472766
203 | Landscaping & Soft Works | 12 | 2026-08-17 | 2026-09-01 | 196 |  | 200FS | External Works | 1 | 4 |  | 212311
61 | DH4 Foundation Waterproofing | 11 | 2026-08-23 | 2026-09-06 | 22 |  | 57SS+10 | Waterproofing | 1 | 4 |  | 39873
54 | DH1 Pile Caps & Ground Beams | 13 | 2026-08-26 | 2026-09-13 | 5 |  | 50FS | RC Frame | 2 | 8 |  | 157679
64 | DH3 Ground Floor Slab | 22 | 2026-08-30 | 2026-09-28 | 27 |  | 60SS+15 | RC Frame | 2 | 8 |  | 589399
65 | DH4 Ground Floor Slab | 22 | 2026-09-13 | 2026-10-12 | 22 |  | 61SS+15 | RC Frame | 2 | 8 |  | 589399
58 | DH1 Foundation Waterproofing | 11 | 2026-09-14 | 2026-09-28 | 5 |  | 54FS | Waterproofing | 1 | 4 |  | 39873
71 | DH2 — GF Steel Erection | 8 | 2026-09-23 | 2026-10-04 | 0 | Yes | 63FS+7 | Steel Erection | 2 | 8 |  | 369723
62 | DH1 Ground Floor Slab | 22 | 2026-09-29 | 2026-10-28 | 5 |  | 58FS | RC Frame | 2 | 8 |  | 589399
140 | DH1 — Chiller Installation & Piping | 10 | 2026-09-29 | 2026-10-12 | 167 |  | 118FS,33SS+105 | Mech HVAC | 1 | 4 |  | 5244460
73 | DH2 — Upper Floor & Roof Steel | 40 | 2026-10-05 | 2026-11-29 | 0 | Yes | 71FS | Steel Erection | 2 | 10 |  | 575893
79 | DH2 — Precast Plank Floors | 20 | 2026-10-19 | 2026-11-15 | 33 |  | 73SS+10 | Precast | 2 | 6 |  | 442610
82 | Admin/NOC Ground Slab | 12 | 2026-11-03 | 2026-11-18 | 53 |  | 65FS+15 | RC Frame | 1 | 8 |  | 457560
123 | Transformer & MV Switchgear Install | 5 | 2026-11-08 | 2026-11-12 | 83 |  | 100FS,30SS+175,31SS+135 | Electrical | 2 | 4 |  | 5393553
70 | DH1 — GF Steel Erection | 8 | 2026-11-09 | 2026-11-18 | 5 |  | 62FS+7,25FS,34SS+125 | Steel Erection | 2 | 8 |  | 369723
124 | Main LV Switchgear Installation | 3 | 2026-11-15 | 2026-11-17 | 83 |  | 123FS | Electrical | 1 | 4 |  | 247326
125 | Generator & UPS Installation | 5 | 2026-11-15 | 2026-11-19 | 131 |  | 101FS,32SS+140,35SS+125 | Mech | 2 | 4 |  | 15046652
74 | DH3 — GF Steel Erection | 8 | 2026-11-16 | 2026-11-25 | 0 | Yes | 64FS+7,73FS-10 | Steel Erection | 2 | 8 |  | 369723
91 | DH2 — Ext Wall Insul & Cladding | 28 | 2026-11-16 | 2026-12-23 | 33 |  | 79FS | Envelope | 2 | 6 |  | 577814
72 | DH1 — Upper Floor & Roof Steel | 40 | 2026-11-19 | 2027-01-13 | 5 |  | 70FS | Steel Erection | 2 | 10 |  | 575893
75 | DH4 — GF Steel Erection | 8 | 2026-11-23 | 2026-12-02 | 0 | Yes | 65FS+7,74FS-3 | Steel Erection | 2 | 8 |  | 369723
95 | DH2 — Roof Waterproofing & Insul | 22 | 2026-11-23 | 2026-12-22 | 33 |  | 91SS+5 | Roofing | 2 | 4 |  | 745988
76 | DH3 — Upper Floor & Roof Steel | 40 | 2026-11-26 | 2027-01-20 | 5 |  | 74FS | Steel Erection | 2 | 10 |  | 575893
83 | Admin/NOC Steel Frame & Precast | 25 | 2026-11-30 | 2027-01-03 | 53 |  | 82FS+7 | Steel Erection | 1 | 8 |  | 285402
111 | DH2 — Cable Trays & Containment | 35 | 2026-11-30 | 2027-01-17 | 50 |  | 95SS+5 | Electrical | 2 | 8 |  | 762450
115 | DH2 — HVAC Ductwork & AHU Install | 35 | 2026-11-30 | 2027-01-17 | 43 |  | 95SS+5 | Mech HVAC | 2 | 8 |  | 624101
77 | DH4 — Upper Floor & Roof Steel | 40 | 2026-12-03 | 2027-01-27 | 0 | Yes | 75FS | Steel Erection | 2 | 10 |  | 575893
78 | DH1 — Precast Plank Floors | 20 | 2026-12-03 | 2026-12-30 | 5 |  | 72SS+10 | Precast | 2 | 6 |  | 442610
120 | DH2 — Riser Piping | 22 | 2026-12-07 | 2027-01-05 | 33 |  | 95SS+10,118FS-5 | Mech Pipe | 2 | 6 |  | 640427
80 | DH3 — Precast Plank Floors | 20 | 2026-12-10 | 2027-01-06 | 5 |  | 76SS+10 | Precast | 2 | 6 |  | 442610
81 | DH4 — Precast Plank Floors | 20 | 2026-12-17 | 2027-01-13 | 0 | Yes | 77SS+10 | Precast | 2 | 6 |  | 442610
90 | DH1 — Ext Wall Insul & Cladding | 28 | 2026-12-31 | 2027-02-08 | 5 |  | 78FS | Envelope | 2 | 6 |  | 577814
105 | Admin/NOC Envelope | 20 | 2027-01-04 | 2027-01-31 | 53 |  | 83FS | Envelope | 1 | 6 |  | 304969
92 | DH3 — Ext Wall Insul & Cladding | 28 | 2027-01-07 | 2027-02-15 | 5 |  | 80FS | Envelope | 2 | 6 |  | 577814
94 | DH1 — Roof Waterproofing & Insul | 22 | 2027-01-07 | 2027-02-07 | 5 |  | 90SS+5 | Roofing | 2 | 4 |  | 745988
131 | DH2 — CRAH Fan-Wall Installation | 33 | 2027-01-11 | 2027-02-24 | 43 |  | 115FS-5,120SS+5 | Mech HVAC | 2 | 6 |  | 560400
142 | DH2 — Electrical Dist. Boards | 14 | 2027-01-11 | 2027-01-28 | 50 |  | 111FS-5 | Electrical | 2 | 6 |  | 356784
146 | DH2 — Busway & Power Feeders | 14 | 2027-01-11 | 2027-01-28 | 50 |  | 111FS-5 | Electrical | 2 | 6 |  | 155415
151 | DH2 — ELV/BMS/Fire Detection | 20 | 2027-01-11 | 2027-02-07 | 71 |  | 111FS-5 | ELV | 2 | 6 |  | 526459
161 | DH2 — Raised Access Flooring | 19 | 2027-01-11 | 2027-02-04 | 84 |  | 115FS-5 | Fit-Out | 2 | 6 |  | 432225
93 | DH4 — Ext Wall Insul & Cladding | 28 | 2027-01-14 | 2027-02-22 | 0 | Yes | 81FS | Envelope | 2 | 6 |  | 577814
96 | DH3 — Roof Waterproofing & Insul | 22 | 2027-01-14 | 2027-02-14 | 5 |  | 92SS+5 | Roofing | 2 | 4 |  | 745988
110 | DH1 — Cable Trays & Containment | 35 | 2027-01-14 | 2027-03-03 | 12 |  | 94SS+5,25FS | Electrical | 2 | 8 |  | 762450
114 | DH1 — HVAC Ductwork & AHU Install | 35 | 2027-01-14 | 2027-03-03 | 5 |  | 94SS+5,25FS | Mech HVAC | 2 | 8 |  | 624101
97 | DH4 — Roof Waterproofing & Insul | 22 | 2027-01-21 | 2027-02-21 | 0 | Yes | 93SS+5 | Roofing | 2 | 4 |  | 745988
112 | DH3 — Cable Trays & Containment | 35 | 2027-01-21 | 2027-03-10 | 12 |  | 96SS+5 | Electrical | 2 | 8 |  | 762450
116 | DH3 — HVAC Ductwork & AHU Install | 35 | 2027-01-21 | 2027-03-10 | 5 |  | 96SS+5 | Mech HVAC | 2 | 8 |  | 624101
119 | DH1 — Riser Piping (Htg & Clg) | 22 | 2027-01-21 | 2027-02-21 | 25 |  | 94SS+10,118FS-5 | Mech Pipe | 2 | 6 |  | 640427
113 | DH4 — Cable Trays & Containment | 35 | 2027-01-28 | 2027-03-17 | 7 |  | 97SS+5 | Electrical | 2 | 8 |  | 762450
117 | DH4 — HVAC Ductwork & AHU Install | 35 | 2027-01-28 | 2027-03-17 | 0 | Yes | 97SS+5 | Mech HVAC | 2 | 8 |  | 624101
121 | DH3 — Riser Piping | 22 | 2027-01-28 | 2027-02-28 | 10 |  | 96SS+10,120SS+15 | Mech Pipe | 2 | 6 |  | 640427
171 | DH2 — Electrical Testing & Dead Bus | 12 | 2027-01-31 | 2027-02-15 | 50 |  | 142FS,146FS | Commissioning | 1 | 4 |  | 85259
164 | Admin/NOC — Fit-Out | 25 | 2027-02-01 | 2027-03-07 | 53 |  | 105FS | Fit-Out | 2 | 8 |  | 2474594
122 | DH4 — Riser Piping | 22 | 2027-02-18 | 2027-03-21 | 10 |  | 97SS+10,121SS+15 | Mech Pipe | 2 | 6 |  | 640427
130 | DH1 — CRAH Fan-Wall Installation | 33 | 2027-02-25 | 2027-04-12 | 5 |  | 114FS-5,119SS+5 | Mech HVAC | 2 | 6 |  | 560400
141 | DH1 — Electrical Dist. Boards | 14 | 2027-02-25 | 2027-03-16 | 12 |  | 110FS-5,124FS | Electrical | 2 | 6 |  | 356784
145 | DH1 — Busway & Power Feeders | 14 | 2027-02-25 | 2027-03-16 | 12 |  | 110FS-5,124FS,36SS+110 | Electrical | 2 | 6 |  | 155415
150 | DH1 — ELV/BMS/Fire Detection | 20 | 2027-02-25 | 2027-03-24 | 33 |  | 110FS-5 | ELV | 2 | 6 |  | 526459
160 | DH1 — Raised Access Flooring | 19 | 2027-02-25 | 2027-03-23 | 34 |  | 114FS-5 | Fit-Out | 2 | 6 |  | 432225
176 | DH2 — HVAC Commissioning & Balancing | 15 | 2027-02-25 | 2027-03-17 | 43 |  | 131FS,171FS | Commissioning | 1 | 6 |  | 34104
132 | DH3 — CRAH Fan-Wall Installation | 33 | 2027-03-04 | 2027-04-19 | 5 |  | 116FS-5,121SS+5 | Mech HVAC | 2 | 6 |  | 560400
143 | DH3 — Electrical Dist. Boards | 14 | 2027-03-04 | 2027-03-23 | 12 |  | 112FS-5 | Electrical | 2 | 6 |  | 356784
147 | DH3 — Busway & Power Feeders | 14 | 2027-03-04 | 2027-03-23 | 12 |  | 112FS-5 | Electrical | 2 | 6 |  | 155415
152 | DH3 — ELV/BMS/Fire Detection | 20 | 2027-03-04 | 2027-03-31 | 33 |  | 112FS-5 | ELV | 2 | 6 |  | 526459
162 | DH3 — Raised Access Flooring | 19 | 2027-03-04 | 2027-03-30 | 46 |  | 116FS-5 | Fit-Out | 2 | 6 |  | 432225
210 | Admin/NOC Commissioning Sign-off | 10 | 2027-03-08 | 2027-03-21 | 53 |  | 164FS | Commissioning | 1 | 3 |  | 35000
133 | DH4 — CRAH Fan-Wall Installation | 33 | 2027-03-11 | 2027-04-26 | 0 | Yes | 117FS-5,122SS+5 | Mech HVAC | 2 | 6 |  | 560400
144 | DH4 — Electrical Dist. Boards | 14 | 2027-03-11 | 2027-03-30 | 7 |  | 113FS-5 | Electrical | 2 | 6 |  | 356784
148 | DH4 — Busway & Power Feeders | 14 | 2027-03-11 | 2027-03-30 | 7 |  | 113FS-5 | Electrical | 2 | 6 |  | 155415
153 | DH4 — ELV/BMS/Fire Detection | 20 | 2027-03-11 | 2027-04-07 | 28 |  | 113FS-5 | ELV | 2 | 6 |  | 526459
163 | DH4 — Raised Access Flooring | 19 | 2027-03-11 | 2027-04-06 | 41 |  | 117FS-5 | Fit-Out | 2 | 6 |  | 432225
170 | DH1 — Electrical Testing & Dead Bus | 12 | 2027-03-17 | 2027-04-01 | 12 |  | 141FS,145FS | Commissioning | 1 | 4 |  | 85259
190 | DH2 — BMS/BAS Integ. Func. Test | 12 | 2027-03-18 | 2027-04-04 | 43 |  | 151FS,176FS | Commissioning | 1 | 4 |  | 626339
191 | DH2 — Fire Alarm Integ. Test | 7 | 2027-03-18 | 2027-03-28 | 48 |  | 151FS,176FS | Commissioning | 1 | 3 |  | 13642
172 | DH3 — Electrical Testing & Dead Bus | 12 | 2027-03-24 | 2027-04-08 | 12 |  | 143FS,147FS | Commissioning | 1 | 4 |  | 85259
173 | DH4 — Electrical Testing & Dead Bus | 12 | 2027-03-31 | 2027-04-15 | 7 |  | 144FS,148FS | Commissioning | 1 | 4 |  | 85259
182 | DH1 — Generator Load-Bank Test | 8 | 2027-04-04 | 2027-04-13 | 36 |  | 125FS,170FS | Commissioning | 1 | 3 |  | 1033664
192 | Section 2 Completion — Readiness Review | 5 | 2027-04-05 | 2027-04-11 | 43 |  | 190FS,191FS,161FS | Management | 1 | 2 |  | 151088
6 | SECTION 2 COMPLETION (DH2 + Plant) | 0 | 2027-04-12 | 2027-04-12 | 43 |  | 192FS
175 | DH1 — HVAC Commissioning & Balancing | 15 | 2027-04-13 | 2027-05-03 | 5 |  | 130FS,170FS | Commissioning | 1 | 6 |  | 34104
177 | DH3 — HVAC Commissioning & Balancing | 15 | 2027-04-20 | 2027-05-10 | 5 |  | 132FS,172FS | Commissioning | 1 | 6 |  | 34104
178 | DH4 — HVAC Commissioning & Balancing | 15 | 2027-04-27 | 2027-05-17 | 0 | Yes | 133FS,173FS | Commissioning | 1 | 6 |  | 34104
180 | DH1 — BMS/BAS Integ. Func. Test | 12 | 2027-05-04 | 2027-05-19 | 5 |  | 150FS,175FS,160FS | Commissioning | 1 | 4 |  | 626339
181 | DH1 — Fire Alarm Integ. Test | 7 | 2027-05-04 | 2027-05-12 | 15 |  | 150FS,175FS | Commissioning | 1 | 3 |  | 13642
205 | District Heating Commissioning (72hr) | 5 | 2027-05-04 | 2027-05-10 | 17 |  | 175FS | Commissioning | 1 | 3 |  | 4075507
193 | DH3 — BMS/BAS Integ. Func. Test | 12 | 2027-05-11 | 2027-05-26 | 5 |  | 152FS,177FS | Commissioning | 1 | 4 |  | 626339
194 | DH3 — Fire Alarm Integ. Test | 7 | 2027-05-11 | 2027-05-19 | 10 |  | 152FS,177FS | Commissioning | 1 | 3 |  | 13642
196 | DH4 — BMS/BAS Integ. Func. Test | 12 | 2027-05-18 | 2027-06-02 | 0 | Yes | 153FS,178FS | Commissioning | 1 | 4 |  | 626339
197 | DH4 — Fire Alarm Integ. Test | 7 | 2027-05-18 | 2027-05-26 | 5 |  | 153FS,178FS | Commissioning | 1 | 3 |  | 13642
206 | Acoustic Testing & IEQ Validation | 5 | 2027-05-20 | 2027-05-26 | 5 |  | 180FS | Commissioning | 1 | 3 |  | 20000
183 | DH1 — S1 Completion Readiness Review | 5 | 2027-05-27 | 2027-06-02 | 5 |  | 181FS,182FS,103FS,140FS,205FS,206FS | Management | 1 | 2 |  | 151088
195 | Section 3 Completion — Readiness Review | 5 | 2027-05-27 | 2027-06-02 | 5 |  | 193FS,194FS,162FS | Management | 1 | 2 |  | 151088
5 | SECTION 1 COMPLETION (DH1 + Shared Infra) | 0 | 2027-06-03 | 2027-06-03 | 5 |  | 183FS
7 | SECTION 3 COMPLETION (DH3 + Plant) | 0 | 2027-06-03 | 2027-06-03 | 5 |  | 195FS
211 | Section 4 — Final Snagging & Readiness | 5 | 2027-06-03 | 2027-06-09 | 0 | Yes | 196FS,197FS,210FS,201FS,202FS,203FS,163FS | Management | 1 | 2 |  | 151088
8 | PROJECT COMPLETION (S4: DH4 + Admin/NOC + External) | 0 | 2027-06-10 | 2027-06-10 | 0 | Yes | 211FS,5FF,6FF,7FF

## Gantt (weekly)
Gantt
ID | Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W54 | W55 | W56 | W57 | W58 | W59 | W60 | W61 | W62 | W63 | W64 | W65 | W66 | W67
1 | PROJECT COMMENCEMENT
10 | Mobilisation & Site Setup
12 | Planning Conditions Discharge
30 | LT-01 Advance Purchase — Transformer Order
11 | Site Survey & Setting Out
13 | Finavia Crane Permits — Application
20 | Architectural Design Development
14 | Finavia Crane Permits — Clearance Period
22 | MEP Design Development
23 | Electrical & ELV Design
21 | Structural Design Development
24 | Civil & External Works Design
40 | Bulk Earthworks — Site Strip & Cut
35 | LT-05 UPS Procurement
36 | LT-06 Busway Procurement
25 | Design Gate Review — Engineer (14-day)
33 | LT-04 Chiller & CRAH Procurement
34 | LT-11 Structural Steel Procurement
41 | Rock Excavation & Blasting
31 | LT-02 MV Switchgear Procurement
32 | LT-03 Generator Procurement
43 | Substation & Gen Pad Foundations
45 | Gatehouse & Compound Foundations
50 | DH1 — Rock-Socketed Bored Piles
42 | Trench Excavation — Site Services
103 | Gatehouse Construction
44 | Cooling Spine Pipe Rack Fnds
100 | Substation Building Construction
101 | Gen Compound Civil & Enclosure
51 | DH2 — Rock-Socketed Bored Piles
104 | Shared Infra — UG Services & Ducts
102 | Cooling Spine Structural Frame
55 | DH2 Pile Caps & Ground Beams
52 | DH3 — Rock-Socketed Bored Piles
56 | DH3 Pile Caps & Ground Beams
200 | Access Roads & Parking Construction
59 | DH2 Foundation Waterproofing
118 | Cooling Spine — Pipework & Distr.
53 | DH4 — Rock-Socketed Bored Piles
57 | DH4 Pile Caps & Ground Beams
60 | DH3 Foundation Waterproofing
63 | DH2 Ground Floor Slab
201 | External Lighting & Security
202 | Perimeter Fencing & Gates
203 | Landscaping & Soft Works
61 | DH4 Foundation Waterproofing
54 | DH1 Pile Caps & Ground Beams
64 | DH3 Ground Floor Slab
65 | DH4 Ground Floor Slab
58 | DH1 Foundation Waterproofing
71 | DH2 — GF Steel Erection
62 | DH1 Ground Floor Slab
140 | DH1 — Chiller Installation & Piping
73 | DH2 — Upper Floor & Roof Steel
79 | DH2 — Precast Plank Floors
82 | Admin/NOC Ground Slab
123 | Transformer & MV Switchgear Install
70 | DH1 — GF Steel Erection
124 | Main LV Switchgear Installation
125 | Generator & UPS Installation
74 | DH3 — GF Steel Erection
91 | DH2 — Ext Wall Insul & Cladding
72 | DH1 — Upper Floor & Roof Steel
75 | DH4 — GF Steel Erection
95 | DH2 — Roof Waterproofing & Insul
76 | DH3 — Upper Floor & Roof Steel
83 | Admin/NOC Steel Frame & Precast
111 | DH2 — Cable Trays & Containment
115 | DH2 — HVAC Ductwork & AHU Install
77 | DH4 — Upper Floor & Roof Steel
78 | DH1 — Precast Plank Floors
120 | DH2 — Riser Piping
80 | DH3 — Precast Plank Floors
81 | DH4 — Precast Plank Floors
90 | DH1 — Ext Wall Insul & Cladding
105 | Admin/NOC Envelope
92 | DH3 — Ext Wall Insul & Cladding
94 | DH1 — Roof Waterproofing & Insul
131 | DH2 — CRAH Fan-Wall Installation
142 | DH2 — Electrical Dist. Boards
146 | DH2 — Busway & Power Feeders
151 | DH2 — ELV/BMS/Fire Detection
161 | DH2 — Raised Access Flooring
93 | DH4 — Ext Wall Insul & Cladding
96 | DH3 — Roof Waterproofing & Insul
110 | DH1 — Cable Trays & Containment
114 | DH1 — HVAC Ductwork & AHU Install
97 | DH4 — Roof Waterproofing & Insul
112 | DH3 — Cable Trays & Containment
116 | DH3 — HVAC Ductwork & AHU Install
119 | DH1 — Riser Piping (Htg & Clg)
113 | DH4 — Cable Trays & Containment
117 | DH4 — HVAC Ductwork & AHU Install
121 | DH3 — Riser Piping
171 | DH2 — Electrical Testing & Dead Bus
164 | Admin/NOC — Fit-Out
122 | DH4 — Riser Piping
130 | DH1 — CRAH Fan-Wall Installation
141 | DH1 — Electrical Dist. Boards
145 | DH1 — Busway & Power Feeders
150 | DH1 — ELV/BMS/Fire Detection
160 | DH1 — Raised Access Flooring
176 | DH2 — HVAC Commissioning & Balancing
132 | DH3 — CRAH Fan-Wall Installation
143 | DH3 — Electrical Dist. Boards
147 | DH3 — Busway & Power Feeders
152 | DH3 — ELV/BMS/Fire Detection
162 | DH3 — Raised Access Flooring
210 | Admin/NOC Commissioning Sign-off
133 | DH4 — CRAH Fan-Wall Installation
144 | DH4 — Electrical Dist. Boards
148 | DH4 — Busway & Power Feeders
153 | DH4 — ELV/BMS/Fire Detection
163 | DH4 — Raised Access Flooring
170 | DH1 — Electrical Testing & Dead Bus
190 | DH2 — BMS/BAS Integ. Func. Test
191 | DH2 — Fire Alarm Integ. Test
172 | DH3 — Electrical Testing & Dead Bus
173 | DH4 — Electrical Testing & Dead Bus
182 | DH1 — Generator Load-Bank Test
192 | Section 2 Completion — Readiness Review
6 | SECTION 2 COMPLETION (DH2 + Plant)
175 | DH1 — HVAC Commissioning & Balancing
177 | DH3 — HVAC Commissioning & Balancing
178 | DH4 — HVAC Commissioning & Balancing
180 | DH1 — BMS/BAS Integ. Func. Test
181 | DH1 — Fire Alarm Integ. Test
205 | District Heating Commissioning (72hr)
193 | DH3 — BMS/BAS Integ. Func. Test
194 | DH3 — Fire Alarm Integ. Test
196 | DH4 — BMS/BAS Integ. Func. Test
197 | DH4 — Fire Alarm Integ. Test
206 | Acoustic Testing & IEQ Validation
183 | DH1 — S1 Completion Readiness Review
195 | Section 3 Completion — Readiness Review
5 | SECTION 1 COMPLETION (DH1 + Shared Infra)
7 | SECTION 3 COMPLETION (DH3 + Plant)
211 | Section 4 — Final Snagging & Readiness
8 | PROJECT COMPLETION (S4: DH4 + Admin/NOC + External)

## Risk
Risk Distribution · Monte-Carlo forecast
Metric | Value
Expected slip (days) | 51.8
P50 — most likely finish (days) | 385.4
P80 (days) | 401.7
P99.6 (days) | 441.2
Standard deviation (days) | 19.3
Baseline (deterministic, days) | 334
Mean finish (days) | 385.8
Finish-date distribution (histogram)
Finish day (bucket mid) | Simulations
320.1 | 2
326.3 | 2
332.5 | 6
338.7 | 23
344.9 | 47
351.2 | 99
357.4 | 193
363.6 | 256
369.8 | 378
376 | 467
382.2 | 524
388.4 | 536
394.6 | 443
400.8 | 351
407 | 248
413.2 | 170
419.4 | 118
425.7 | 62
431.9 | 40
438.1 | 19
444.3 | 9
450.5 | 4
456.7 | 2
462.9 | 1
Top variance drivers
Activity | Contribution
Bulk Earthworks — Site Strip & Cut | 10%
DH1 — Rock-Socketed Bored Piles | 10%
DH2 — Rock-Socketed Bored Piles | 10%
DH2 — Upper Floor & Roof Steel | 7%
DH4 — Upper Floor & Roof Steel | 7%
DH4 — HVAC Ductwork & AHU Install | 6%
DH4 — CRAH Fan-Wall Installation | 6%
Rock Excavation & Blasting | 6%

## Charts
Resource — resource S-curve + histogram
Period | Resource (period) | Cumulative
W1 | 10 | 0
W2 | 12 | 10
W3 | 9 | 22
W4 | 18 | 31
W5 | 21 | 49
W6 | 21 | 70
W7 | 41 | 91
W8 | 37 | 132
W9 | 41 | 169
W10 | 37 | 210
W11 | 33 | 247
W12 | 32 | 280
W13 | 32 | 312
W14 | 40 | 344
W15 | 58 | 384
W16 | 50 | 442
W17 | 72 | 492
W18 | 70 | 564
W19 | 74 | 634
W20 | 80 | 708
W21 | 96 | 788
W22 | 126 | 884
W23 | 118 | 1010
W24 | 128 | 1128
W25 | 112 | 1256
W26 | 140 | 1368
W27 | 104 | 1508
W28 | 112 | 1612
W29 | 84 | 1724
W30 | 88 | 1808
W31 | 108 | 1896
W32 | 68 | 2004
W33 | 68 | 2072
W34 | 48 | 2140
W35 | 48 | 2188
W36 | 40 | 2236
W37 | 64 | 2276
W38 | 116 | 2340
W39 | 112 | 2456
W40 | 168 | 2568
W41 | 156 | 2736
W42 | 168 | 2892
W43 | 168 | 3060
W44 | 160 | 3228
W45 | 174 | 3388
W46 | 254 | 3562
W47 | 274 | 3816
W48 | 266 | 4090
W49 | 242 | 4356
W50 | 224 | 4598
W51 | 204 | 4822
W52 | 246 | 5026
W53 | 262 | 5272
W54 | 281 | 5534
W55 | 244 | 5815
W56 | 186 | 6059
W57 | 127 | 6245
W58 | 73 | 6372
W59 | 49 | 6445
W60 | 36 | 6494
W61 | 30 | 6530
W62 | 28 | 6560
W63 | 29 | 6588
W64 | 27 | 6617
W65 | 18 | 6644
W66 | 10 | 6662
W67 | 2 | 6672
W67 | 0 | 6674

## Timeline (monthly)
High-Level Timeline · 1 column = 1 month
ID | Activity | Mar 26 | Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27
1 | Contract & Mobilization
2 | Procurement
3 | Other
4 | Design Phase
5 | Construction
6 | Testing & Commissioning
7 | Handover & Close-out

## Narrative
Narrative & Feedback
Four data halls (DH1-DH4) on separate piled foundations with steel frame and precast plank floors. DH1+DH2 share a common foundation slab and are structurally coupled. DH3 and DH4 are separate structures. DH1 and DH2 proceed in staggered parallel (DH1 leads DH2 by ~4 weeks). DH3 follows after DH2 frame substantially complete. DH4 is the last hall running concurrently with admin/NOC and external works. Four overlapping construction fronts once foundations are cast.

## Feedback & Issues
No review feedback / carried issues.