## Historical Analogs
HISTORICAL PRODUCTIVITY RATES — NORD BUILD DATABASE (ev_1)
Evidence ID | Project | Activity | Trade Group | Qty | Unit | Crews | Members/Crew | Duration (wd) | Man-Hours | Productivity Rate | Rate Unit
hist-prj-001-act-132 | PRJ-001 Helsinki | Bulk Earthworks & Rough Grading | Earthworks | 2500 | m³ | 2 | 8 | 10 |  |  | m³/man-hr
hist-prj-001-act-137 | PRJ-001 Helsinki | Basement Excavation & Shoring | Earthworks | 3000 | m³ | 2 | 8 | 15 |  |  | m³/man-hr
hist-prj-001-act-137 | PRJ-001 Helsinki | Rock Excavation (blasting -20%) | Blasting | 3000 | m³ rock | 2 | 8 | 19 |  |  | m³ rock/man-hr
hist-prj-001-act-134 | PRJ-001 Helsinki | Rock-Socketed Bored Piles | Piling | 100 | piles | 2 | 6 | 30 |  |  | piles/man-hr
hist-prj-004-act-138 | PRJ-004 Helsinki | Rock-Socketed Bored Piles | Piling | 100 | piles | 2 | 6 | 30 |  |  | piles/man-hr
hist-prj-001-act-140 | PRJ-001 Helsinki | Pile Caps & Ground Beams | RC Frame | 800 | m³ RC | 2 | 8 | 10 |  |  | m³ RC/man-hr
hist-prj-001-act-141 | PRJ-001 Helsinki | Foundation Slab | RC Frame | 600 | m³ RC | 2 | 8 | 10 |  |  | m³ RC/man-hr
hist-prj-001-act-139 | PRJ-001 Helsinki | Foundation Waterproofing | Waterproofing | 500 | m² | 1 | 4 | 5 |  |  | m²/man-hr
hist-prj-001-act-145 | PRJ-001 Helsinki | Structural Frame (Floors 1-N) | RC Frame | 1800 | m³ RC | 2 | 12 | 45 |  |  | m³ RC/man-hr
hist-prj-001-act-146 | PRJ-001 Helsinki | Precast Floor Planks | Precast | 4000 | m² | 2 | 6 | 30 |  |  | m²/man-hr
hist-prj-004-act-82 | PRJ-004 Helsinki | Structural Steel — Fabrication | Steel Fab. | 1 | LS | 1 | 12 | 35 |  | LS — use analog duration | days directly
hist-prj-004-act-148 | PRJ-004 Helsinki | Ground Floor Steel Erection | Steel Erection | 1 | LS | 2 | 8 | 8 |  | LS — use analog duration | days directly
hist-prj-004-act-149 | PRJ-004 Helsinki | Upper Floor & Roof Steel | Steel Erection | 1 | LS | 2 | 10 | 40 |  | LS — use analog duration | days directly
hist-prj-001-act-150 | PRJ-001 Helsinki | Ext Wall Thermal Insulation | Envelope | 3500 | m² | 1 | 6 | 20 |  |  | m²/man-hr
hist-prj-001-act-153 | PRJ-001 Helsinki | Roof Waterproofing | Roofing | 1200 | m² | 1 | 4 | 8 |  |  | m²/man-hr
hist-prj-001-act-154 | PRJ-001 Helsinki | Roof Insulation & Finishing | Roofing | 1200 | m² | 1 | 4 | 5 |  |  | m²/man-hr
hist-prj-001-act-168 | PRJ-001 Helsinki | Riser Piping (Htg & Clg) | Mech Pipe | 600 | lm | 2 | 6 | 20 |  |  | lm/man-hr
hist-prj-001-act-169 | PRJ-001 Helsinki | HVAC Ductwork — Lower Floors | Mech HVAC | 2000 | m² duct | 2 | 8 | 20 |  |  | m² duct/man-hr
hist-prj-001-act-170 | PRJ-001 Helsinki | Chiller/CRAH Install (per unit) | Mech HVAC | 1 | unit | 1 | 4 | 5 |  | LS — use analog duration | days directly
hist-prj-001-act-183 | PRJ-001 Helsinki | Cable Trays & Containment | Electrical | 1 | LS | 2 | 8 | 25 |  | LS — use analog duration | days directly
hist-prj-001-act-184 | PRJ-001 Helsinki | Main Power Feeder Cables | Electrical | 1 | LS | 2 | 6 | 10 |  | LS — use analog duration | days directly
hist-prj-001-act-185 | PRJ-001 Helsinki | Distribution Boards | Electrical | 1 | LS | 2 | 6 | 10 |  | LS — use analog duration | days directly
hist-prj-001-act-201 | PRJ-001 Helsinki | Internal Partition Walls | Fit-Out | 4500 | m² | 2 | 10 | 20 |  |  | m²/man-hr
hist-prj-001-act-203 | PRJ-001 Helsinki | Raised Access Flooring | Fit-Out | 3500 | m² | 1 | 6 | 10 |  |  | m²/man-hr
hist-prj-001-act-207 | PRJ-001 Helsinki | Wall Finishes (Paint & Tile) | Fit-Out | 5000 | m² | 2 | 8 | 15 |  |  | m²/man-hr
hist-prj-001-act-162 | PRJ-001 Helsinki | Access Roads & Paths | External Works | 500 | lm | 1 | 6 | 8 |  |  | lm/man-hr
hist-prj-001-act-164 | PRJ-001 Helsinki | Landscaping | External Works | 800 | m² | 1 | 4 | 8 |  |  | m²/man-hr
hist-prj-001-act-215 | PRJ-001 Helsinki | HVAC Commissioning | Commissioning | 1 | LS | 1 | 6 | 10 |  | LS — use analog duration | days directly
hist-prj-001-act-217 | PRJ-001 Helsinki | Electrical Systems Testing | Commissioning | 1 | LS | 1 | 4 | 8 |  | LS — use analog duration | days directly
hist-prj-001-act-220 | PRJ-001 Helsinki | BMS/BAS Integrated Test | Commissioning | 1 | LS | 1 | 4 | 8 |  | LS — use analog duration | days directly
hist-prj-001-act-218 | PRJ-001 Helsinki | Fire Alarm Integrated Test | Commissioning | 1 | LS | 1 | 3 | 5 |  | LS — use analog duration | days directly
hist-prj-001-act-222 | PRJ-001 Helsinki | Acoustic & IEQ Testing | Commissioning | 1 | LS | 1 | 3 | 3 |  | LS — use analog duration | days directly
LEGEND:
Yellow = input | Change → rate recalculates
Green = formula | Live arithmetic
Orange = judgement | LS or parameter

## Polaris Durations
POLARIS DC-1 — DURATIONS COMPUTED FROM HISTORICAL PRODUCTIVITY RATES
Yellow = input · Green = formula · Orange = judgement · Change Margin % → all durations recalculate
Sched ID | Activity | Trade Group | Analog Evidence ID | BOQ Qty | Unit | Rate (per man-hr) | Rate Unit | Crews | Members/Crew | Hrs/Day | Dur. Raw (wd) | Dur. Base (wd) | Margin % | Dur. Final (wd) | Notes
40 | Bulk Earthworks — Site Strip & Cut | Earthworks | hist-prj-001-act-132 | 12000 | m³ | 1.953 | m³/man-hr | 2 | 8 | 8 |  |  | $B$37 |  | 12,000 m³. Rate from PRJ-001.
41 | Rock Excavation & Blasting | Blasting | hist-prj-001-act-137 | 4500 | m³ rock | 1.25 | m³/man-hr | 2 | 8 | 8 |  |  | $B$37 |  | -20% vs excavation (blasting restricted hours)
42 | Trench Excavation — Site Services | Earthworks | hist-prj-001-act-137 | 2000 | m³ | 1.563 | m³/man-hr | 1 | 8 | 8 |  |  | $B$37 |  | Service trenches
50 | DH1 — Rock-Socketed Bored Piles | Piling | hist-prj-001-act-134 | 40 | piles | 0.0347 | piles/man-hr | 2 | 6 | 8 |  |  | $B$37 |  | ~40 piles/hall. 2 rigs at 1.67 piles/rig-day.
54 | DH1 Pile Caps & Ground Beams | RC Frame | hist-prj-001-act-140 | 240 | m³ RC | 0.625 | m³/man-hr | 2 | 8 | 8 |  |  | $B$37 |  | ~240 m³ per hall
58 | DH1 Foundation Waterproofing | Waterproofing | hist-prj-001-act-139 | 250 | m² | 3.125 | m²/man-hr | 1 | 4 | 8 |  |  | $B$37 |  | ~250 m² per hall
62 | DH1 Ground Floor Slab | RC Frame | hist-prj-001-act-141 | 600 | m³ RC | 0.469 | m³/man-hr | 2 | 8 | 8 |  |  | $B$37 |  | ~600 m³ per hall
78 | DH1 — Precast Plank Floors | Precast | hist-prj-001-act-146 | 3000 | m² | 1.389 | m²/man-hr | 2 | 6 | 8 |  |  | $B$37 |  | ~3,000 m² per hall
90 | DH1 — Ext Wall Insulation & Cladding | Envelope | hist-prj-001-act-150 | 2250 | m² | 3.646 | m²/man-hr | 2 | 6 | 8 |  |  | $B$37 |  | ~2,250 m² per hall
94 | DH1 — Roof Waterproofing & Insulation | Roofing | hist-prj-001-act-153 | 1500 | m² | 4.688 | m²/man-hr | 2 | 4 | 8 |  |  | $B$37 |  | ~1,500 m² per hall
114 | DH1 — HVAC Ductwork & AHU Install | Mech HVAC | hist-prj-001-act-169 | 2000 | m² duct | 0.781 | m²/man-hr | 2 | 8 | 8 |  |  | $B$37 |  | ~2,000 m² per hall
118 | Cooling Spine — Pipework & Distr. | Mech Pipe | hist-prj-001-act-168 | 1200 | lm | 0.313 | lm/man-hr | 2 | 6 | 8 |  |  | $B$37 |  | 1,200 lm across cooling spine
119 | DH1 — Riser Piping (Htg & Clg) | Mech Pipe | hist-prj-001-act-168 | 300 | lm | 0.313 | lm/man-hr | 2 | 6 | 8 |  |  | $B$37 |  | ~300 lm per hall
130 | DH1 — CRAH Fan-Wall Installation | Mech HVAC | hist-prj-001-act-170 | 120 | units | 0.006 | units/man-hr | 2 | 6 | 8 |  |  | $B$37 |  | ~120 CRAH per hall. 5× scaling from 1 unit/160 man-hr analog.
140 | DH1 — Chiller Installation & Piping | Mech HVAC | hist-prj-001-act-170 | 4 | units | 0.006 | units/man-hr | 1 | 4 | 8 |  |  | $B$37 |  | 4 chillers (N+1)
160 | DH1 — Raised Access Flooring | Fit-Out | hist-prj-001-act-203 | 1500 | m² | 7.292 | m²/man-hr | 2 | 6 | 8 |  |  | $B$37 |  | ~1,500 m² per hall
200 | Access Roads & Parking Construction | External Works | hist-prj-001-act-162 | 500 | lm | 1.302 | lm/man-hr | 2 | 6 | 8 |  |  | $B$37 |  | ~500 lm + base/kerbs/wearing course
203 | Landscaping & Soft Works | External Works | hist-prj-001-act-164 | 800 | m² | 3.125 | m²/man-hr | 1 | 4 | 8 |  |  | $B$37 |  | ~800 m² + winter allowance
10 | Mobilisation & Site Setup | General Labour | hist-prj-001-act-130 | — | LS | LS | wd | 1 | 6 | 8 | — | — | LS | 8 | Analog: 5d + 3d DC complexity
70 | DH1 — GF Steel Erection | Steel Erection | hist-prj-004-act-148 | — | LS | LS | wd | 2 | 8 | 8 | — | — | LS | 8 | 8d LS per hall (PRJ-004)
72 | DH1 — Upper Floor & Roof Steel | Steel Erection | hist-prj-004-act-149 | — | LS | LS | wd | 2 | 10 | 8 | — | — | LS | 40 | 40d LS per hall (PRJ-004)
110 | DH1 — Cable Trays & Containment | Electrical | hist-prj-001-act-183 | — | LS | LS | wd | 2 | 8 | 8 | — | — | LS | 35 | 25d × 2.5 DC scale → 63d ÷ 2 gangs → 32d + margin → 35d
141 | DH1 — Electrical Dist. Boards | Electrical | hist-prj-001-act-185 | — | LS | LS | wd | 2 | 6 | 8 | — | — | LS | 14 | 10d × 2.5 DC → 25d ÷ 2 gangs → 13d + margin → 14d
145 | DH1 — Busway & Power Feeders | Electrical | hist-prj-001-act-184 | — | LS | LS | wd | 2 | 6 | 8 | — | — | LS | 14 | 10d × 2.5 DC → 25d ÷ 2 gangs → 13d + margin → 14d
150 | DH1 — ELV/BMS/Fire Detection | ELV | hist-prj-001-act-183 | — | LS | LS | wd | 2 | 6 | 8 | — | — | LS | 20 | 25d × DC scale → 2 gangs → 20d
164 | Admin/NOC — Fit-Out | Fit-Out | hist-prj-001-act-201 | — | LS | LS | wd | 2 | 8 | 8 | — | — | LS | 25 | Conventional office fit-out: 25d LS
170 | DH1 — Electrical Testing & Dead Bus | Commissioning | hist-prj-001-act-217 | — | LS | LS | wd | 1 | 4 | 8 | — | — | LS | 12 | 8d × 1.5 DC = 12d
175 | DH1 — HVAC Commissioning & Balancing | Commissioning | hist-prj-001-act-215 | — | LS | LS | wd | 1 | 6 | 8 | — | — | LS | 15 | 10d × 1.5 DC = 15d
180 | DH1 — BMS/BAS Int. Func. Test | Commissioning | hist-prj-001-act-220 | — | LS | LS | wd | 1 | 4 | 8 | — | — | LS | 12 | 8d × 1.5 DC = 12d
181 | DH1 — Fire Alarm Integrated Test | Commissioning | hist-prj-001-act-218 | — | LS | LS | wd | 1 | 3 | 8 | — | — | LS | 7 | 5d × 1.4 DC = 7d
182 | DH1 — Generator Load-Bank Test | Commissioning | hist-prj-001-act-218 | — | LS | LS | wd | 1 | 3 | 8 | — | — | LS | 8 | 5d × 1.6 DC = 8d
MARGIN % | 10% | ← Change this → ALL quantity-driven durations recalculate. 10% = first-build DC + winter + learning curve.
DC MEP SCALING | 2.5 | ← DC complexity factor vs commercial office. Documented, not formula-driven.
LEGEND:
Yellow | Input — change and durations recalculate
Green | Formula — live arithmetic
Orange | Judgement — margin, LS duration, scaling factor

## Cost Mapping
BOQ-TO-ACTIVITY COST MAPPING
BOQ Ref | Description | BOQ Amount (€) | Activity IDs | Loaded Amount (€) | Exclusions / Notes
A.01-A.07 | Site est., cranage, env. controls | 2675159 | 10,40,41,70-77,102 | 2675159 | A.02/A.05/A.06/A.08 excluded
B.01-B.10 | Earthworks, blasting, piling, substructure | 6105520 | 40-45,50-65,82 | 6105520 | B.11 contingency excluded
C.01-C.08 | Steel, precast, RC, fire protection | 8522330 | 70-81,82-83,94-97,100-103 | 8522330 | Supply+install on erection
D.01-D.08 | Cladding, roofing, louvres, doors | 5382523 | 90-97,100-105 | 5382523 | Envelope supply+install
E.01-E.07 | Raised floor, containment, admin fit-out | 4485437 | 160-164,183-211 | 4485437 | Finishes on fit-out
F.01-F.12 | Chillers, CRAH, pipework, DH plant | 21530097 | 114-122,130-133,140,205 | 21530097 | Equipment supply on install
G.01-G.14 | TX, generators, UPS, LV, busway | 26912621 | 110-113,123-125,141-148 | 26912621 | €15.0M gen/UPS; €5.4M TX
H.01-H.09 | ELV, BMS, DCIM, fire, CCTV | 4933981 | 150-153,180-197,201 | 4933981 | BMS on integrated test
I.01-I.08 | Roads, fencing, fibre, lighting | 3588350 | 103-104,200-203 | 3588350 | Ext works mapped
J.01-J.07 | FAT, L2-L5, as-built, statutory | 2242718 | 170-173,180-197,182,183-211 | 2242718 | Commissioning mapped
LOADED
CONTRACT |  | 92400000
NOT LOADED |  |  |  |  | Risk, time, financial, contingency, rounding
LOAD RATIO

## Read Me
HOW TO USE THIS WORKBOOK
CHANGING DURATIONS
Go to 'Polaris Durations'. Change yellow cells (BOQ qty, crews, members, hrs/day) → raw/base/final durations recalculate live. Change the Margin % cell → every quantity-driven duration updates at once.
CHANGING RATES
On 'Historical Analogs', change yellow cells (crews/members/duration) → rate recalculates. Polaris sheet uses typed rates (col G) — copy changed rates across.
LUMP-SUM
Activities shown as 'LS' use analog duration directly. Orange cells are manually entered — change them directly.
MARGIN
10% = first-build DC learning curve + winter + 22-month tempo. Set to 0% for perfect conditions, 15% to stress-test.
COST
€82.97M loaded (89.8%). Excluded: risk allowances, time prelims, financial instruments, contingency. See 'Cost Mapping'.
CELL COLOURS
Yellow = input (change). Green = formula (live). Orange = judgement (margin, LS, scaling).