## Slide 1
Polaris DC-1 — What the Project Manager Needs to Know

## Slide 2
FIDIC Yellow Book 2017 with Particular Conditions Rev A — Tender Issue

## Slide 3
— Contract Sum €92.4M · 22 months · 4 Sections · Vantaa, Finland
---

## Slide 4
Slide 1: The Big Picture for Site
**What this contract does to you on the ground:**---• You carry **all ground risk** — every cubic metre of unexpected rock, every patch of bad ground is ours to pay for and programme around• You have **14 days** from the moment you become aware of a problem to submit a fully detailed claim — miss it and the claim is dead forever• You are guaranteeing **absolute performance** on PUE ≤1.25, WUE ≤0.25, availability 99.982%, and 4MW waste heat at ≥70°C — no excuses, no "reasonable skill and care"• The employer holds **10% of every invoice** (€9.24M total) and releases nothing until the Performance Certificate — 36 months after you finish• Design documents you didn't write (Employer's Requirements + Tenant Technical Annex) — if they contain errors, you pay to fix them

## Slide 5
Slide 2: The Site — What the Ground Tells Us
**Geotechnical Report (PDC_SS_001, Oct 2025 — 14 boreholes):**---

## Slide 6
Slide 2: The Site — What the Ground Tells Us
What we know | What it means for you
Granitic gneiss bedrock at 4.0–9.2m (shallowest in east) | **Blasting required in eastern third** of site — mechanical excavation not viable. Pre-blast condition surveys needed for residential + logistics neighbour
Perched groundwater at 2.6–3.9m | **Sump pumping / well-pointing** for ALL excavations below ~2.5m. Higher in spring snowmelt
Three residual risks the investigation couldn't close | See next slide — these are yours under SP-5
110kV overhead line crosses north boundary | Crane/plant exclusion zone; network operator permission required
Residential boundary NE | 45 dB(A) night-time noise limit — restricts blasting, generator testing, night work
Aviation height limit (3km from Helsinki-Vantaa) | Obstacle lighting likely required on tall cranes and permanent plant

## Slide 7
Slide 3: The Three Ground Risks You Own (SP-5)
SP-5 deletes the entire "Unforeseeable Physical Conditions" clause. These three unresolved items from the Employer's own geotech report are now **ours to carry, 100%**:**What to do now:** Price these as known risks in the tender. Include a ground-risk contingency in your preliminaries. If we win, commission the follow-up investigation before excavation starts.---

## Slide 8
Slide 3: The Three Ground Risks You Own (SP-5)
Risk | Location | Our Exposure
**Made ground (~900m², extent unknown)** | NW corner (BH-01: 1.7m loose fill, origin unrecorded) | Not suitable for founding — removal and replacement or piled slab. Possible archaeological watching brief (Finnish Heritage Agency). Programme risk: enabling works delay while extent is investigated
**Boulder-rich horizon (rock not proven)** | Between BH-07/BH-08/BH-09 (central-east) | Two boreholes hit refusal on boulders at 6.4–7.8m without reaching rockhead. Boulders can deflect piles, increase blasting, make excavation unpredictable. The report recommends further investigation before finalising piling methodology
**Elevated sulphide (waste classification pending)** | Vicinity of BH-12 (south-central, 3.2–4.6m) | Dark grey/black sulphide-stained till with sulphurous odour. May require classified waste disposal, segregated stockpiling, and different handling. Lab results not available at report issue

## Slide 9
Slide 4: The Programme — What Drives Your Critical Path
**Four sections, staggered completions:****Key programme constraints:**---• **Blasting: 08:00–18:00 Mon-Fri only** (SP-18). Pre-blast surveys + notification to authority + neighbours required before first blast• **Generator testing: 09:00–16:00 Mon-Fri only** (SP-18)• **Deliveries: 06:00–22:00 Mon-Fri only** — single shared access from Setkunnantie through logistics neighbour• **Night noise: 45 dB(A) at residential boundary** — no blasting, no generator testing, restricted plant after 22:00• **Commissioning: L1 to L5** must be tracked in monthly reports (SP-21)• **Taking-Over needs BOTH** occupancy inspection (käyttöönottotarkastus) AND Tenant technical acceptance (SP-22)

## Slide 10
Slide 4: The Programme — What Drives Your Critical Path
Section | Time for Completion | LD exposure
Section 1 (likely Phase 1 data halls) | 14 months | Per Part A — LD rate per section
Section 2 | 16 months | Per Part A
Section 3 | 19 months | Per Part A
Section 4 (Final Completion) | 22 months | Per Part A ÷ LD cap = 20% of Contract Sum

## Slide 11
Slide 5: Your Deadlines — The Ones That Bite
---

## Slide 12
Slide 5: Your Deadlines — The Ones That Bite
What | Deadline | If You Miss It
**Claims notification** (SP-15) | **14 days** from awareness of event | **Claim is dead — absolutely barred.** No discretion, no waiver, no extension by Engineer or arbitrator. Full particulars required within the 14 days
**Subcontractor payment** (SP-4) | 60 days from sub's invoice **BUT** only after Employer pays us | You cannot pay subs until we're paid. Finnish law may override this, but subcontractors will push back — manage their expectations day one
**Variation work** (SP-9) | **Immediately** on instruction | If you wait for pricing to be agreed before starting — it's a "substantial failure" and grounds for termination under 15.2
**Progress reports** (SP-21) | Monthly | Must include L1–L5 commissioning status per section + every long-lead equipment order status
**IPC submission** (Part A) | Monthly | Engineer has 42 days to review. Silence = NOT deemed certified (SP-12 deletes deemed certification). If the Engineer sits on it, you sit on it
**Employer payment** (Part A) | 75 days from IPC to cash | 42 days Engineer review + 33 days Employer payment. Budget cashflow accordingly

## Slide 13
Slide 6: The Design Guarantees You're On The Hook For
**SP-6 — Absolute fitness-for-purpose warranty (not "reasonable skill and care"):****The problem:** You are guaranteeing performance of systems designed to the Employer's Requirements and Tenant Technical Annex — but you have no right to relief if those documents contain errors (SP-2 deleted 1.9). If the Tenant's load assumptions or cooling specs don't work in practice, you still have to make the numbers.**What to do:** Have your MEP lead do a sanity-check on the ER and Technical Annex now, before we submit. Flag anything that looks impossible or contradictory.---

## Slide 14
Slide 6: The Design Guarantees You're On The Hook For
Metric | Target | What It Means On Site
**PUE** | ≤1.25 annualised | Every watt of overhead (cooling, lighting, losses) is measured against IT load. Affects every MEP design decision you make
**WUE** | ≤0.25 L/kWh | Water consumption for cooling. Influences cooling system selection and makes commissioning tuning critical
**Availability** | 99.982% (≤94 minutes downtime/year) | This is Tier III-equivalent. Redundant everything. Every single-point-of-failure kills you
**Waste heat** | ≥4 MWth at ≥70°C | You are delivering a district heating supply. The District Heating Agreement (PDC_DH_001) is in the tender pack — read it. Heat exchangers, flow temperatures, and commissioning must prove delivery

## Slide 15
Slide 7: What You Must Put In Place Before We Start
---

## Slide 16
Slide 7: What You Must Put In Place Before We Start
Action | Owner | Deadline
**Performance Security** — 10% on-demand bond (Part A) | You / Commercial | Before start
**PI Insurance** — €10M each claim, 6-year tail (Part A) | You / Commercial | Before start
**All-Risks Insurance** — Works (Part A) | You / Commercial | Before start
**Blasting notification** — to Vantaa authority + neighbours | You | Before first blast
**Pre-blast condition surveys** — residential + logistics neighbour | You | Before first blast
**110kV line — network operator permission** for crane/plant near line | You | Before any tall plant near north boundary
**Background check regime** — for all personnel entering data halls after first energisation (SP-19) | You / HR | Before commissioning
**Site security measures** — per ER, including access logging (SP-19) | You | From Commencement Date
**Boulder zone investigation** — seismic refraction or additional boreholes BH-07 to BH-09 | You / Geotech | Before piling/excavation in that zone
**Made ground investigation** — prove extent of NW corner fill | You / Geotech | Before foundations in that area
**Sulphide testing** — confirmatory on BH-12 material | You / Geotech | Before bulk excavation reaches 3.2m near BH-12

## Slide 17
Slide 8: Subcontractor Management
**SP-4 changes how you deal with subs:****The reality:** Finnish subcontractors will not accept pay-when-paid on 60-day terms. In practice, this clause creates tension — your subs will demand payment, the Employer may not have paid us yet, and the contract offers no protection. You need to: 1. Be upfront with subs about payment timing 2. Budget for bridging finance to keep key subs working while Employer payments are pending 3. Vet subs for financial robustness — they're effectively financing our contract---• All subcontracts must provide for **60-day payment** from sub's invoice• No payment to subs **unless and until** the Employer has paid us for that work• Finnish Tilaajavastuulaki (1233/2006) compliance must be evidenced every 3 months

## Slide 18
Slide 9: Disputes — There Is No Middle Ground
---• **No Dispute Board** (SP-16 deletes DAAB entirely)• Every unresolved issue goes straight to **LCIA arbitration in London** (SP-17)• This means: expensive, slow, outside Finland, in English• **Practical effect:** The Engineer and Employer know it costs us €150-250k+ just to challenge a decision. That's a bargaining lever in their favour. Document everything meticulously — if it ever reaches London, your site records are the only defence.

## Slide 19
Slide 10: Your Personal Risk Register — Top 5
---*Based on PDC_PC_001 Rev A Particular Conditions + PDC_SS_001 Geotechnical Report (Oct 2025). Ground-risk statements are grounded in actual borehole data, not assumptions.*

## Slide 20
Slide 10: Your Personal Risk Register — Top 5
Rank | Risk | Your Mitigation
1 | **14-day claims bar** — missing a notification kills a legitimate claim | Set a weekly "claims review" meeting. Every superintendent must report anything that could become a claim. Log everything.
2 | **Ground conditions — boulders, made ground, sulphide** — all ours | Budget for it. Investigate early. Don't start bulk excavation in unknown zones.
3 | **Commissioning to L5 + Tenant acceptance** — takes longer than you think | Build 4-6 weeks of commissioning float into your Section 1 programme. L1-L5 is a multi-stage process with Tenant sign-off — it's a collaboration, not a checklist.
4 | **Blasting constraints** — limited hours, residential neighbour, vibration limits | Engage a licensed Finnish blasting contractor who knows SFS 4812 and has worked near residential. Pre-blast surveys are non-negotiable.
5 | **Subcontractor cashflow** — 75-day Employer payment + 60-day sub terms = subs carrying 4-5 months | This will cause attrition. Identify which subs are essential (MEP, BMS, cooling) and ensure they have the balance sheet to carry it — or arrange bridge financing.