# POLARIS DC-1 — REV C FINAL ASSESSMENT

# Comparison: Rev B → Rev C | 24 February 2026

Recommendation: SIGN.

---

# 1. REV B → REV C — WHAT CHANGED

# — Critical Items (all three resolved)

| # | Ask (Rev B recommendation) | Rev C response | Verdict |
| --- | --- | --- | --- |
| 1 | Restore liability cap | Sub-Clause 1.15 reinstated. Cap at Accepted Contract Amount (€92.4M). Carve-outs: death/PI, fraud, wilful misconduct, abandonment, insurance proceeds | ACCEPTED |
| 2 | Amend performance warranty to reasonable skill & care | RSC restored. PUE ≤1.25, WUE ≤0.25, 99.982% availability, 4MWth waste heat targets retained as performance guarantees — but measured against professional skill & care standard, not absolute | ACCEPTED |
| 3 | Restore error relief for Employer's Requirements | Sub-Clause 1.9 reinstated in full and unamended. ER and Tenant Technical Annex errors now at Employer risk | ACCEPTED |

# — Strong Push Items (all three resolved)

| # | Ask | Rev C response | Verdict |
| --- | --- | --- | --- |
| 4 | Remove concurrent delay bar | SP-7 bar deleted. Engineer must apportion delay fairly between concurrent causes on basis of contemporary records | ACCEPTED |
| 5 | Remove/limit IPC deduction right | Employer deduction limited to Delay Damages that have actually accrued and been agreed or determined. No deduction for anticipated future LDs | ACCEPTED |
| 6 | Extend claims notice, remove absolute bar | Sub-Clause 20.2.1 restored in full (28 days). Sub-Clause 20.2.2 includes Engineer's obligation to notify non-compliance and consequences of failing to do so | ACCEPTED |

# — Nice-to-Have Items

| # | Ask | Rev C response | Verdict |
| --- | --- | --- | --- |
| 7 | Broader cost adjustment, lower franchise | Labour added (steel/copper/diesel/labour basket). Franchise reduced 5%→2% | Accepted in part |
| 8 | Reduce retention to 5% | 5% retention. Bond option from outset. Half released at S1 TOC, remainder at S4 TOC | ACCEPTED — exceeds ask |
| 9 | Reduce performance security to 5% | Unchanged at 10% on-demand | Not accepted |
| 10 | Financing charges to ECB+7% | Unchanged at ECB+2% | Not accepted |

# — Unasked-for Concessions

- Advance payment: 5% → 10%

- LD cap: 12% → 10%

- Subcontractor payment: 45 days → 30 days

- Ground risk (SP-5): time-only EOT → full 4.12 reinstated (time + cost)

- Exceptional Events (SP-14): limited list → Sub-Clause 18.1 reinstated in full

- Variation work (SP-9): must proceed immediately but Engineer must interim-valuate within 28 days and certify

# — Sole Gap — Knowingly Accepted

---

- DAAB (SP-16): remains deleted. Contractor letter NB-PDC-031 explicitly accepts as "knowingly accepted residual risk." For a 22-month programme with Finnish Chamber of Commerce arbitration in Helsinki, a standing board is disproportionate.

# 2. COMMERCIAL JOURNEY — REV A → REV B → REV C

---

| Metric | Rev A | Rev B | Rev C |
| --- | --- | --- | --- |
| Liability cap | None | None | €92.4M |
| Advance payment | €0 | €4.62M | €9.24M |
| Retention | 10%, all at PC, no bond | 7.5%, half at S4 TOC, bond from S1 | 5%, half at S1, bond from Day 1 |
| LD cap | 20% (€18.5M) | 12% (€11.1M) | 10% (€9.24M) |
| DNP | 36 months | 24 months | 24 months |
| ER errors | Contractor | Contractor | Employer |
| Design warranty | Absolute | Absolute | Reasonable skill & care |
| Claims notice | 14d, absolute bar | 21d, absolute bar | 28d, full FIDIC process |
| Ground risk | Deleted | Time only | Full (time + cost) |
| Concurrent delay | Bar | Bar | Apportionment |
| Cost adjustment | None | 3 commodities, 5% franchise | +labour, 2% franchise |
| Arbitration | LCIA London | FCC Helsinki | FCC Helsinki |
| Subcontractor payment | 60d pay-when-paid | 45d | 30d |
| Exceptional Events | Narrow list | +25yr weather | Full 18.1 restored |
| Employer IPC deduction | None | Anticipated LDs | Actual LDs only |

# 3. SCORECARD

---

| Tier | Outcome |
| --- | --- |
| Red-line (3 items) | 3/3 accepted (100%) |
| Strong push (3 items) | 3/3 accepted (100%) |
| Nice-to-have (4 items) | 2/4 accepted + 1 partial (63%) |
| Unasked-for wins | 6 additional concessions |
| Sole gap | DAAB deletion — knowingly accepted per NB-PDC-031 |

# 4. CONCLUSION

Three rounds of negotiation. This contract is now aligned with our historical database on every material commercial metric. The three critical risks identified in Rev A — unlimited liability, absolute design warranty, and ER error trap — are all resolved. The contract mechanics (claims, variations, concurrent delay, ground risk, exceptional events) have been rebuilt to standard FIDIC position. The commercial terms (advance, retention, LDs, DNP, subcontractor payment) match or exceed our benchmark portfolio.

The one gap — no DAAB — is consciously accepted. For a €92.4M, 22-month programme with Helsinki-seated FCC arbitration, a standing dispute board would be disproportionate. Our Finnish portfolio has historically managed without one.

Recommendation: Sign Rev C.