## Slide 1
Polaris DC-1 — Rev C Final

## Slide 2
Project Manager Brief · 2 slides · Drop into your own deck
---

## Slide 3
Rev C — Signed This Week · €92.4M · 22 months · 4 Sections
Advance Payment 10% (€9.24M)
Retention 5% · bond option from Day 1
LD Cap 10% (€9.24M)
Claims Notice 28 days (FIDIC standard)
---

## Slide 4
What Moved at Rev C — Your Site Reality
Ground risk restored in full — SP-5 gives you both time AND cost relief for unforeseen physical conditions. The three geotech unknowns (made ground NW, boulder zone central-east, sulphide BH-12) are still yours to investigate before you dig, but anything genuinely unforeseen beyond them attracts EOT + cost. You now have the standard FIDIC 4.12 mechanism.
Variation work — interim valuation within 28 days — SP-9 still requires you to start immediately on instruction, but if price isn't agreed within 28 days the Engineer must make an interim valuation and certify it in the next IPC. You won't be working for free while the commercial team argues about price.
No more Employer deductions for anticipated Delay Damages — SP-12 now limits deductions to damages that have actually accrued and been agreed/determined. No more unilateral withholding based on what the Employer "thinks may become due."
Concurrent delay bar gone — SP-7 now requires the Engineer to apportion delay between concurrent causes fairly. You get EOT for your share of Employer-risk events. You won't lose the whole period.
28-day claims notice, full FIDIC process — SP-15 restores the standard 28-day notice with Sub-Clause 20.2.2 fully operational. Engineer must notify you of any non-compliance and the consequences of failing to do so. No more absolute time bar.
Performance warranty — reasonable skill and care — SP-6 now says "reasonable skill, care and diligence." The PUE/WUE/availability/waste-heat targets remain as performance guarantees, but you are judged against a professional standard, not an absolute one. You have a defence if the targets are unachievable through no fault of your design.
One thing to be aware of: No DAAB. Disputes go straight to Finland Chamber of Commerce arbitration in Helsinki. Document your site records meticulously — if a dispute reaches arbitration, your contemporaneous records are your only narrative.
---

## Slide 5
Notes for your deck
Slide 1 is a KPI layout — four big numbers, clean
Slide 2 is the operational summary — what the Rev C changes mean for how you run the site
The 10% performance security (on-demand bond) and PI insurance (€10M per claim, 6-year tail) are unchanged from before — you already have those in hand
All site constraints from Rev A (blasting hours, noise limits, 110kV line, aviation height, shared access) are unchanged