## Schedule of Areas
Month | Zone Type | Zone Name | Area (m2) | Occupier / Function | Start Month | End Month | Notes
Mar 2026 | Parking | Staff & Operative Parking | 1200 | Nordbuild / All | Mar 2026 | Dec 2027 | Expands monthly. 6 visitor spaces outside gate.
Mar 2026 | Welfare | Offices + Canteen + Changing | 300 | Nordbuild | Mar 2026 | Dec 2027 | 2-storey modular. Scales with headcount.
Mar 2026 | Storage | TP-008 Fencing & Ducting | 400 | Ulkoalue Uusimaa Oy (TP-008) | Mar 2026 | Nov 2026 | Early phase near SW.
Mar 2026 | Storage | TP-001 Stockpile + Compound | 2400 | Kallio & Maa Oy (TP-001) | Mar 2026 | Oct 2026 | Eastern half. Peaks 4,200 m2 May 2026.
Mar 2026 | Route | Vehicle Spine 6.0m + E-W Distributor | - | Nordbuild | Mar 2026 | Dec 2027 | Fixed for project duration.
Mar 2026 | Route | Pedestrian Route 2.0m segregated | - | Nordbuild | Mar 2026 | Dec 2027 | Northern edge. 3 crossings.
Mar 2026 | Lifting | Material Lifting Points LP-1 to LP-4 | - | All | Mar 2026 | Dec 2027 | Hardstanding south of each data hall.
May 2026 | Storage | TP-001 Stockpile PEAK | 4200 | Kallio & Maa Oy (TP-001) | May 2026 | May 2026 | PEAK. 18-22 lorry movements/day. Blasting.
Aug 2026 | Storage | TP-002 Steel Laydown PEAK | 900 | Terasrakenne Pohjola Oy (TP-002) | Aug 2026 | Dec 2026 | PEAK STEEL. 250t crane + 110kV DNO permission.
Oct 2026 | Storage | TP-003 Cladding + Roofing PEAK | 1100 | Julkisivu Vantaa Oy (TP-003) | Oct 2026 | Feb 2027 | PEAK ENVELOPE. Mast-climbers active.
Dec 2026 | Storage | TP-004 External Storage PEAK | 1600 | Sisarak. Helsinki Oy (TP-004) | Dec 2026 | Dec 2026 | PEAK EXTERNAL. Largest space release when weathertight.
Jan 2027 | Storage | TP-005 CRAH + Pipe PEAK | 900 | Ilmatek LVI Oy (TP-005) | Jan 2027 | Mar 2027 | PEAK MECH. 2 rigging + 2 welding gangs.
Jan 2027 | Storage | TP-006 Dist Boards PEAK | 900 | Voima Electric Oy (TP-006) | Jan 2027 | Feb 2027 | PEAK ELEC. All halls active.
Feb 2027 | Parking | Staff & Operative Parking PEAK | 2650 | Nordbuild / All | Feb 2027 | Feb 2027 | PEAK. 250 ops + 28 staff. 106 spaces.
Feb 2027 | Welfare | Offices + Welfare PEAK | 347 | Nordbuild | Feb 2027 | Feb 2027 | PEAK WELFARE. 2-storey modular.
Mar 2027 | Storage | TP-008 Paving + Planting (Late Phase) | 600 | Ulkoalue Uusimaa Oy (TP-008) | Mar 2027 | Jun 2027 | RELOCATION: compound on parking ground.
Apr 2027 | Storage | TP-008 External Works PEAK | 800 | Ulkoalue Uusimaa Oy (TP-008) | Apr 2027 | Jun 2027 | PEAK EXT. Permanent roads, parking, landscaping.
Jun 2027 | Storage | TP-008 Final Phase | 600 | Ulkoalue Uusimaa Oy (TP-008) | Jun 2027 | Jun 2027 | PROJECT COMPLETION Jun 10.
Jul 2027 | Parking | Staff & Operative Parking | 600 | Nordbuild | Jul 2027 | Dec 2027 | 60 ops. Shrinking parking.
Jul 2027 | Welfare | Offices + Welfare (Reduced) | 200 | Nordbuild | Jul 2027 | Dec 2027 | 12 staff. Welfare downsizing.
Jul 2027 | Storage | TP-005 Final Commissioning | 100 | Ilmatek LVI Oy (TP-005) | Jul 2027 | Oct 2027 | S1+S3 completed. Final defecting.
Jul 2027 | Storage | TP-006 Final Commissioning | 100 | Voima Electric Oy (TP-006) | Jul 2027 | Oct 2027 | Final testing. Completion Oct 1.
Jul 2027 | Storage | TP-007 Final Commissioning | 100 | Tietoverkko Systems Oy (TP-007) | Jul 2027 | Oct 2027 | Final BMS/ELV. Completion Oct 7.
Jul 2027 | Storage | TP-008 Roads + Landscaping | 400 | Ulkoalue Uusimaa Oy (TP-008) | Jul 2027 | Nov 2027 | Permanent roads, car parks, planting.
Sep 2027 | Storage | TP-008 Snagging Works | 200 | Ulkoalue Uusimaa Oy (TP-008) | Sep 2027 | Nov 2027 | TP-006 (Oct 1) and TP-007 (Oct 7) complete.
Oct 2027 | Storage | TP-008 Final Snagging | 150 | Ulkoalue Uusimaa Oy (TP-008) | Oct 2027 | Nov 2027 | TP-005 completes Oct 27. Last trade contractor.
Nov 2027 | Storage | TP-008 Final Works | 100 | Ulkoalue Uusimaa Oy (TP-008) | Nov 2027 | Nov 2027 | TP-008 completes Nov 22. All trades demobilised.
Dec 2027 | - | DEMOBILISATION | - | Nordbuild Oy | Dec 2027 | Dec 2027 | S4 sectional completion Jan 2 2028. Handover.

## Summary
Month | Ops | Staff | Parking (m2) | Welfare (m2) | Laydown (m2) | Total External (m2) | % of Site
Mar 2026 | 20 | 12 | 1200 | 300 | 2800 | 4300 | 8.9
Apr 2026 | 40 | 15 | 1200 | 300 | 4600 | 6100 | 12.6
May 2026 | 50 | 18 | 1200 | 300 | 5300 | 6800 | 14.1
Jun 2026 | 65 | 20 | 1200 | 300 | 5200 | 6700 | 13.9
Jul 2026 | 85 | 22 | 1200 | 300 | 4900 | 6400 | 13.3
Aug 2026 | 100 | 24 | 1200 | 300 | 5300 | 6800 | 14.1
Sep 2026 | 130 | 26 | 1450 | 300 | 5100 | 6850 | 14.2
Oct 2026 | 155 | 28 | 1700 | 300 | 5200 | 7200 | 14.9
Nov 2026 | 180 | 28 | 1950 | 300 | 5200 | 7450 | 15.4
Dec 2026 | 210 | 28 | 2250 | 320 | 5800 | 8370 | 17.3
Jan 2027 | 230 | 28 | 2450 | 334 | 5700 | 8484 | 17.6
Feb 2027 | 250 | 28 | 2650 | 347 | 4500 | 7497 | 15.5
Mar 2027 | 235 | 26 | 2500 | 327 | 3300 | 6127 | 12.7
Apr 2027 | 200 | 24 | 2150 | 300 | 2300 | 4750 | 9.8
May 2027 | 150 | 20 | 1650 | 300 | 1400 | 3350 | 6.9
Jun 2027 | 80 | 16 | 1200 | 300 | 600 | 2100 | 4.3
Jul 2027 | 60 | 12 | 600 | 200 | 700 | 1500 | 3.1
Aug 2027 | 40 | 10 | 500 | 175 | 300 | 975 | 2
Sep 2027 | 25 | 8 | 450 | 150 | 200 | 800 | 1.7
Oct 2027 | 15 | 6 | 400 | 125 | 150 | 675 | 1.4
Nov 2027 | 8 | 5 | 350 | 100 | 100 | 550 | 1.1
Dec 2027 | 5 | 4 | 300 | 75 | 0 | 375 | 0.8