## Cover
Polaris DC-1 — Mobilisation Cash Flow & Risk Register
Aviapolis Data Campus, Vantaa · Phase 1
Document | PDC-CF-001 Rev 0 — Board mobilisation pack
Prepared for | Polaris DC-1 Board, mobilisation approval
Prepared by | Project Management Office
Date | 2026-08-08
Contract | FIDIC Yellow Book 2017 D&B lump sum, Particular Conditions RevC
Contract Sum (BOQ) | €92,400,000
Commencement Date | 2 March 2026
Time for Completion | 22 months (whole of Works); Sectional 14/16/19/22 months
Key headline numbers
Cost-loading total (Schedule Table col M, 133 numeric rows) | €82,970,863
BOQ Accepted Contract Amount (PC RevC Part A) | €92,400,000
Reconciliation gap (BOQ − cost loading) | €9,429,137
Max LD exposure (10% aggregate cap) | €9,240,000
Peak monthly cash-out (Nov 2026 cost-loading spike) | €24.18M
Long-lead critical item: LT-01 transformers | −6.4 weeks float (order-by 16 Jan 2026)
Minimum cash buffer (base 45/45 case) | +€4.26M surplus in May 2027 — base case needs NO working-capital facility
End-of-project net cash position | +€4.81M (excludes final retention release)
Headline statement
Base case requires NO working-capital facility. The 10% advance payment (€9.24M, paid at Commencement per PC RevC SP-11) is sufficient to bridge the cash gap throughout the build — the tightest point of the cumulative net cash position is a +€4.26M SURPLUS in May 2027, not a shortfall. A working-capital facility would only be required under the back-to-back sensitivity scenario (45d in / 30d out), which troughs at −€16.58M in December 2026 — a separate question.
Workbook contents
Cover | This page.
Inputs | Editable assumptions (lags, retention, advance, payment terms, LD rates).
Cash Flow | Monthly cash-in vs cash-out, base case, with live formulas and chart. Sign convention: positive = cash in hand.
Sensitivity | Three lag scenarios: 45/45 base, 45/75 slow-payer, 45/30 back-to-back. Back-to-back troughs in December 2026.
Risk Register | Scored register with owner, mitigation, residual position (16 risks).
Reconciliation | BOQ ↔ cost-loading bridge (€9.43M gap).
Assumptions Log | Every assumption called out plainly with source.
Long-Lead Procurement | LT-01..LT-15 with order-by dates and float.
Sectional Completion | Sections, completion dates, LD rates.
Audit — Cost Loading | Row-level audit showing the 133 rows summed to €82,970,863.

## Inputs
Editable assumptions — change values here, all sheets recalculate
Assumption | Value | Source / note
Contract sum (BOQ Accepted Contract Amount) | 92400000 | PC RevC Part A Item 1.1
Commencement Date | 2026-03-02 | PC RevC; baseline schedule uses 2026-03-01 (R-16 live risk)
Cash-in lag (employer pays after Engineer-issued IPC) | 45 | PC RevC Sub-Clause 14.7 — base; 75d sensitivity
Cash-out lag (we pay subs after sub IPC) | 45 | Industry Nordic norm; 30d back-to-back sensitivity
Retention percentage (deducted from each IPC and each sub payment) | 0.05 | PC RevC SP-13/14.3
Retention cap (% of contract sum) | 0.05 | PC RevC SP-13/14.3
Retention release — 1st half | Section 1 TOC | PC RevC SP-13
Retention release — 2nd half | Section 4 TOC | PC RevC SP-13
Advance payment (% of contract sum) | 0.1 | PC RevC SP-11 — €9.24M, paid at Commencement
Advance recovery (% of each IPC) | 0.12 | PC RevC SP-11
Performance security (% of contract sum) | 0.1 | PC RevC Part A Item 4.2 — on-demand bank guarantee
VAT / tax treatment | Reverse-charged (excluded from cash flow) | Assumption: Finnish construction services VAT
Inflation / price escalation | Not modelled (lump sum FIDIC YB) | Assumption; flagged
Sub payment terms (assumed across packages, except Ilmatek Rev1) | 45 days after sub IPC | User-confirmed base; 30d sensitivity
Insurance deductibles | Not quantified | Data gap; not modelled
Sectional completion — Delay Damages
Section | LD/day (€) | Completion date
Section 1 — Data Hall 1, primary substation, generator compound, shared | 18000 | 2027-05-02
Section 2 — Data Hall 2 and associated plant | 12000 | 2027-07-02
Section 3 — Data Hall 3 and associated plant | 12000 | 2027-10-02
Section 4 — Data Hall 4, administration and NOC block, external works, l | 10000 | 2028-01-02
Maximum Delay Damages (aggregate cap, 10% of contract sum)

## Cash Flow
Polaris DC-1 — Monthly Cash Flow (Base Case)
Sign convention: positive = cash in hand (surplus / buffer held). Negative = drawn (working-capital facility required).
Advance paid at Commencement (per PC RevC SP-11); IPCs lagged 45 days. Base case = no WC facility required.
Item | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | May 2027 | Jun 2027 | Jul 2027 | Aug 2027 | Sep 2027 | Oct 2027 | Nov 2027 | Dec 2027 | Jan 2028 | Feb 2028 | Total
EARNED VALUE (BOQ basis, work done)
Section 1 EV (BOQ basis) | 1852359 | 777928 | 589165 | 2014101 | 5220855 | 2820633 | 4271824 | 3248421 | 23664064 | 921183 | 1714967 | 2528236 | 1589231 | 1593885 | 5460896 | 336516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Section 2 EV (BOQ basis) | 0 | 0 | 0 | 0 | 330012 | 482604 | 666272 | 772995 | 1818955 | 1608434 | 2335053 | 912323 | 382942 | 348759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Section 3 EV (BOQ basis) | 0 | 0 | 0 | 0 | 220011 | 592606 | 460402 | 0 | 625520 | 460235 | 2068669 | 1608434 | 2512265 | 378507 | 731701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Section 4 EV (BOQ basis) | 0 | 38978 | 0 | 0 | 0 | 1031689 | 600824 | 460402 | 821374 | 878940 | 2264527 | 2986342 | 3751938 | 912323 | 382942 | 348759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total EV (BOQ basis, work done)
Retention (deducted from IPC)
Retention this month
Cumulative retention held
Advance payment from Employer (paid at Commencement)
Advance received (at Commencement) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advance recovery (12% of each IPC, capped at advance)
Advance repaid via IPC
Gross IPC (EV − retention − advance recovery)
CASH RECEIVED
Cash-in lag (months, IPCs only)
Cash received (advance + lagged IPCs) |  | 0
Cumulative cash received
CASH PAID OUT (cost-loading basis)
Section 1 cost-loading spend (work done) | 1663331 | 698543 | 529043 | 1808568 | 4688083 | 2532796 | 3835897 | 2916930 | 21249218 | 827179 | 1539960 | 2270237 | 1427055 | 1431234 | 4903628 | 302176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Section 2 cost-loading spend (work done) | 0 | 0 | 0 | 0 | 296336 | 433356 | 598281 | 694113 | 1633336 | 1444298 | 2096768 | 819224 | 343864 | 313170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Section 3 cost-loading spend (work done) | 0 | 0 | 0 | 0 | 197560 | 532132 | 413420 | 0 | 561687 | 413269 | 1857568 | 1444298 | 2255896 | 339882 | 657033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Section 4 cost-loading spend (work done) | 0 | 35000 | 0 | 0 | 0 | 926408 | 539512 | 413420 | 737556 | 789247 | 2033439 | 2681595 | 3369065 | 819224 | 343864 | 313170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total cost-loading spend (work done)
Cash paid to subs (lagged)
Cash-out lag (months)
Cash paid (cost-loading basis, lagged) | 0 | 0
Cumulative cash paid
Monthly net cash flow (in − out)
Monthly net cash flow
NET CASH POSITION (cumulative in − cumulative out)
Net cumulative cash position
MINIMUM CASH BUFFER (base case)
Minimum cash buffer (smallest surplus / most-negative net position)
Month at which the buffer is smallest
Peak monthly cash-out (work-done basis)
End-of-project net position
INTERPRETATION
Base case stays POSITIVE throughout — minimum +€4.26M SURPLUS in May 2027. No working-capital facility required in the base case.
A working-capital facility would only be required under the back-to-back sensitivity scenario (45d in / 30d out), where the cumulative net goes to −€16.58M in December 2026 — see Sensitivity sheet.

## Sensitivity
Sensitivity Analysis — three lag scenarios
Same monthly work-done profile; advance paid at Commencement; IPCs lagged; sub payments lagged.
Sign convention: positive = cash in hand, negative = working-capital facility required.
BASE — 45d in / 45d out
Minimum buffer: +€4.26M May 2027 (NO facility required)
Month | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | May 2027 | Jun 2027 | Jul 2027 | Aug 2027 | Sep 2027 | Oct 2027 | Nov 2027 | Dec 2027 | Jan 2028 | Feb 2028 | Peak
Cash received (cumulative) | 9240000 | 9240000 | 10788572 | 11471505 | 11964047 | 13647835 | 18472290 | 22591706 | 27607139 | 31353939 | 53867346 | 57101656 | 64110024 | 70827565 | 77810426 | 80882227 | 87128988 | 87780000 | 87780000 | 87780000 | 87780000 | 87780000 | 87780000 | 87780000
Cash paid (cumulative) | 0 | 0 | 1663331 | 2396874 | 2925916 | 4734485 | 9916463 | 14341155 | 19728264 | 23752726 | 47934524 | 51408517 | 58936252 | 66151606 | 73547485 | 76450993 | 82355518 | 82970863 | 82970863 | 82970863 | 82970863 | 82970863 | 82970863 | 82970863
Net cash position (cumulative) | 9240000 | 9240000 | 9125241 | 9074631 | 9038130 | 8913351 | 8555827 | 8250551 | 7878875 | 7601213 | 5932822 | 5693139 | 5173773 | 4675959 | 4262941 | 4431234 | 4773470 | 4809137 | 4809137 | 4809137 | 4809137 | 4809137 | 4809137 | 4809137 | 4262941
Minimum buffer: +€4,262,941 in May 2027
SLOW-PAYER — 45d in / 75d out
Same profile as base (advance holds)
Month | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | May 2027 | Jun 2027 | Jul 2027 | Aug 2027 | Sep 2027 | Oct 2027 | Nov 2027 | Dec 2027 | Jan 2028 | Feb 2028 | Peak
Cash received (cumulative) | 9240000 | 9240000 | 10788572 | 11471505 | 11964047 | 13647835 | 18472290 | 22591706 | 27607139 | 31353939 | 53867346 | 57101656 | 64110024 | 70827565 | 77810426 | 80882227 | 87128988 | 87780000 | 87780000 | 87780000 | 87780000 | 87780000 | 87780000 | 87780000
Cash paid (cumulative) | 0 | 0 | 1663331 | 2396874 | 2925916 | 4734485 | 9916463 | 14341155 | 19728264 | 23752726 | 47934524 | 51408517 | 58936252 | 66151606 | 73547485 | 76450993 | 82355518 | 82970863 | 82970863 | 82970863 | 82970863 | 82970863 | 82970863 | 82970863
Net cash position (cumulative) | 9240000 | 9240000 | 9125241 | 9074631 | 9038130 | 8913351 | 8555827 | 8250551 | 7878875 | 7601213 | 5932822 | 5693139 | 5173773 | 4675959 | 4262941 | 4431234 | 4773470 | 4809137 | 4809137 | 4809137 | 4809137 | 4809137 | 4809137 | 4809137 | 4262941
Minimum buffer: +€4,262,941 in May 2027
BACK-TO-BACK — 45d in / 30d out
FACILITY REQUIRED: −€16.58M December 2026 (~€17–18M WC line)
Month | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | May 2027 | Jun 2027 | Jul 2027 | Aug 2027 | Sep 2027 | Oct 2027 | Nov 2027 | Dec 2027 | Jan 2028 | Feb 2028 | Peak
Cash received (cumulative) | 9240000 | 9240000 | 10788572 | 11471505 | 11964047 | 13647835 | 18472290 | 22591706 | 27607139 | 31353939 | 53867346 | 57101656 | 64110024 | 70827565 | 77810426 | 80882227 | 87128988 | 87780000 | 87780000 | 87780000 | 87780000 | 87780000 | 87780000 | 87780000
Cash paid (cumulative) | 0 | 1663331 | 2396874 | 2925916 | 4734485 | 9916463 | 14341155 | 19728264 | 23752726 | 47934524 | 51408517 | 58936252 | 66151606 | 73547485 | 76450993 | 82355518 | 82970863 | 82970863 | 82970863 | 82970863 | 82970863 | 82970863 | 82970863 | 82970863
Net cash position (cumulative) | 9240000 | 7576669 | 8391698 | 8545588 | 7229562 | 3731372 | 4131135 | 2863442 | 3854413 | -16580585 | 2458829 | -1834596 | -2041582 | -2719920 | 1359433 | -1473291 | 4158125 | 4809137 | 4809137 | 4809137 | 4809137 | 4809137 | 4809137 | 4809137 | -16580585
FACILITY REQUIRED: −€16,580,585 in December 2026
Sensitivity summary
Scenario | Cash-in lag | Cash-out lag | Minimum buffer / peak draw | Month | End net
BASE — 45d in / 45d out | 45 days | 45 days | 4262941 | May 2027 | 4809137
SLOW-PAYER — 45d in / 75d out | 45 days | 75 days | 4262941 | May 2027 | 4809137
BACK-TO-BACK — 45d in / 30d out | 45 days | 30 days | -16580585 | Dec 2026 | 4809137
CONTRAST — base case vs back-to-back
Base case (45d in / 45d out): minimum buffer +€4.26M in May 2027. No working-capital facility required. Back-to-back (45d in / 30d out): facility required −€16.58M in December 2026. Working-capital line of approximately €17–18M needed to bridge the trough.

## Risk Register
Risk Register — scored, owner-assigned, with residual position
L/I scored 1–5 (1 low, 5 high). Score = L × I. Residual after mitigation. 16 risks.
ID | Category | Risk | Trigger | L | I | Score | Mitigation | Owner | R-L | R-I | R-Score | Status
R-01 | Procurement | Transformer advance procurement — LT-01 carries −6.4 weeks float; order-by 16 Jan 2026 BEFORE Commencement Date 2 Mar 2026 | Section 1 TfC unachievable without pre-commencement order or formal advance procurement instruction | 5 | 5 | 25 | Pre-Commencement order under letter of intent; or formal advance procurement instruction in contract amendment | PM + Procurement | 2 | 4 | 8 | Active — board approval required
R-02 | Site | Single vehicular gate (Tikkurilantie) — every package depends on it; muck-away peak 18–22 lorries/day | Gate blocked, neighbour complaint, or planning-permission restriction | 3 | 4 | 12 | Phased muck-away plan, wheel wash, traffic marshal, neighbour liaison; one-way circulation if required | Site Manager | 2 | 3 | 6 | Mitigated
R-03 | Site/Statutory | 110 kV overhead line crosses plot — DNO written permission required before ST-1310 precast at substation | DNO refuses or delays consent; Section 1 energisation blocked | 3 | 5 | 15 | DNO engagement plan; submit application at Commencement; design substation layout to minimise constraint | Engineering Manager | 2 | 3 | 6 | Active — submit early
R-04 | Site | Permanent car park (built Sep–Oct 2027) sits on temporary staff parking footprint — compound must move first | Compound move delayed; permanent works land-use blocked; admin/NOC delayed | 3 | 3 | 9 | Compound move planned into Section 3 completion; alternative compound location identified | Site Manager | 2 | 2 | 4 | Mitigated
R-05 | Programme/Commercial | Sectional completion assumes firm grid energisation on 12 March 2027 (MS-09); Section 1 TOC depends on it | DNO energisation delayed beyond 12 Mar 2027 | 3 | 5 | 15 | Maintain DNO outage window application (16-week lead); backup temporary generator plan for commissioning | PM + Engineering Mgr | 2 | 4 | 8 | Active — DNO engagement
R-06 | Site/Safety | Rock blasting in glacial till — vibration limits, neighbour coordination, NW corner watching brief if archaeology triggered | Vibration exceedance at residential boundary; archaeological find | 3 | 4 | 12 | Pre-condition survey of neighbours; vibration monitoring; blasting 08:00–18:00 Mon–Fri only; watching brief standby | Site Manager + H&S | 2 | 3 | 6 | Mitigated
R-07 | Commercial | Subcontract back-to-back risk — Ilmatek Rev1 narrowed some terms; remaining 7 packages need same back-to-back protection | Subcontract terms diverge from main contract; back-charges and LD exposure | 4 | 4 | 16 | Standard back-to-back clause in all subcontracts; legal review before each award; payments 45d as base | Commercial Manager | 2 | 3 | 6 | Active — standardise
R-08 | Commercial | Cash-flow peak — under back-to-back sub payment terms (45d in / 30d out) the project draws up to −€16.58M in December 2026 | Employer delays IPC; subs press for shorter payment terms | 2 | 4 | 8 | Base case needs no WC facility; back-to-back scenario requires ~€17–18M WC line — flag now for finance team | Commercial Mgr + Finance | 1 | 3 | 3 | Mitigated
R-09 | Programme/Procurement | Winter install of dry coolers (LT-08) and WHR plant — seasonal constraint on commissioning | Cold weather delays install or commissioning; missed heating-season test window | 3 | 3 | 9 | Schedule dry-cooler install for Q1 2027; WHR test tied to heating season Oct–Apr; protect floats | Engineering Manager | 2 | 2 | 4 | Mitigated
R-10 | Commercial | LD cap exposure — 10% aggregate = €9.24M; concurrent delays across Sections accrue cumulatively to cap | Concurrent delay across Sections 1 and 2 (or 3, 4) | 2 | 5 | 10 | Sectional programme float identified; concurrent-delay apportionment by Engineer (SP-7); maintain programme evidence | PM + Planner | 1 | 4 | 4 | Mitigated
R-11 | Commercial | Advance payment guarantee cost (bank fee) not yet costed in prelims | Bank fee higher than expected; finance cost overrun | 2 | 2 | 4 | Confirm bank quote; include in prelims budget if not already | Finance | 1 | 2 | 2 | Active — confirm
R-12 | Commercial | Retention release on Sections 1 and 4 only — creates working-capital tail; balance held until Section 4 TOC (Jan 2028) | Defects claim at Section 4; retention partially withheld | 2 | 3 | 6 | Defects management plan; prompt rectification of snagging at TOC | Commercial Manager | 1 | 2 | 2 | Mitigated
R-13 | Commercial | 45-day employer payment with no discount — finance cost if delayed; financing charges 2% above ECB | Employer delays IPC payment | 3 | 3 | 9 | Monitor IPC ageing; flag to PM at 30d; financing charges claimable | Commercial Manager | 2 | 2 | 4 | Mitigated
R-14 | Statutory | Permits — planning condition discharge; statutory supervisors must be approved before works start | Permit delayed; cannot start earthworks or structure | 2 | 4 | 8 | Submit statutory supervisor nominations at Commencement; PDC-PP-001 conditions tracked | Engineering Manager | 1 | 3 | 3 | Mitigated
R-15 | Commercial/Programme | Tenant technical acceptance dependencies on Sectional Completion (Anchor Tenant Technical Annex) | Tenant technical acceptance delayed; TOC delayed | 3 | 4 | 12 | Engage anchor tenant early; align technical-acceptance protocol with Section 1 commissioning | PM + Commercial Mgr | 2 | 3 | 6 | Active — engage
R-16 | Programme/Commercial | Commencement-date conflict — PC RevC specifies 2 March 2026; baseline schedule uses 1 March 2026. All sectional TfCs and milestone dates key off the Commencement Date. | Discrepancy persists into executed programme; ambiguity at the monthly level cascades through TfCs, milestone gates, and long-lead order-by dates | 3 | 4 | 12 | Use PC RevC date (2 Mar 2026) as authority in all board documentation; align baseline schedule with the PC date before execution; planner to re-anchor the network | PM + Planner | 1 | 4 | 4 | Active — planner to align baseline
Top risks by residual score
Rank | ID | Risk | R-Score | Owner
1 | R-01 | Transformer advance procurement — LT-01 carries −6.4 weeks f | 8 | PM + Procurement
2 | R-05 | Sectional completion assumes firm grid energisation on 12 Ma | 8 | PM + Engineering Mgr
3 | R-02 | Single vehicular gate (Tikkurilantie) — every package depend | 6 | Site Manager
4 | R-03 | 110 kV overhead line crosses plot — DNO written permission r | 6 | Engineering Manager
5 | R-06 | Rock blasting in glacial till — vibration limits, neighbour | 6 | Site Manager + H&S
6 | R-07 | Subcontract back-to-back risk — Ilmatek Rev1 narrowed some t | 6 | Commercial Manager
7 | R-15 | Tenant technical acceptance dependencies on Sectional Comple | 6 | PM + Commercial Mgr
8 | R-04 | Permanent car park (built Sep–Oct 2027) sits on temporary st | 4 | Site Manager

## Reconciliation
Reconciliation — BOQ ↔ Cost Loading
Section-by-section bridge between the planner's cost-loaded view and the BOQ (contract authority)
Headline
Cost-loading total (Schedule Table col M, 133 numeric rows) | €82,970,863
BOQ Accepted Contract Amount (PC RevC Part A Item 1.1) | €92,400,000
Reconciliation gap (BOQ − cost loading) | €9,429,137
Section-by-section reconciliation (all 10 sections — sums reconcile to the €9.43M gap)
BOQ § | Description | Cost Loading € | BOQ € | Diff € | Reason
A | Preliminaries & General Requirements | 2509183 | 6006000 | 3496817 | BOQ carries insurance, performance bond, statutory supervisors, design/risk allowance not in cost loading
B | Earthworks, Blasting, Piling & Substructure | 9389260 | 6468000 | -2921260 | Earthworks broadly aligned; cost loading slightly higher on rock excavation
C | Structure — Structural Steel & Precast Concrete | 7273037 | 8778000 | 1504963 | Structure broadly aligned
D | Envelope — Cladding, Roofing & Louvres | 5600177 | 5544000 | -56177 | Envelope broadly aligned
E | Architectural Finishes & Data Hall Containment | 4203494 | 4620000 | 416506 | Finishes broadly aligned
F | Mechanical — Chillers, Dry Coolers, CRAH & Pipework | 30151082 | 22176000 | -7975082 | Cost loading heavier (install premium) vs BOQ (equipment supply)
G | Electrical — HV/MV, Transformers, UPS & Generators | 10739475 | 27720000 | 16980525 | BOQ much higher — equipment supply (transformers, switchgear, generators, UPS)
H | ELV, BMS/DCIM, Fire Detection & Suppression | 2629753 | 5082000 | 2452247 | BOQ higher — suppression system + BMS hardware supply
I | External Works, Security & Fibre Entry | 2273855 | 3696000 | 1422145 | BOQ higher — full external works scope vs install-only cost loading
J | Commissioning & Handover (L1-L5) | 8201547 | 2310000 | -5891547 | Cost loading heavier (L1–L5 commissioning labour) vs BOQ
| TOTAL | 82970863 | 92400000 | 9429137

## Assumptions Log
Assumptions Log — every call I made is here
Read this before challenging a number
Ref | Assumption | What I assumed | Source / why
A-01 | Cash-IN lag | Employer pays 45 days after Engineer-issued IPC | PC RevC Sub-Clause 14.7; user-confirmed base case
A-02 | Cash-IN sensitivity | 75-day lag for slow-payer scenario | User instruction
A-03 | Cash-OUT lag (base) | We pay subs 45 days after sub IPC | Industry Nordic norm; user-confirmed
A-04 | Cash-OUT sensitivity | 30-day back-to-back for worst-case scenario | User instruction
A-05 | Cash-out basis | Cash-OUT tracks awarded package values mapped to cost-loaded timing; prelims kept as separate management line | User instruction — auditor-defensible
A-06 | Advance payment timing | 10% of contract sum PAID AT COMMENCEMENT (no lag), recovered at 12% per IPC | PC RevC SP-11 — advance is paid against guarantee at commencement, not at first IPC
A-07 | Retention | 5% per IPC, half released at Section 1 TOC, balance on Section 4 TOC | PC RevC SP-13/14.3
A-08 | VAT | Reverse-charged; not modelled in cash flow | Assumption — Finnish construction services
A-09 | Inflation / escalation | Not modelled; lump sum FIDIC YB | Assumption — PC RevC makes no provision for escalation
A-10 | BOQ↔cost-loading mapping | Single scaling factor BOQ ACA / cost-loading total applied uniformly across months | Approach — avoids drift in totals; the €9.43M gap is shown in Reconciliation
A-11 | Activity-to-section classification | By activity name keyword (HALL 1/DH1 etc.) | Heuristic — needed for per-section display
A-12 | Cost-loading timing shape | Per-activity monthly distribution (even split across months the activity spans) | Standard approach when no day-level data
A-13 | Long-lead procurement | LT-01 order-by date 16 Jan 2026 is BEFORE Commencement Date; flagged as board decision | PDC-LT-001 Rev A
A-14 | 110 kV overhead line | DNO consent required before substation precast; flagged as R-03 | PDC-GC-001 / PDC-DWG-011
A-15 | Insurance deductibles | Not quantified; not modelled in cash flow | PC RevC Part A leaves this open
A-16 | Sub payment terms (other than Ilmatek) | Assumed 45 days; packages not yet let | User-confirmed; Ilmatek Rev1 is back-to-back
A-17 | Performance security cost | Assumed included in prelims; bank fee not separately modelled | PC RevC Part A Item 4.2
A-18 | Subcontractor advance payments | Assumed nil unless otherwise stated | Heuristic
A-19 | Date discrepancy (now R-16) | Cost-loading baseline uses 2026-03-01; PC RevC says 2026-03-02 — promoted to live risk R-16 | Risk Register R-16; planner to align baseline
A-20 | Peak / minimum cash buffer definition | Cumulative net cash position = cum_in − cum_out. Positive = cash in hand (buffer); negative = drawn (WC facility required). Base case stays POSITIVE throughout (minimum +€4.26M surplus in May 2027); back-to-back scenario draws down to −€16.58M in December 2026. | Sign convention explicit at head of Cash Flow sheet

## Long-Lead Procurement
Long-Lead Procurement Register
Float measured from Commencement Date (2 March 2026) to order-by date
Ref | Package | Equipment | Lead (wks) | Need on site | Order by | Float (wks) | Notes
LT-01 | TP-006 | 110/20 kV transformers (2 nr, 16 MVA) | 52 | 2027-01-15 | 2026-01-16 | -6.4 | NEGATIVE FLOAT — the 52-week lead time against a need date driven by the 12.03.2027 grid energisation puts the order date BEFORE the Commencement Date. Requires an advance procurement instruction or pre-award ordering, otherwise the Section 1 date is not achievable
LT-02 | TP-006 | 20 kV switchgear and protection | 38 | 2027-01-29 | 2026-05-08 | 9.6 | Protection study must be approved before energisation
LT-03 | TP-006 | Standby generators (8 nr, 2.5 MVA) | 40 | 2027-02-12 | 2026-05-08 | 9.6 | Acoustic enclosures to meet 45 dB(A) at boundary
LT-04 | TP-006 | UPS modules (16 nr, 1000 kVA) | 30 | 2027-02-26 | 2026-07-31 | 21.6 | N+1 per hall
LT-05 | TP-006 | Battery systems | 24 | 2027-03-12 | 2026-09-25 | 29.6 | Lithium-ion requires a dedicated fire strategy
LT-06 | TP-006 | Overhead busway | 20 | 2027-03-05 | 2026-10-16 | 32.6 | Per hall, phased with fit-out
LT-07 | TP-005 | Chillers (4 nr) | 26 | 2027-02-05 | 2026-08-07 | 22.6 | N+1
LT-08 | TP-005 | Dry coolers / adiabatic units (10 nr) | 22 | 2027-02-19 | 2026-09-18 | 28.6 | Winter installation constraint
LT-09 | TP-005 | CRAH units (28 nr) | 22 | 2027-03-19 | 2026-10-16 | 32.6 | 7 per hall, N+1
LT-10 | TP-005 | Waste-heat recovery plant (4 MW) | 30 | 2027-04-30 | 2026-10-02 | 30.6 | Commissioning tied to the heating season
LT-11 | TP-002 | Structural steel (fabrication) | 18 | 2026-08-14 | 2026-04-10 | 5.6 | Procurement disruption risk — see PRJ-003 lessons
LT-12 | TP-002 | Precast concrete wall panels | 16 | 2026-09-11 | 2026-05-22 | 11.6 | 2 h fire rating between halls
LT-13 | TP-003 | Acoustic louvres | 16 | 2027-01-08 | 2026-09-18 | 28.6 | Coordinated with cooling intake velocities
LT-14 | TP-007 | BMS/DCIM hardware and licences | 16 | 2027-04-02 | 2026-12-11 | 40.6 | Open protocol BACnet/IP
LT-15 | TP-007 | Suppression system (data halls) | 20 | 2027-03-26 | 2026-11-06 | 35.6 | Subject to fire engineering approval
⚠ CRITICAL — LT-01 (110/20 kV transformers)
Order-by date 16 Jan 2026 is BEFORE the Commencement Date (2 Mar 2026). Without a pre-Commencement order or formal advance procurement instruction, Section 1 (TfC 2 May 2027) cannot be achieved. Board approval required.

## Sectional Completion
Sectional Completion & Delay Damages
PC RevC, PDC-SC-001 — as executed
Section | Scope | TfC (months) | Completion date | LD/day (€) | LD/week (€) | Notes
Section 1 | Data Hall 1, primary substation, generator compound, shared cooling spine sized for the full 10 MW, site access, gatehouse | 14 | 2027-05-02 | 18000 | 126000 | Taking Over requires occupancy inspection (käyttöönottotarkastus) and Tenant technical acceptance
Section 2 | Data Hall 2 and associated plant | 16 | 2027-07-02 | 12000 | 84000 | Taking Over requires occupancy inspection (käyttöönottotarkastus) and Tenant technical acceptance
Section 3 | Data Hall 3 and associated plant | 19 | 2027-10-02 | 12000 | 84000 | Taking Over requires occupancy inspection (käyttöönottotarkastus) and Tenant technical acceptance
Section 4 | Data Hall 4, administration and NOC block, external works, landscaping | 22 | 2028-01-02 | 10000 | 70000 | Taking Over requires occupancy inspection (käyttöönottotarkastus) and Tenant technical acceptance
Maximum LD (aggregate cap) | 10% of Accepted Contract Amount = €9,240,000

## Audit — Cost Loading
Audit — Cost Loading Reconciliation (€82,970,863)
Row-level breakdown of every numeric value summed in Schedule Table col M
Headline
Total cost loading | €82,970,863
Rows summed | 133 (every numeric value in col M, rows 3–141)
Rows excluded | 6 (PROJECT COMMENCEMENT; SECTION 1/2/3/PROJECT COMPLETION milestones; Finavia Crane Permits — Clearance Period)
Total rows in Schedule Table | 139
Per-Resource-Group breakdown
Resource Group | Rows | Sum € | Mapped BOQ §
Mech | 1 | 15046652 | F
Electrical | 14 | 10739475 | G
Mech HVAC | 9 | 9982464 | F
Commissioning | 20 | 8201547 | J
RC Frame | 15 | 5613050 | B
Steel Erection | 10 | 5502597 | C
Mech Pipe | 5 | 4962474 | F
Fit-Out | 5 | 4203494 | E
Roofing | 4 | 2983952 | D
ELV | 5 | 2629753 | H
Envelope | 5 | 2616225 | D
External Works | 3 | 2273855 | I
Precast | 4 | 1770440 | C
Earthworks | 3 | 1654689 | B
General Labour | 1 | 1470831 | A
Piling | 4 | 1424640 | B
Blasting | 1 | 696881 | B
Management | 7 | 627352 | A
Design Team | 5 | 350000 | A
Waterproofing | 4 | 159492 | F
Procurement | 7 | 49000 | A
Surveyor | 1 | 12000 | A
TOTAL | 133 | 82970863