# Polaris DC-1 — Execution Plan

Aviapolis Data Campus, Vantaa · Phase 1 · FIDIC Yellow Book 2017 D&B

Document: PDC-EP-001 Rev 0

Prepared for: Polaris DC-1 Board, mobilisation approval

Prepared by: Project Management Office

Date: 8 August 2026

Contract: FIDIC Yellow Book 2017 Design & Build lump sum, Particular Conditions RevC

Contract Sum: €92,400,000 (BOQ Accepted Contract Amount, PC RevC Part A Item 1.1)

Commencement Date: 2 March 2026  |  Time for Completion: 22 months (whole of Works)

(Note: PC RevC says 2 March 2026; baseline schedule uses 1 March 2026 — promoted to live Risk R-16 in the workbook Risk Register.)

# 1. Executive summary

Polaris DC-1 is a four-data-hall hyperscale campus on the Aviapolis site in Vantaa, delivered under a FIDIC Yellow Book 2017 D&B lump sum contract. The contract is split into four Sections with their own Time for Completion and Delay Damages: DH1 + shared infrastructure (14 months, TfC 2 May 2027), DH2 (16 months, 2 July 2027), DH3 (19 months, 2 October 2027), DH4 + admin/NOC + external works (22 months, 2 January 2028 — whole of the Works). The Accepted Contract Amount is €92.4M; maximum LD exposure is 10% of that = €9.24M.

Three board asks are packaged in this plan:

Authorise pre-Commencement procurement of LT-01 transformers (110/20 kV, 16 MVA, 52-week lead). Without it, the Section 1 date is unachievable. (See §4 and Risk R-01.)

Endorse the sectional completion framework and the four TfCs as the delivery thesis.

Approve the 10% advance payment (€9.24M) and 10% performance security execution, both supported by the PC RevC.

## 1.1 Headline cash-flow finding

The base case (45d employer payment, 45d sub payment, 10% advance paid at Commencement per PC RevC SP-11) requires NO working-capital facility. The tightest point of the cumulative net cash position is a +€4.26M SURPLUS in May 2027 — not a shortfall. A working-capital facility would only be required under the back-to-back sub-payment sensitivity (30d instead of 45d), where the cumulative net drops to −€16.58M in December 2026 — a separate question the board should consider when standardising the subcontract terms across TP-001 to TP-008. See §9 for the full cash-flow discussion.

# 2. Project context

Scope: a 4-hall, ~26,500 m² data campus with primary substation, generator compound, shared cooling spine sized for the full 10 MW IT load, admin/NOC block, gatehouse, external works, security and fibre entry. Delivery is design-and-build lump sum. The Employer (Polaris Digital Infrastructure Oy), the Contractor (NordBuild Oy), and the Engineer (Norvia Consulting Oy) are named in the Particular Conditions.

Commercial baseline:

Contract sum: €92,400,000 (BOQ PDC-BOQ-001 Rev A, confirmed by PC RevC Part A Item 1.1)

Payment: Engineer IPC ≤28d, Employer 45d after IPC (Sub-Clauses 14.6 / 14.7). 5% retention (SP-13). 10% advance (SP-11) PAID AT COMMENCEMENT against guarantee, recovered at 12% per IPC.

Performance security: 10% on-demand bank guarantee (Part A Item 4.2). No parent company guarantee required.

Limit of liability: capped at contract sum, with carve-outs for death/injury, fraud, wilful misconduct, abandonment, insurance proceeds (Sub-Clause 1.15 + SP-3).

Insurance: PI €10M each and every claim, 6 years after last TOC; TPL €5M per occurrence unlimited aggregate (Part A Items 19.2.3 / 19.2.4).

BOQ ↔ cost-loading reconciliation (see Appendix A): the planner's cost-loaded baseline (Schedule Table col M) sums to €82,970,863 (verified by summing every numeric value in 133 rows; 6 milestone/hold rows excluded); the BOQ is €92,400,000. The €9.43M gap is a structural shift — the cost loading is a labour + install view (its 22 Resource Groups are crews), while the BOQ carries full equipment supply in Sections F (mechanical), G (electrical) and H (ELV). See §11 and Appendix A. Row-level audit of the 133 summed rows is in the workbook (Audit — Cost Loading sheet).

# 3. Sequence and phasing — sectional completion

The four Sections are not just contractual milestones — they are the entire delivery thesis. Each Section has its own Time for Completion, its own Delay Damages rate, and its own physical scope. The TfCs build cumulatively: Section 1 includes everything the other halls depend on.

## Section 1 — TfC 14 months — completion 2 May 2027

Scope: Data Hall 1, primary substation, generator compound (8 × 2.5 MVA standby sets), shared cooling spine sized for the full 10 MW IT load, site access from Tikkurilantie, gatehouse.

Critical-path drivers: the 110 kV grid energisation (MS-09) on 12 March 2027; the 110/20 kV transformer procurement (LT-01, 52-week lead, −6.4 weeks float); the shared cooling spine; the L1–L5 commissioning sequence (MS-11 to MS-13). LD/day: €18,000 (highest of the four Sections).

Cost-loading profile: cost-loaded work for Section 1 runs to approximately €44.8M (work-done basis, incl. pro-rated prelims); BOQ EV for Section 1 ≈ €36.8M (lower because Section 1's BOQ value is concentrated in equipment supply that lands in cost-loaded Section 6 equipment install).

Commencement date note: all Section dates key off 2 March 2026 (PC RevC). The planner's baseline schedule currently uses 1 March 2026 — promoted to live Risk R-16 in the workbook Risk Register. Action: planner to align baseline with PC date before execution.

## Section 2 — TfC 16 months — completion 2 July 2027

Scope: Data Hall 2 + associated plant. Critical-path drivers: structural steel erection (LT-11), envelope completion, CRAH install (LT-09), commissioning. LD/day: €12,000.

## Section 3 — TfC 19 months — completion 2 October 2027

Scope: Data Hall 3 + associated plant. Critical-path drivers: parallel hall-3 build following the Section 2 pattern; waste-heat-recovery plant commissioning tied to the heating season (Oct–Apr only, MS-17). LD/day: €12,000.

## Section 4 — TfC 22 months — completion 2 January 2028 (whole of Works)

Scope: Data Hall 4 + admin/NOC block + external works + landscaping. Critical-path drivers: external works after Section 3 completion; permanent car park (Sep–Oct 2027) on the temporary staff-parking footprint, which forces a compound-move sequence (R-04). LD/day: €10,000.

Sectional Completion & Delay Damages summary (per PDC-SC-001 Rev C, executed):

| Section | TfC (mo) | Completion date | LD/day (€) | LD/week (€) |
| --- | --- | --- | --- | --- |
| 1 — DH1 + substation + shared cooling spine + gatehouse | 14 | 2 May 2027 | 18,000 | 126,000 |
| 2 — DH2 + plant | 16 | 2 Jul 2027 | 12,000 | 84,000 |
| 3 — DH3 + plant | 19 | 2 Oct 2027 | 12,000 | 84,000 |
| 4 — DH4 + admin/NOC + external works | 22 | 2 Jan 2028 | 10,000 | 70,000 |
| AGGREGATE CAP | — | — | — | 9,240,000 |

# 4. Long-lead procurement

The procurement lead-time register (PDC-LT-001 Rev A) identifies 15 long-lead items. Order-by dates are back-calculated from the need-on-site date against the Commencement Date of 2 March 2026. One item carries NEGATIVE FLOAT — see below.

⚠ LT-01 — 110/20 kV transformers (2 nr, 16 MVA, TP-006): 52-week lead, need on site 15 January 2027, order by 16 January 2026, FLOAT −6.4 WEEKS. Without a pre-Commencement order under letter of intent, or a formal advance procurement instruction in the contract, Section 1 (TfC 2 May 2027) is unachievable. This is the single biggest live issue for the board. (Risk R-01.)

| Ref | Pkg | Equipment | Lead (wks) | Need on site | Order by | Float (wks) |
| --- | --- | --- | --- | --- | --- | --- |
| LT-01 | TP-006 | 110/20 kV transformers (2 nr, 16 MVA) | 52 | 2027-01-15 | 2026-01-16 | −6.4 |
| LT-02 | TP-006 | 20 kV switchgear + protection | 38 | 2027-01-29 | 2026-05-08 | +9.6 |
| LT-03 | TP-006 | Standby generators (8 nr, 2.5 MVA) | 40 | 2027-02-12 | 2026-05-08 | +9.6 |
| LT-04 | TP-006 | UPS modules (16 nr, 1000 kVA) | 30 | 2027-02-26 | 2026-07-31 | +21.6 |
| LT-05 | TP-006 | Battery systems (Li-ion) | 24 | 2027-03-12 | 2026-09-25 | +29.6 |
| LT-06 | TP-006 | Overhead busway | 20 | 2027-03-05 | 2026-10-16 | +32.6 |
| LT-07 | TP-005 | Chillers (4 nr) | 26 | 2027-02-05 | 2026-08-07 | +22.6 |
| LT-08 | TP-005 | Dry coolers / adiabatic (10 nr) | 22 | 2027-02-19 | 2026-09-18 | +28.6 |
| LT-09 | TP-005 | CRAH units (28 nr) | 22 | 2027-03-19 | 2026-10-16 | +32.6 |
| LT-10 | TP-005 | Waste-heat recovery plant (4 MW) | 30 | 2027-04-30 | 2026-10-02 | +30.6 |
| LT-11 | TP-002 | Structural steel fabrication | 18 | 2026-08-14 | 2026-04-10 | +5.6 |
| LT-12 | TP-002 | Precast concrete wall panels | 16 | 2026-09-11 | 2026-05-22 | +11.6 |
| LT-13 | TP-003 | Acoustic louvres | 16 | 2027-01-08 | 2026-09-18 | +28.6 |
| LT-14 | TP-007 | BMS/DCIM hardware and licences | 16 | 2027-04-02 | 2026-12-11 | +40.6 |
| LT-15 | TP-007 | Suppression system (data halls) | 20 | 2027-03-26 | 2026-11-06 | +35.6 |

# 5. Site set-up

Per PDC-LOG-001 (company standard, sizing tables) and the per-package baselines and PDC-DWG-017 site logistics plan:

Site establishment is sized for a peak of ~250 operatives and 28 staff: offices 224 m², canteen 150 m², drying/changing 125 m², WCs 10, basins 13, first-aid 40 m²; total ≈600 m² net / ≈380 m² two-storey footprint; must sit within 200 m of the working face (else satellite welfare needed).

Parking: 1 space per 2.5 operatives at 25 m²/space incl. aisles; 6 visitor spaces outside the secure line; segregated footpath to welfare.

One vehicular gate (Tikkurilantie) — every package depends on it. GW-1010 establishes the gate (PDC-SCH-001).

Single 250 t mobile crane working east along the halls; 600–900 m² laydown per hall (30×20 m standing plus clear radius).

Peak muck-away 18–22 lorry movements per day through the single gate (GW-1100); wheel wash required at the earthworks exit.

Bulk-earthworks stockpile (Kallio 4,200 m² peak laydown) is the single biggest area constraint on the plot.

Permanent car park (EX-1500, Sep–Oct 2027) is built on the temporary staff parking footprint — compound must move first. (Risk R-04.)

110 kV overhead line crosses the plot — DNO written permission required before ST-1310 precast at the substation. (Risk R-03.)

Working restrictions per PDC-PP-001: blasting 08:00–18:00 Mon–Fri; generator testing 09:00–16:00 Mon–Fri; night-time noise 45 dB(A) at NE boundary.

# 6. Package interfaces

Eight tender packages (TP-001 through TP-008) plus main-contract prelims and commissioning. Interfaces and sequencing:

TP-001 Earthworks & Substructure — Bulk earthworks (rock excavation by blasting, glacial till) and piling. Driven by Section 1 — must be substantially complete before structural steel erection (TP-002) and the substation pad foundations. Permits and pre-condition surveys gate the work.

TP-002 Structural Steel & Precast — Steel frame (65 kg/m²), steel to MEP spine, mezzanine and plant support steelwork, precast wall panels (2 h fire rating between halls). LT-11 (18 wks) is the critical path.

TP-003 Envelope — Cladding, roofing, acoustic louvres. Cannot start until TP-002 has handed over zones weathertight. LT-13 (16 wks) has 28.6 wks float — not critical.

TP-004 Architectural Finishes & Data Hall Containment — Raised access, fire-rated partitions, finishes. Phased per hall after envelope. Heavy coordination with TP-005 (MEP rough-in) and TP-006 (electrical containment).

TP-005 Mechanical — Chillers, dry coolers, CRAH units, waste-heat recovery plant, pipework. Critical-path equipment (LT-07 to LT-10). WHR plant commissioning tied to the heating season Oct–Apr (MS-17).

TP-006 Electrical — HV/MV, transformers (LT-01, the critical item), switchgear, generators, UPS, busway. Critical-path; LT-01 is the binding constraint.

TP-007 ELV, BMS/DCIM, Fire Detection & Suppression — Open-protocol BACnet/IP BMS; suppression system subject to fire-engine approval (LT-15).

TP-008 External Works, Security & Fibre Entry — Perimeter fencing, security, fibre entry. Mostly Section 4 work, but the early fibre entry and security mast must be in place before any DNO commissioning.

Commissioning — Main-contract L1–L5 (per BOQ Section J): L1 factory acceptance, L2 site acceptance, L3 pre-integration, L4 integrated systems testing (MS-11, Month 13), L5 24 h load-bank test (MS-12, Month 14).

# 7. Commercial terms that affect delivery

Advance payment 10% (€9.24M) — PAID AT COMMENCEMENT against advance payment guarantee (SP-11); recovered at 12% per IPC. Provides early cash-flow bridge for mobilisation, design and the first wave of long-lead procurement.

Retention 5% per IPC, half released on Section 1 TOC, balance on Section 4 TOC (SP-13). Creates a working-capital tail of €4.62M held until Section 4 in January 2028.

Sectional Delay Damages: €18k / €12k / €12k / €10k per day for Sections 1–4 (max €126k / €84k / €84k / €70k per week). Aggregate cap 10% of contract sum = €9.24M.

Performance security: 10% (€9.24M) on-demand bank guarantee (Part A Item 4.2).

Concurrent delay: apportionment by the Engineer (SP-7); no Cost for concurrent periods.

Sole remedy for delay: Delay Damages (SP-8) — no parallel common-law damages.

Sign convention for cash flow (workbook Cash Flow tab): positive cumulative net = cash in hand (buffer); negative cumulative net = working-capital facility required.

# 8. Risk summary — top items

Sixteen risks are scored in the Risk Register sheet of the cash flow workbook (PDC-CF-001 Rev 0). Top six by residual score:

| Rank | ID | Risk | R-Score | Owner |
| --- | --- | --- | --- | --- |
| 1 | R-01 | LT-01 transformers, −6.4 wks float; Section 1 at risk | 8 | PM + Procurement |
| 2 | R-05 | Grid energisation MS-09 (12 Mar 2027) gates Section 1 TOC | 8 | PM + Engineering Mgr |
| 3 | R-03 | 110 kV overhead line — DNO consent before substation precast | 6 | Engineering Manager |
| 4 | R-06 | Rock blasting — vibration, neighbour, archaeology trigger | 6 | Site Manager + H&S |
| 5 | R-15 | Tenant acceptance dependencies on Sectional Completion | 6 | PM + Commercial Mgr |
| 6 | R-08 | Back-to-back sub terms draw to −€16.58M in December 2026 | 3 | Commercial Mgr + Finance |
| 7 (new) | R-16 | Commencement-date conflict (PC 2 Mar vs baseline 1 Mar) | 4 | PM + Planner |

# 9. Cash flow highlights

Base case (45d in / 45d out, 10% advance paid at Commencement, 5% retention):

Minimum cash buffer: +€4.26M SURPLUS in May 2027. The cumulative net cash position stays POSITIVE throughout the build — the 10% advance (€9.24M, paid at Commencement per PC RevC SP-11) is sufficient to bridge the cash gap. Peak monthly cash-out €24.18M in November 2026; end-of-project net +€4.81M. The base case requires NO working-capital facility.

Sensitivity (workbook Sensitivity sheet, three scenarios):

Slow-payer scenario (45d in / 75d out) — minimum buffer +€4.26M in May 2027 (same as base; advance holds).

Back-to-back scenario (45d in / 30d out) — facility required −€16.58M in December 2026. A working-capital line of approximately €17–18M would be needed to bridge the trough if subs press for shorter payment terms. (This is the real facility case — see §1.1 headline.)

Sign convention (workbook Cash Flow tab): positive = cash in hand (buffer); negative = drawn (WC facility required). The label 'minimum cash buffer' replaces the earlier 'peak funding requirement' because the base case never goes negative — it is the tightest point of a surplus, not a funding shortfall.

All three sensitivities assume sub payment terms as stated. A genuine sub-side dispute that delays sub-IPC processing would change the picture and is flagged in the workbook assumptions log (A-03, A-04).

# 10. Assumptions

The full assumptions log is in the workbook (Assumptions Log sheet). Headline items:

Employer pays 45 days after Engineer-issued IPC (PC RevC Sub-Clause 14.7; user-confirmed base case). 75-day sensitivity shown in workbook.

Advance payment (10%) PAID AT COMMENCEMENT against guarantee (PC RevC SP-11), recovered at 12% per IPC. (Critical — see §7 and §9.)

We pay subs 45 days after sub IPC (industry Nordic norm; user-confirmed). 30-day sensitivity for back-to-back pressure case.

Cash-OUT is built on the BOQ mapped to cost-loaded timing; prelims kept as a separate management line and not folded into package spend (user-confirmed for auditor defensibility).

VAT reverse-charged, not modelled (Finnish construction services). Inflation / escalation not modelled (lump sum FIDIC YB). Insurance deductibles not quantified (data gap).

Cost loading total €82,970,863 (verified by summing every numeric value in Schedule Table col M, 133 rows — see workbook Audit — Cost Loading sheet). BOQ total €92,400,000. Gap €9.43M (Appendix A).

Commencement-date conflict (PC RevC 2 March 2026 vs baseline 1 March 2026) is now a live item in the workbook Risk Register as R-16, with the planner assigned to align the baseline. All board documentation uses the PC date as authority.

Activity-to-section mapping is heuristic by activity name keyword; unallocated prelims are pro-rated by classified-cost share.

# Appendix A — BOQ ↔ Cost-Loading Reconciliation

Headline: cost-loading total €82,970,863; BOQ Accepted Contract Amount €92,400,000; gap €9,429,137.

Section-by-section view (all 10 sections; per-section deltas sum exactly to the €9.43M gap):

| BOQ § | Description | Cost Loading € | BOQ € | Diff € |
| --- | --- | --- | --- | --- |
| A | Preliminaries & General Requirements | 2,509,183 | 6,006,000 | +3,496,817 |
| B | Earthworks, Blasting, Piling & Substructure | 9,389,260 | 6,468,000 | -2,921,260 |
| C | Structure — Structural Steel & Precast Concrete | 7,273,037 | 8,778,000 | +1,504,963 |
| D | Envelope — Cladding, Roofing & Louvres | 5,600,177 | 5,544,000 | -56,177 |
| E | Architectural Finishes & Data Hall Containment | 4,203,494 | 4,620,000 | +416,506 |
| F | Mechanical — Chillers, Dry Coolers, CRAH & Pipework | 30,151,082 | 22,176,000 | -7,975,082 |
| G | Electrical — HV/MV, Transformers, UPS & Generators | 10,739,475 | 27,720,000 | +16,980,525 |
| H | ELV, BMS/DCIM, Fire Detection & Suppression | 2,629,753 | 5,082,000 | +2,452,247 |
| I | External Works, Security & Fibre Entry | 2,273,855 | 3,696,000 | +1,422,145 |
| J | Commissioning & Handover (L1-L5) | 8,201,547 | 2,310,000 | -5,891,547 |
|  | TOTAL | 82,970,863 | 92,400,000 | +9,429,137 |

Why the gap exists — the structural story (all 10 sections accounted for):

Section G (Electrical): BOQ higher by €16,980,525. The BOQ carries full equipment supply — transformers, switchgear, 8 × standby generators, 16 × UPS modules, busway. The cost loading carries install-only labour for those items.

Section H (ELV): BOQ higher by €2,452,247. Suppression system hardware + BMS/DCIM hardware supply not fully in cost loading.

Section A (Preliminaries): BOQ higher by €3,496,817. Insurance, performance bond, statutory supervisors, design development & risk allowance in BOQ A but light in cost loading.

Section I (External): BOQ higher by €1,422,145. Full external works scope (security, fibre entry, paving, landscaping) in BOQ vs install-only cost loading.

Section C (Structure): BOQ higher by €1,504,963. Steel and precast supply in BOQ slightly exceeds cost-loading labour.

Section E (Finishes): BOQ higher by €416,506. Finishes and data-hall containment supply in BOQ slightly exceeds cost loading.

Section B (Earthworks): cost loading higher by €2,921,260. Bulk earthworks, blasting, piling — cost loading priced at planner's rates higher than BOQ.

Section D (Envelope): cost loading higher by €56,177. Negligible — cladding/roofing align closely.

Section F (Mechanical): cost loading higher by €7,975,082. Cost-loaded Mech/Mech HVAC/Mech Pipe resource groups carry full install premium; BOQ F is equipment-supply-weighted.

Section J (Commissioning): cost loading higher by €5,891,547. Cost-loaded Commissioning RG carries L1–L5 labour; BOQ J is lighter.

Net residual: €9,429,137. The bigger story is the structural shift — the cost loading is a labour+install view; the BOQ is a supply+install view. The two views complement each other for cash-flow modelling.

FOR THE CASH FLOW:

Cash-IN is built on the BOQ (€92.4M) using the cost-loaded monthly profile scaled by a single factor (BOQ / cost-loading total ≈ 1.1136). The reconciliation is preserved because the per-section BOQ and cost-loading values reconcile at the workbook Reconciliation sheet.

Cash-OUT is built on the BOQ mapped to cost-loaded activity timing (€82.97M of cost-loaded labour/install), with the equipment-supply gap shown implicitly as part of the Advance Procurement line paid against the relevant procurement milestones (LT-01 to LT-15).

Preliminaries (€6.006M BOQ Section A) are shown as a separate management/prelims spend line that is not subject to the 45-day sub payment lag — they are paid monthly in arrears per the cost-loaded timing.

# Appendix B — Sectional Completion & Delay Damages (PDC-SC-001 Rev C)

| Section | Scope | TfC (mo) | Completion date | LD/day (€) |
| --- | --- | --- | --- | --- |
| 1 | DH1 + primary substation + generator compound + shared cooling spine + site access + gatehouse | 14 | 2 May 2027 | 18,000 |
| 2 | DH2 + plant | 16 | 2 July 2027 | 12,000 |
| 3 | DH3 + plant | 19 | 2 October 2027 | 12,000 |
| 4 | DH4 + admin/NOC + external works + landscaping | 22 | 2 January 2028 | 10,000 |

Aggregate LD cap: 10% of contract sum = €9,240,000.

Concurrent delay: apportioned by the Engineer (SP-7); no Cost for concurrent periods.

Sole remedy for delay: Delay Damages only (SP-8).

Taking-Over requires the Finnish occupancy inspection (käyttöönottotarkastus) and the Tenant technical acceptance (Anchor Tenant Technical Annex).

All Section dates key off the Commencement Date of 2 March 2026 (per PC RevC). The baseline schedule currently uses 1 March 2026 — Risk R-16 in the workbook.

# Appendix C — Key Milestones (PDC-MS-001 Rev A)

| Ref | Milestone | Type | Date |
| --- | --- | --- | --- |
| MS-01 | Commencement Date | Contract | 2 Mar 2026 |
| MS-04 | Statutory supervisors approved | Permit | Before works start |
| MS-05 | Blasting permit + pre-condition survey | Permit | Before rock excavation |
| MS-07 | Long-lead HV equipment ordered | Procurement | Month 2 |
| MS-08 | 110 kV outage window applied for | DNO | 16 wks before energisation |
| MS-09 | Earliest firm grid energisation | DNO | 12 Mar 2027 (CRITICAL) |
| MS-10 | Tenant fit-out access to Hall 1 | Tenant | Month 12 (overlaps Section 1) |
| MS-11 | Section 1 L4 integrated systems testing | Commissioning | Month 13 |
| MS-12 | Section 1 L5 24h load-bank test | Commissioning | Month 14 |
| MS-13 | Section 1 occupancy inspection | Authority | Month 14 |
| MS-14 | Section 1 Taking Over | Contract | 2 May 2027 — LD €18k/day |
| MS-15 | Section 2 Taking Over | Contract | 2 July 2027 — LD €12k/day |
| MS-16 | District heating boundary works complete | Offtaker | 31 Aug 2027 |
| MS-17 | Waste-heat 72h witnessed test (heating season only) | Offtaker | Oct–Apr |
| MS-18 | Section 3 Taking Over | Contract | 2 Oct 2027 — LD €12k/day |
| MS-19 | Section 4 Taking Over / whole of Works | Contract | 2 Jan 2028 — LD €10k/day |