## Slide 1
Polaris DC-1 — Aviapolis Data Campus, Vantaa
Period 05 — Monthly Progress Report
Data date: 31 July 2026 · Reporting window: 01–31 July 2026
Issued for PMC / ER record
Sources: PDC-BOQ-001 Rev A · PDC-SCH-001/5/8 Rev0/2 · PDC-MS-001 Rev A · PDC-LT-001 Rev A · PDC-PROG-001/5/8 P05 · PDC-LAB-P05 · PDC-MIN-P05 · PDC-LTR-PMC-011

## Slide 2
Executive summary
Period 05 · 31.07.2026
Section 1 forecast-met; 0 working days float on DH2 chain
• Section 1 forecast completion — 2027-05-02 — met; 0 working days float on DH2 chain
• Critical path — DH1 piling → DH2 piling → DH2 pile caps → DH2 waterproofing; any further loss on GW-1200 directly on completion date
• Days lost this period — 2 cal days on DH2 pile caps; cause 22.07.2026 concrete supply failure at Rudus Vantaa (Kallio's nominated supplier)
• Risk allocation — DH2 chain slip is Kallio supply-chain risk under PDC-SUB-001 Rev0; no Kallio claim lodged; no Employer valuation reserved
• EVM at month-end — SPI 0.98 · CPI 0.86 · SV −EUR 65,681 · CV −EUR 529,413 (driven by Section A prelims cost profile)
• Money position — BAC EUR 92,400,000 · PM EAC held at BAC (no uplift warranted) · formal CPI-projection EAC EUR 107.5m presented as sanity check only
• TP-005 baseline status — Ilmatek Rev2 baseline programme NOT YET ACCEPTED by PMC; P05 position reported against an unaccepted baseline
• Open PM actions — 7 — 1 due 05.08.2026 (DH1 piling % reconciliation); 5 dependent on third parties (DNO, Vantaan Energia, ER instruction)
• Headline risk — 110 kV outage window under review (CD-05) — Employer-side; affects ST-1310 substation precast erection
Polaris DC-1 · Aviapolis Data Campus, Vantaa · Period 05 monthly progress — PMC
2/10

## Slide 3
TP-001 Kallio — substructure
Period 05 · 31.07.2026
Pile log 41/68 = 60%; DH2 chain slip = Kallio supply-chain risk (no claim lodged)
• DH1 piling (GW-1200) — 60% cum (41 of 68 design installed + concreted). ON programme. Kallio claim 64% is time-elapsed — pending A05-01 reconciliation (05.08).
• DH2 pile caps (GW-1300) — Completed 28.07 — 2 cal days late. Cause: 22.07 concrete supply failure at Rudus Vantaa, Kallio's nominated supplier (Kallio P05 N-04). Risk: Kallio (supply chain). No claim lodged in P05.
• DH2 waterproofing (GW-1500) — NOT STARTED at 31.07. Root cause: F-S link from GW-1300 — access only released 29.07 (PDC-LAB-P05). Propagated Kallio risk. Now programmed W/c 03.08.
• Piling rig 2 (Junttan PM20) — Off-hire 13.07–15.07 — hydraulic failure. Kallio plant risk. No EoT claim lodged.
• NW corner (B.04) — 1,620 m³ @ EUR 63.43, BOQ value EUR 102,762.98. PROVISIONAL — Kallio has reserved time and cost (N-05). Awaiting Employer instruction. Piling rate reduced 3.0 → 1.8 piles/day.
• Labour — At planned level (25–26 fitters+welders W30/W31). Not the issue.
• Cost position — No Employer liability reserved. Kallio risk on the 22.07 event. B.04 EUR 102,762.98 — Employer instruction pending (PMC → ER).
Polaris DC-1 · Aviapolis Data Campus, Vantaa · Period 05 monthly progress — PMC
3/10

## Slide 4
TP-005 Ilmatek — mechanical
Period 05 · 31.07.2026
5% on IL-1400 cooling spine; Rev2 baseline NOT YET ACCEPTED
• IL-1400 cooling spine — 5% cum (QS). Sub claim 12% offsite prefabrication DENIED under PDC-SUB-005 Rev1 Cl. 4.7 — payment on completion of work in the Permanent Works, not offsite materials.
• Tender qualification Q7 — Did NOT survive into executed Rev1 subcontract. Contracts module finding.
• Labour — 5 on site W30/W31 vs 11 planned — materially below programme. Ilmatek responsibility. Watching item; Cl. 4.4 recovery schedule request will issue after this report.
• Rev2 baseline programme — NOT YET ACCEPTED by PMC. Programme Compliance review documented 8 high-severity findings (sectional milestones not flagged; IL-1550 commissioning in winter; IL-1200/IL-1260 lead times compressed).
• Reported position — Reported against an unaccepted baseline programme. Acceptance decision will be notified under separate cover. Reported TP-005 sectional completion date 2027-03-31 is provisional.
• Currency adjustment — IL-1400 offsite claim vs QS implies adjustment EUR −132,236 to be applied to IV-005 once valuation runs.
• IL-1200 chillers — Procurement — order placed per PDC-LT-001 LT-01 (need-by 2026-09-15). No on-site progress this period.
Polaris DC-1 · Aviapolis Data Campus, Vantaa · Period 05 monthly progress — PMC
4/10

## Slide 5
TP-008 Lehtinen — external works & security
Period 05 · 31.07.2026
Ahead on access roads; NE car park blocked by R-09 (Employer-side)
• Access roads & parking (I.01) — 40% cum (sub and QS agree). Sub-base complete to main gate. AHEAD of programme — good weather.
• Perimeter fencing (GW-2000 / I.02) — Starts 17.08 per programme. Posts delivered 29.07. ON programme.
• NE car park construction — BLOCKED by temporary parking compound still in use (Risk R-09). Employer-side internal site logistics constraint, owner TL.
• Owning action — Logistics (TL) to commit a relocation date in writing before P06.
• Package size — Section I total EUR 3,696,000 (BoQ I.01–I.09). I.01 alone EUR 877,247.74. Currently 40% on I.01 supports EV c. EUR 350,899.
• Fibre entry (I.06) — EUR 298,842.64 — not yet started; on programme for Q4 2026 mobilisation.
• Stormwater (I.04) — EUR 711,530.09 — design development ongoing; on programme.
Polaris DC-1 · Aviapolis Data Campus, Vantaa · Period 05 monthly progress — PMC
5/10

## Slide 6
Earned Value (month-end)
Period 05 · 31.07.2026
SPI 0.98 / CPI 0.86 — time on plan, cost skewed by Section A prelims profile
PV
EUR 3.30m
Planned value to date
EV
EUR 3.24m
Earned value to date
AC
EUR 3.77m
Actual cost to date
PM EAC
EUR 92.4m
Held at BAC; no uplift
EVM detail
SPI (EV/PV)
0.980
Schedule performance index — on plan
CPI (EV/AC)
0.859
Cost performance index — over (driven by Section A prelims profile)
SV (EV−PV)
−EUR 65,681
Schedule variance — marginal behind
CV (EV−AC)
−EUR 529,413
Cost variance — over budget (structural)
TCPI to BAC
0.989
Cost performance required to hit BAC — feasible
EV this period
EUR 399,326
P05 earned vs P04 EV estimate
Formal EAC
EUR 107.5m
CPI-projection — sanity check only; NOT PM forecast
Basis: Section A prelims straight-line; Section B (B.06 60% QS, B.07 5%); Section F (IL-1400 5% QS); Section I (I.01 40%). Source: PDC-BOQ-001 Rev A · PDC-SCH-001/5/8 Rev0/2 · PDC-LAB-P05 · PDC-PROG-001/5/8 P05.
Polaris DC-1 · Aviapolis Data Campus, Vantaa · Period 05 monthly progress — PMC
6/10

## Slide 7
Critical path slippage
Period 05 · 31.07.2026
DH2 chain — 0 working days float remaining (Kallio supply-chain risk)
Activity
BL finish
Actual / status
Variance
Cause / risk allocation
GW-1200 DH1 piling
2026-08-25
41/68 (60% QS)
0 cal days
On programme
GW-1300 DH2 pile caps
2026-07-26
Completed 28.07
−2 cal days
Kallio risk — 22.07 supplier failure (Rudus Vantaa)
GW-1500 DH2 waterproofing
2026-08-12
Not started
−2 cal days (propagated)
Kallio risk — F-S link from GW-1300; access released 29.07
MS-06 Section 1
2027-05-02
Forecast-met
0
0 working days float on DH2 chain
ST-1310 substation precast
2026-11-25
At risk
Pending 110 kV review
Employer risk — DNO written permission required (CD-05)
Section 1 is intact only because the 2 days of float on the DH2 chain were exactly what the Kallio-risk 22.07 concrete supply failure cost. The next slip — Kallio or Employer — must trigger a FIDIC Cl. 8.3 notification.
Polaris DC-1 · Aviapolis Data Campus, Vantaa · Period 05 monthly progress — PMC
7/10

## Slide 8
Money-proportionate variances & risk allocation
Period 05 · 31.07.2026
No Employer liability reserved on the DH2 chain at month-end
Item
EUR
Status / risk allocation
B.04 NW corner made ground (provisional)
102,762.98
Employer instruction pending (PMC → ER); Kallio reservation N-05
Kallio 22.07 Rudus Vantaa concrete supply failure
—
Kallio risk — no claim lodged in P05; no Employer valuation reserved
IL-1400 offsite prefab claim vs QS
−132,236 (adjustment)
To be applied to IV-005 once Ilmatek valuation runs
Rig 2 (Junttan PM20) 13–15.07
Sub cost (TBC)
Kallio risk — mechanical (hydraulic failure); no EoT claim lodged
110 kV outage window
TBC
Employer risk — PMC / Design; ER letter 30.07.2026
Sections at risk if 110 kV slips
ST-1310 + Section G
Affects TP-002 precast and TP-006 commissioning
R-09 TMP compound blocks NE car park
—
Employer / TL risk — internal site logistics
Risk allocation: the DH2 chain slip this period is Kallio supply-chain risk under PDC-SUB-001 Rev0 — Kallio's nominated concrete supplier Rudus Vantaa failed on 22.07; no Kallio claim has been lodged in P05; no Employer valuation is reserved against it. The EUR 132,236 IL-1400 adjustment is a contractually clean position; tender Q7 did not survive Rev1. The EUR 102,762.98 B.04 reservation is Employer-side and is held for written instruction. The 110 kV outage window is the principal Employer-side risk and is under ER review (CD-05).
Polaris DC-1 · Aviapolis Data Campus, Vantaa · Period 05 monthly progress — PMC
8/10

## Slide 9
4-week look-ahead
Period 05 · 31.07.2026
W/c 03.08 → W/c 24.08.2026
Week
Activity
Owner
W32 (03.08)
DH2 waterproofing start · DH1 piling continue · access roads hardstanding handover · UPS modules procurement (LT-04 order-by 31.07)
Kallio / Lehtinen / PMC
W33 (10.08)
Halls 3-4 pile caps start · A05-01 reconciliation close-out · NW corner written-instruction request to ER
Kallio / PMC → ER
W34 (17.08)
Perimeter fencing start · Ilmatek Cl. 4.4 letter issued
Lehtinen / PMC
W35 (24.08)
TMP compound relocation (R-09) · 110 kV outage window confirmation
TL / Logistics / PMC
Polaris DC-1 · Aviapolis Data Campus, Vantaa · Period 05 monthly progress — PMC
9/10

## Slide 10
Open checks & actions
Period 05 · 31.07.2026
7 actions — 1 firm due 05.08.2026
Ref
Action
Owner
Due
A05-01
Reconcile DH1 piling % with QS site measure (pile log 41/68 = 60%)
PK (Kallio)
2026-08-05
A05-02
DNO exclusion-zone confirmation for ST-1310 precast
PMC / Design
TBC
A05-03
B.04 NW corner remeasure, time consequence
PMC → ER
TBC
A05-04
R-09 TMP compound relocation
TL / Logistics
TBC
A05-05
Ilmatek recovery schedule (PDC-SUB-005 Rev1 Cl. 4.4)
PMC
After report
A05-06
Ilmatek Rev2 baseline programme acceptance decision
PMC
TBC
A05-07
110 kV outage window confirmation with Vantaan Energia
PMC / Design
TBC
Polaris DC-1 · Aviapolis Data Campus, Vantaa · Period 05 monthly progress — PMC
10/10