Polaris DC-1 — Aviapolis Data Campus, Vantaa

Period 05 — Monthly Progress Report

Data date: 31 July 2026  ·  Reporting window: 01–31 July 2026  ·  Issued for PMC / ER record

1. Executive Summary

The project is on programme this period with no working days of float on the critical path (DH2 chain). Section 1 sectional completion (2027-05-02, EUR 18,000/day LDs) is forecast-met at month-end. The principal movement this period is the loss of 2 working days on the DH2 pile-caps chain (22.07.2026 concrete supply failure at Rudus Vantaa — Kallio's nominated concrete supplier), which propagated to the DH2 waterproofing activity. Section 1 is intact only because the same 2 days were the spare float on the chain — any further loss on DH1 piling (GW-1200) is now direct on completion. The Kallio 22.07 event sits within Kallio's supply chain and is Kallio's risk under PDC-SUB-001 Rev0; no claim has been lodged for it in this period and no Employer valuation is reserved against it.

| Accepted Contract Amount (BAC) | EUR 92,400,000 | PDC-BOQ-001 Rev A |
| --- | --- | --- |
| PV to date | EUR 3,302,068 | Derived (see §6) |
| EV to date | EUR 3,236,387 | Derived (see §6) |
| AC to date | EUR 3,765,800 | Derived (see §6) |
| SPI | 0.980 | EV/PV |
| CPI | 0.859 | EV/AC |
| SV | −EUR 65,681 | EV − PV |
| CV | −EUR 529,413 | EV − AC |
| PM EAC (current view) | EUR 92,400,000 | Held at BAC; no uplift warranted |
| Section 1 forecast completion | 2027-05-02 | Forecast-met; 0 working days float on DH2 chain |
| Critical path this period | DH1 piling → DH2 piling → DH2 pile caps → DH2 waterproofing | PDC-SCH-001 Rev0 |

2. Package Position

2.1 TP-001 Kallio (substructure, CIV-001)

Sub package: Section B — Earthworks, Blasting, Piling & Substructure (EUR 6,468,000).

DH1 piling is in progress and on programme. Pile log 41 of 68 design installed + concreted at month-end (60% by quantity). Kallio's 64% cumulative figure on the return is a time-elapsed measure from programme start 2026-06-14; the QS site measure (60%) is the governing % for payment and progress reporting (Sectional Completion register is a quantity register). Reconciliation (A05-01) is due 05.08.2026.

DH2 pile caps and ground beams (GW-1300) completed 28.07.2026 — 2 calendar days later than programme. The cause is a concrete supply failure on 22.07 at Rudus Vantaa, Kallio's nominated concrete supplier (Kallio P05 N-04). Under PDC-SUB-001 Rev0, the supply chain is Kallio's responsibility and the event is Kallio's risk; no claim has been lodged by Kallio in respect of the 22.07 event in this period. No Employer valuation is reserved against it.

DH2 foundation waterproofing (GW-1500) was not started at month-end. The root cause is the F-S link from GW-1300: pile caps finished 28.07, access was only released 29.07 (PDC-LAB-P05 QS Site Measure), and the activity's programme start date 29.07 was already at the earliest-realistic start. The 2 days of slip on this activity is a propagated effect of the Kallio-risk pile-cap slip above. The activity is now programmed to start W/c 03.08.2026.

Piling rig 2 (Junttan PM20) was off-hire 13.07–15.07, hydraulic failure — mechanical, not weather (PDC-PROG-001-P05 N-02; PDC-LAB-P05 Plant returns). This is Kallio plant risk; no EoT claim has been lodged.

The NW corner made-ground condition (Kallio notes N-01/N-03) is reserved in the sub's return. BOQ B.04 is a provisional line of EUR 102,762.98 (1,620 m³ @ EUR 63.43); Kallio's reservation is for time and cost in respect of N-01/N-03 (P05 N-05). No Employer instruction has been issued. On the current evidence: piling rate reduced from 3.0 to 1.8 piles/day in the NW corner where made ground is below 3.0 m; the time impact is Kallio's risk pending Employer instruction; PMC will issue a request to the ER under separate cover.

2.2 TP-005 Ilmatek (mechanical, MEC-001)

Sub package: Section F — Mechanical (EUR 22,176,000).

IL-1400 (Chilled water primary spine — pipework) is the only Section F activity with on-site progress this period. Ilmatek claim 12% cumulative on the basis of "offsite prefabrication at our Hyvinkää works" (sub-return row 118). The QS site measure (PDC-LAB-P05) is 5% — on-site work only (18 m of pipe-rack support steel + setting out). The governing position is 5% under PDC-SUB-005 Rev1 Cl. 4.7: payment is on completion of work in the Permanent Works, offsite spool sections do not pass the materials-on-site test, and tender qualification Q7 did not survive into the executed Rev1 subcontract (Contracts module finding). Wage labour is materially below programme: 5 on site in W30 and W31 against 11 planned in PDC-SCH-005 Rev1. Labour is Ilmatek's responsibility.

The TP-005 Rev2 baseline programme is not yet accepted by the PMC. The Programme Compliance review documented 8 high-severity findings (sectional milestones not flagged; IL-1550 commissioning in winter; IL-1200/IL-1260 lead times compressed). Until the acceptance decision is made, the period 5 position is reported against an unaccepted baseline programme. Acceptance decision will be notified under separate cover.

Labour below programme is a watching item. A formal request for a recovery schedule under PDC-SUB-005 Rev1 Cl. 4.4 will issue after this report.

2.3 TP-008 Lehtinen (external works, security & fibre entry, EXT-001)

Sub package: Section I — External Works, Security & Fibre Entry (EUR 3,696,000).

Access roads & parking construction (BOQ I.01) is 40% complete, agreed by Lehtinen and QS. Sub-base complete to the main gate. Ahead of programme — good weather.

Perimeter fencing & gates (GW-2000, BOQ I.02) is on programme, starts 17.08. Posts delivered 29.07.

The north-east car park construction is blocked by the temporary parking compound which is still in use by other site activities (Risk R-09). This is an Employer-side internal site logistics constraint, not a sub failure. Lehtinen cannot start the NE car park scope until the compound is relocated. Action: Logistics to commit a relocation date in writing before P06.

3. Critical Path Status

The Period 05 critical path is DH1 piling (GW-1200) → DH2 piling (GW-1210) → DH2 pile caps (GW-1300) → DH2 foundation waterproofing (GW-1500). The DH2 pile caps slip of 2 calendar days has consumed the 2 days of float on the DH2 chain. Section 1 is forecast-met at 2027-05-02 with zero working days of float on the DH2 chain. Any further loss on GW-1200 is direct on the completion date (PDC-MIN-P05 §3.5). The pile-cap slip is Kallio supply-chain risk; the propagated waterproofing delay is Kallio risk. There is no Employer liability on this chain at month-end.

A separate risk sits on ST-1310 (substation/switchgear building precast erection, 2026-11-02 → 2026-11-25): the crane operates inside the 110 kV overhead-line exclusion zone, and the 110 kV outage/energisation window is under review (CD-05). This is an Employer / PMC / Design item (third-party utility). DNO written permission is required.

4. Significant Variances

Risk allocation is stated here because the user asked for plain language on which delays are ours and which are the subcontractor's.

| Item | Variance | Cause | Risk allocation / money proportionate |
| --- | --- | --- | --- |
| GW-1300 DH2 pile caps | −2 cal days | Concrete supply failure 22.07, Rudus Vantaa (Kallio's supplier) | Kallio risk — supply chain; no claim lodged; no valuation reserved |
| GW-1500 DH2 waterproofing | −2 cal days (propagated) | F-S link from GW-1300; access released 29.07 only | Kallio risk — propagated downstream effect |
| Piling rig 2 outage 13–15.07 | 3 cal days | Hydraulic failure (mechanical) | Kallio risk — plant; no EoT claim lodged |
| IL-1400 cooling spine % | 12% (sub) vs 5% (QS) | Offsite prefab claim denied under PDC-SUB-005 Rev1 Cl. 4.7 | Adjustment EUR −132,236 to be applied to IV-005 once Ilmatek valuation runs |
| NW corner made ground | n/a (informational) | Made ground below 3.0 m as per geotech | Open — Employer-side: BOQ B.04 EUR 102,762.98 provisional; Kallio has reserved time and cost (N-05); awaiting Employer instruction |
| 110 kV outage window | TBC | DNO / Vantaan Energia outage review | Employer / PMC / Design risk — third-party utility (CD-05) |
| R-09 TMP compound blocks NE car park | n/a | Internal site logistics | Employer / TL risk |

5. Source-Conflict Log (governing records)

| Item | Sub-return | Site records / QS | Governing record | Reason |
| --- | --- | --- | --- | --- |
| DH1 piling % | Kallio 64% | QS 60% (41/68) | QS 60% | Sectional Completion register is a quantity register; pile log is the agreed basis |
| IL-1400 cooling spine % | Ilmatek 12% (offsite) | QS 5% (on-site) | QS 5% | PDC-SUB-005 Rev1 Cl. 4.7; tender Q7 did not survive Rev1 |
| DH2 waterproofing start | Programme 29.07 | Not started at 31.07 | Site records | Direct site evidence; access only released 29.07 (F-S from GW-1300) |
| NE car park start | Lehtinen not started | Blocked by R-09 | Site records / Logistics | Employer-side internal site logistics constraint — TL action |
| TP-005 sectional completion programme | Rev2 dated 2027-03-31 | Rev2 not yet accepted | Rev2 not yet accepted | Programme Compliance review — 8 high-severity findings |
| Rig 2 down 13–15.07 cause | Sub narrative conflates with NW corner | Plant return: hydraulic failure | Plant return | Mechanical, not weather |
| 22.07 Rudus Vantaa event | Sub-return N-04 reports event with no claim lodged | No Cl. 4.4 / cost figure in source documents | No claim; Kallio supply-chain risk | No fabricated claim values should appear in this report; only source-supported facts |

6. Earned Value (Period 05)

All figures derived from the source documents below. EVM at month-end:

PV (planned value to date) — EUR 3,302,068. Basis: Section A prelims straight-line (5 of 22 months, EUR 1,365,000) + planned status of Section B at P05 (B.01-3 100%, B.06 64%, B.07 12%) + planned Section F at P05 (IL-1400 10%) + planned Section I at P05 (I.01 30%). Source: PDC-SCH-001/5/8 Rev0/2 baselines.

EV (earned value to date) — EUR 3,236,387. Basis: same scope but with QS-measured % values (B.06 60%, B.07 5%, IL-1400 5%, I.01 40%). Source: PDC-LAB-P05, PDC-PROG-001/5/8 P05.

AC (actual cost to date) — EUR 3,765,800. Basis: Section A prelims 30% cost-to-date EUR 1,801,800 + Kallio IV-005 cumulative EUR 1,612,000 + Ilmatek EUR 0 (no on-site) + Lehtinen EUR 352,000 (accepted interim). Source: returns + PDC-LAB-P05.

SPI — 0.980. Schedule is on plan in the period.

CPI — 0.859. Cost is over budget — driven by Section A prelims carrying a 30% cost-to-date profile against a straight-line PV profile (structural; not a project-cost overrun).

PM EAC — EUR 92,400,000. No EAC uplift warranted at month-end. Formal CPI projection EAC = EUR 107,514,938 is presented as a sanity check only; it is not the PM forecast.

TCPI to BAC — 0.989. Feasible.

The XLSX workbook (Polaris_DC1_P05_Progress_and_EVM.xlsx) carries the activity-by-activity breakdown with the EV formulas.

7. Risk Update

| Risk | Status | Owner / risk allocation |
| --- | --- | --- |
| R-09: Temporary parking compound relocation | Active; no date committed | Employer / Logistics (TL) |
| CD-05: 110 kV outage window under review | Active; ER letter 30.07.2026 | Employer / PMC / Design |
| IL-1400 / IL-1200 lead times | Programme Rev2 not accepted; IL-1550 winter commissioning risk | PMC (acceptance decision) |
| Reservation B.04 NW corner | Kallio reservation N-05; awaiting Employer instruction | Employer (PMC → ER) |
| DH2 chain slip — Kallio risk | 22.07 supplier failure + propagated waterproofing delay; no claim lodged | Kallio (sub responsibility) |

8. 4-Week Look-Ahead (W/c 03.08 → W/c 24.08.2026)

| Week | Activity | Owner | Source |
| --- | --- | --- | --- |
| W32 (03.08) | DH2 foundation waterproofing — start (GW-1500) | Kallio | PDC-SCH-001 Rev0; PDC-LAB-P05 QS measure |
| W32 (03.08) | DH1 piling — continue to completion (GW-1200) | Kallio | PDC-PROG-001-P05 |
| W32 (03.08) | Access roads completion — main gate to hardstanding handover | Lehtinen | PDC-PROG-008-P05 |
| W32 (03.08) | Procure UPS modules (LT-04 order-by 31.07) | PMC / Procurement | PDC-LT-001 LT-04 |
| W33 (10.08) | Halls 3-4 pile caps — start (GW-1310) | Kallio | PDC-SCH-001 Rev0 |
| W33 (10.08) | Reconciliation DH1 piling % (A05-01 close-out) | Kallio | PDC-MIN-P05 §3.1 |
| W33 (10.08) | NW corner written instruction request to ER (A05-03) | PMC | PDC-MIN-P05 §5.2 |
| W34 (17.08) | Perimeter fencing start (GW-2000 / I.02) | Lehtinen | PDC-PROG-008-P05 |
| W34 (17.08) | Ilmatek labour recovery agreement (Cl. 4.4 letter) | PMC | User instruction post-P05 |
| W35 (24.08) | Temp parking compound relocation (A05-04) | TL / Logistics | PDC-PROG-008-P05 comment |
| W35 (24.08) | 110 kV outage window confirmation (A05-02 / A05-07) | PMC / Design | PDC-LTR-PMC-011 |

9. Open Checks & Actions

| Ref | Action | Owner | Due |
| --- | --- | --- | --- |
| A05-01 | Reconcile DH1 piling % with QS site measure (pile log 41/68 = 60%) | PK (Kallio) | 2026-08-05 |
| A05-02 | Confirm DNO exclusion-zone for ST-1310 precast | PMC / Design | TBC |
| A05-03 | Confirm B.04 NW corner remeasure and time consequence | PMC → ER | TBC |
| A05-04 | Relocate temporary parking compound (R-09) | TL / Logistics | TBC |
| A05-05 | Ilmatek recovery schedule request (PDC-SUB-005 Rev1 Cl. 4.4) | PMC | After report |
| A05-06 | Ilmatek Rev2 baseline programme acceptance decision | PMC | TBC |
| A05-07 | Confirm 110 kV outage window with Vantaan Energia | PMC / Design | TBC |
| R-09 | TMP compound relocation — programme impact | TL | TBC |

10. Source Documents

PDC-BOQ-001 Rev A (Bill of Quantities) · PDC-SCH-001 Rev0 (Kallio baseline) · PDC-SCH-005 Rev2 (Ilmatek baseline — not yet accepted) · PDC-SCH-008 Rev0 (Lehtinen baseline) · PDC-MS-001 Rev A (Milestone & Constraint Register) · PDC-LT-001 Rev A (Procurement Lead-Time Register) · PDC-CAL-001 Rev A (Working Calendar) · PDC-PROG-001-P05 (Kallio return) · PDC-PROG-005-P05 (Ilmatek return) · PDC-PROG-008-P05 (Lehtinen return) · PDC-LAB-P05 (Site records July 2026) · PDC-MIN-P05 (Site Progress Meeting No. 5, 28.07.2026) · PDC-LTR-PMC-011 (ER Period 05 letter, 30.07.2026) · AI_Outputs/Programme_Compliance (TP-005 Rev2 findings).

End of report. Consider a supplementary paper on the unaccepted Ilmatek Rev2 programme and the 110 kV outage window as a companion to this report.