## Cover
Polaris DC-1 — Aviapolis Data Campus, Vantaa
Period 05 Progress Report — Supporting Schedule
Data date: 31 July 2026 · Reporting window: 01–31 July 2026
Issued for Project Manager's review
Source documents (every figure traceable to):
Source | Use
PDC-BOQ-001 Rev A | Bill of Quantities, accepted contract amount EUR 92,400,000
PDC-SCH-001 Rev0 | Kallio (TP-001) baseline programme
PDC-SCH-005 Rev2 | Ilmatek (TP-005) baseline programme — NOT YET ACCEPTED by PMC
PDC-SCH-008 Rev0 | Lehtinen (TP-008) baseline programme
PDC-MS-001 Rev A | Milestone and Constraint Register
PDC-LT-001 Rev A | Procurement Lead-Time Register
PDC-CAL-001 Rev A | Working Calendar (Summer shutdown Wks 28–30)
PDC-PROG-001-P05 | Kallio Period 05 progress return
PDC-PROG-005-P05 | Ilmatek Period 05 progress return
PDC-PROG-008-P05 | Lehtinen Period 05 progress return
PDC-LAB-P05 | Site labour, plant & QS measure, July 2026
PDC-MIN-P05 | Site Progress Meeting No. 5, 28 July 2026
PDC-LTR-PMC-011 | ER Period 05 letter, 30 July 2026
AI_Outputs/Programme_Compliance | Programme Compliance review (TP-005 Rev2 findings)

## Activity Progress
Baseline ID | Sub-Return ID | Activity | Sub-package | BL Start | BL Finish | Actual Start | Actual Finish | Sub % cum | QS % cum | Agreed % | BOQ Value (EUR) | EV (EUR) | Status | Source / note
GW-1200 | — | DH1 piling (Hall 1-2 / Hall 3-4) — pile-log quantum 41/68 | TP-001 | 2026-06-14 | 2026-08-25 | 2026-06-14 |  | 0.64 | 0.6 | 0.6 | 370031.31 |  | ON TRACK — 60% QS (41/68) | PDC-PROG-001-P05 pile log: 41 of 68 design; PDC-LAB-P05 QS concurs. 64% is time-elapsed. BOQ value B.06 (rock-socketed piling, 10 nr). EV = 60% × B.06.
B.04 | — | Excavation of unrecorded made ground, NW corner (provisional) | TP-001 | — | — | — | — | 0 | 0 | 0 | 102762.98 |  | RESERVATION — NOT INSTRUCTED | BOQ B.04 (PDC-BOQ-001 Rev A) — 1,620 m³ @ EUR 63.43. PROVISIONAL — Kallio reservation N-05 (time and cost). NOT yet instructed. Action A05-03 awaiting PMC/ER instruction.
GW-1300 | 55 | DH2 pile caps and ground beams | TP-001 | 2026-07-02 | 2026-07-26 | 2026-07-04 | 2026-07-28 | 1 | 1 | 1 | 630714.6 |  | SLIPPED 2 DAYS — Kallio supply-chain risk | PDC-PROG-001-P05 row 55 'Completed 28.07.2026 (2 days later than programme)'; cause 22.07 concrete supply failure at Rudus Vantaa (Kallio N-04). Kallio supply-chain risk under PDC-SUB-001 Rev0. No claim lodged in P05. EV = 5% of B.07 reflects ongoing Halls 3-4 pile caps not started.
GW-1310 | — | Halls 3-4 pile caps and ground beams | TP-001 | 2026-08-10 | 2026-09-15 | — | — | 0 | 0 | 0 | 0 |  | NOT STARTED — CRITICAL PATH | Linked off GW-1200. Critical path. Start currently scheduled W32.
GW-1500 | 59 | DH2 foundation waterproofing | TP-001 | 2026-07-27 | 2026-08-12 | — | — | 0 | 0 | 0 | 159491.05 |  | NOT STARTED — Kallio risk (propagated) | PDC-LAB-P05 QS Site Measure: 'NOT COMMENCED at 31.07. Access to DH2 caps only released 29.07.' Root cause: F-S link from GW-1300. Propagated Kallio risk. Now programmed W/c 03.08.
GW-1200 | — | Piling rig 2 (Junttan PM20) — mechanical delay | TP-001 | 2026-07-13 | 2026-07-15 | 2026-07-13 | 2026-07-15 | 0 | 0 | 0 | 0 |  | DELAY EVENT — Kallio plant risk | PDC-PROG-001-P05 N-02: 'hydraulic failure. Off hire 13.07–15.07 inclusive. Parts ex Tampere. Rig returned to service 16.07.' PDC-LAB-P05 Plant returns concurs. Kallio plant risk; no EoT claim lodged.
IL-1400 | 118 | Chilled water primary spine — pipework (F.06) | TP-005 | 2026-06-15 | 2026-10-12 | 2026-06-22 |  | 0.12 | 0.05 | 0.05 | 1889088.28 |  | DENIED — 5% QS vs 12% offsite claim | PDC-PROG-005-P05 row 118: 12% offsite prefab; PDC-LAB-P05 QS: 5% on-site. Governing: QS 5%. PDC-SUB-005 Rev1 Cl. 4.7; tender Q7 did not survive Rev1. Rev2 baseline NOT YET ACCEPTED.
IL-1200 | — | Chillers — order and manufacture (F.01) | TP-005 | 2026-04-01 | 2026-08-08 | — | — | 0 | 0 | 0 | 2189947.86 |  | PROCUREMENT — no on-site | Order placed per PDC-LT-001 LT-01 (need-by 2026-09-15). Process tracking not quantified for P05.
IL-1500 | 140 | DH1 Chiller installation & piping | TP-005 | 2026-09-01 | 2026-11-21 | — | — | 0 | 0 | 0 | 0 |  | AWAITING DH1 SLAB | PDC-PROG-005-P05 row 140: 'Not started — awaits DH1 slab'. Logic consistent with Kallio GW-1300 dependency.
I.01 | 200 | Access roads & parking construction (part of I.01) | TP-008 | 2026-07-01 | 2026-09-30 | 2026-07-01 |  | 0.4 | 0.4 | 0.4 | 877247.74 |  | AHEAD OF PROGRAMME | PDC-PROG-008-P05 row 200: 40% sub-base complete to main gate. PDC-LAB-P05 QS: 40% agrees.
GW-2000 | 202 | Perimeter fencing & gates (I.02) | TP-008 | 2026-08-17 | 2026-10-10 | — | — | 0 | 0 | 0 | 472765.84 |  | ON PROGRAMME | Starts 17.08 per programme. Posts delivered 29.07. On programme.
I.01 | — | NE car park construction (part of I.01) | TP-008 | — | — | — | — | 0 | 0 | 0 | 0 |  | BLOCKED — R-09 TMP relocation (Employer risk) | Blocked by temporary parking compound still in use. Employer-side internal site logistics. Owner: Logistics (TL). No date committed.
ST-1310 | — | Substation/switchgear building — precast erection | TP-002 | 2026-11-02 | 2026-11-25 | — | — | 0 | 0 | 0 | 0 |  | AT RISK — Employer risk (110 kV review) | Crane operates within 110 kV overhead-line exclusion zone — DNO written permission required. 110 kV outage window under review (CD-05). Owner: PMC / Design.
MS-06 | — | Section 1 — Sectional Completion (Hall 1-2 ops-ready) | TP — main | 2027-05-02 | 2027-05-02 | — | — | 0 | 0 | 0 | 0 |  | FORECAST-MET — 0 days float on DH2 chain | PDC-SC-001 / PDC-MS-001. Contractual date 2027-05-02. LDs EUR 18,000/day. Forecast-met at month-end. 0 working days float. Any further loss on GW-1200 is direct on completion date.
TOTALS — Earned Value | [12 empty] | EV % of this report's baseline-scope activities

## EVM Summary
EARNED VALUE MANAGEMENT — Period 05 (Data date 31.07.2026)
Metric | Value (EUR) | Basis / source
Budget at Completion (BAC) | 92400000 | PDC-BOQ-001 Rev A: Accepted Contract Amount (Summary sheet).
Planned Value to date (PV) | 3302068 | Derived: Section A prelims straight-line (5/22 months) + planned Section B (B.01-3 100%, B.06 64%, B.07 12%) + Section F (IL-1400 10%) + Section I (I.01 30%).
Earned Value to date (EV) | 3236387 | Derived: Section A prelims (5/22 months) + Section B (B.01-3 100%, B.06 60% [QS] + B.07 5%) + Section F (IL-1400 5% [QS]) + Section I (I.01 40%).
Actual Cost to date (AC) | 3765800 | Section A prelims 30% cost-to-date EUR 1,801,800 + Kallio IV-005 cumulative EUR 1,612,000 + Ilmatek EUR 0 + Lehtinen EUR 352,000 (accepted interim).
Schedule Variance (SV = EV−PV) | -65681 | Negative — programme is EUR 65,681 behind plan at month-end.
Cost Variance (CV = EV−AC) | -529413 | Negative — programme is EUR 529,413 over cost budget at month-end. Skewed by Section A prelims cost-to-date profile.
SPI (EV/PV) | 0.98 | Schedule performance index 0.98 — on plan this period.
CPI (EV/AC) | 0.859 | Cost performance index 0.86 — over (driven by Section A prelims profile, not project overrun).
EAC (formal = AC + (BAC−EV)/CPI) | 107514938 | Straight-line CPI projection. NOT a PM judgement.
VAC (formal = BAC − formal EAC) | -15114938 | Negative — assumes CPI persists for full project.
PM manual EAC (current view) | 92400000 | PM judgement: PM EAC held at BAC. No uplift warranted. CPI driver is structural.
VAC (BAC − PM EAC) | 0 | Per PM manual EAC.
EV earned this period (P05) | 399326 | Delta vs P04 EV estimate.
TCPI to BAC = (BAC−EV)/(BAC−AC) | 0.989 | Cost performance required to hit BAC: 0.989 — feasible.

## Critical Path
Baseline ID | Activity | BL Start | BL Finish | Actual / Status | Variance (cal days) | Cause / risk allocation
GW-1200 | DH1 piling | 2026-06-14 | 2026-08-25 | In progress, 41/68 (60% QS) | 0 cal days loss | On programme at month-end. 41 of 68 design installed + concreted. Pile log verified by QS.
GW-1300 | DH2 pile caps and ground beams | 2026-07-02 | 2026-07-26 | Completed 28.07 | −2 cal days | Concrete supply failure 22.07, Rudus Vantaa (Kallio's nominated supplier). Kallio supply-chain risk under PDC-SUB-001 Rev0. No claim lodged in P05.
GW-1500 | DH2 foundation waterproofing | 2026-07-27 | 2026-08-12 | Not started at 31.07 | −2 cal days (propagated) | Root cause: F-S link from GW-1300. Access only released 29.07. Propagated Kallio risk. Now programmed W/c 03.08.
MS-06 | Section 1 Sectional Completion | 2027-05-02 | 2027-05-02 | Forecast-met | 0 cal days | 0 working days float on DH2 chain. Any further loss on GW-1200 is direct on completion date.
ST-1310 | Substation precast erection | 2026-11-02 | 2026-11-25 | At risk | Pending 110 kV review | 110 kV outage window under review (CD-05). Employer / PMC / Design risk. DNO written permission required.

## Conflict Log
# | Item | Sub-return | Site records / QS | Governing record | Reason
1 | DH1 piling % cum | Kallio 64% | QS 60% (41/68) | QS 60% | QS measure uses installed-pile count against the 68-pile DH1 design scope (PDC-LAB-P05). Kallio's 64% is time-elapsed % from programme start 2026-06-14. Sectional Completion register is a quantity register. Reconciliation A05-01 due 05.08.
2 | IL-1400 cooling spine % cum | Ilmatek 12% (offsite prefab) | QS 5% (on-site) | QS 5% | PDC-SUB-005 Rev1 Cl. 4.7 pays on completion of work in the Permanent Works. Offsite spool sections do not pass materials-on-site. Tender qualification Q7 did not survive into Rev1 (Contracts module finding).
3 | DH2 waterproofing start | Programme 29.07 | Not started at 31.07 | Site records | PDC-LAB-P05 QS Site Measure: 'NOT COMMENCED at 31.07. Access to DH2 caps only released 29.07.' — root cause is F-S link from GW-1300, not weather or storm.
4 | NE car park construction start | Lehtinen not started | Blocked by R-09 compound | Site records / Logistics | Employer-side internal site logistics constraint — temporary parking compound relocation. Not a sub failure. Logistics to commit a relocation date in writing before P06.
5 | TP-005 sectional completion programme | Rev2 dated 2027-03-31 | Rev2 not yet accepted by PMC | Rev2 not yet accepted | Programme Compliance review documented 8 high-severity findings against PDC-SCH-005 Rev2. Reported position is against an unaccepted baseline programme.
6 | Piling rig 2 down 13–15.07 cause | Kallio N-04 narrative conflates with NW corner | Plant return: hydraulic failure | Plant return | PDC-PROG-001-P05 N-02 and PDC-LAB-P05 Plant Returns both record: 'hydraulic failure. Parts ex Tampere. Rig returned to service 16.07.' Cause = mechanical, not weather.
7 | 22.07 Rudus Vantaa concrete supply failure | Kallio N-04: event noted; NO claim lodged; NO Cl. 4.4 reference | No alternative record | Sub-return N-04 — no Employer liability | Full-text search of the project folder confirms no EUR figure or Cl. 4.4 instrument for the 22.07 event exists in any document. Under PDC-SUB-001 Rev0 the supply chain is Kallio's responsibility. No Employer valuation is reserved against the 22.07 event.

## Open Checks
Ref | Open check | Owner | Due | Source / context
A05-01 | Reconcile DH1 piling % with QS site measure (pile log 41/68 = 60%) | PK (Kallio) | 2026-08-05 | PDC-MIN-P05 §3.1 / §4. Pile log 41/68 acknowledged by both parties; sub's 64% is time-elapsed.
A05-02 | DNO exclusion-zone confirmation for ST-1310 precast | PMC / Design | TBC | PDC-LTR-PMC-011 CD-05: 110 kV outage review; PDC-SCH-005 Rev2 IL-1550 commissioning risk.
A05-03 | Confirm B.04 NW corner remeasure and time consequence | PMC → ER | TBC | Kallio reservation N-01/N-03/N-05. PDC-BOQ-001 B.04 EUR 102,762.98. NOT yet instructed.
A05-04 | Relocation of temporary parking compound (R-09) | TL / Logistics | TBC | PDC-PROG-008-P05 comment. Blocks NE car park construction. Employer-side risk.
A05-05 | Ilmatek recovery schedule request under PDC-SUB-005 Rev1 Cl. 4.4 | PMC | After report | Held at user's instruction. Labour 5 vs 11 planned W30/W31.
A05-06 | Ilmatek Rev2 baseline programme acceptance decision | PMC | TBC | Programme Compliance review complete (8 high-severity findings). Decision required before P06 EAC against TP-005.
A05-07 | Confirm 110 kV outage window with Vantaan Energia | PMC / Design | TBC | PDC-LTR-PMC-011 CD-05. 16 weeks' notice required per PDC-CAL-001. Affects ST-1310 + Section G.
R-09 | TMP compound relocation — programme impact | TL | TBC | Logged in PDC Risk Register. No quantified impact on programme yet.