## Progress
ILMATEK LVI OY — MONTHLY PROGRESS RETURN
Polaris DC-1 · TP-005 Mechanical · Period 05 · data date 31.07.2026 · programme ref PDC-SCH-005 Rev1
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Prev cum % | This period % | Cum % at 31.07 | Basis of claim
118 | Cooling Spine — Pipework & Distribution | 0 | 12 | 12 | Site mobilisation, setting out, and offsite prefabrication of spool sections at our Hyvinkää works
140 | DH1 — Chiller Installation & Piping | 0 | 0 | 0 | Not started — awaits DH1 slab
Offsite prefabrication is claimed as progress in accordance with our tender qualification Q7.
Materials on site: none this period. Materials offsite (spools, uninstalled): EUR 184,000.

## Resources
LABOUR AND SUPERVISION — TP-005
Period 05 · weekly average on Polaris DC-1 site
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Week | W/c | Pipefitters | Welders | Supervision | Total on site | Planned (Rev1)
W27 | 2026-06-29 | 0 | 0 | 1 | 1 | 6
W28 | 2026-07-06 | 0 | 0 | 1 | 1 | 8
W29 | 2026-07-13 | 2 | 0 | 1 | 3 | 11
W30 | 2026-07-20 | 3 | 1 | 1 | 5 | 11
W31 | 2026-07-27 | 3 | 1 | 1 | 5 | 11