## Progress Summary
KALLIO MAANRAKENNUS OY — MONTHLY PROGRESS RETURN
Polaris DC-1 · TP-001 Earthworks, Blasting, Piling & Substructure · Period 05 · data date 31.07.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Prev cum % | This period % | Cum % at 31.07 | Status | Comment
42 | Trench Excavation — Site Services | 55 | 45 | 100 | Complete | Completed 05.07.2026
44 | Cooling Spine Pipe Rack Fnds | 20 | 80 | 100 | Complete | Completed 07.07.2026
103 | Gatehouse Construction | 25 | 75 | 100 | Complete | Completed 21.07.2026
104 | Shared Infra — UG Services & Ducts | 60 | 40 | 100 | Complete | Completed 26.07.2026
55 | DH2 Pile Caps & Ground Beams | 40 | 60 | 100 | Complete | Completed 28.07.2026 (2 days later than programme)
101 | Gen Compound Civil & Enclosure | 35 | 65 | 100 | Complete | Completed 30.07.2026
100 | Substation Building Construction | 30 | 50 | 80 | In progress | Blockwork complete, roof deck week 32
50 | DH1 — Rock-Socketed Bored Piles | 30 | 34 | 64 | In progress | Rock harder than anticipated NW corner; rig 2 down 13–15.07
51 | DH2 — Rock-Socketed Bored Piles | 0 | 38 | 38 | In progress | Started 05.07 per programme
52 | DH3 — Rock-Socketed Bored Piles | 0 | 22 | 22 | In progress | Ahead of programme
56 | DH3 Pile Caps & Ground Beams | 0 | 35 | 35 | In progress | Following DH3 piling

## DH1 Pile Log
DH1 — ROCK-SOCKETED BORED PILE INSTALLATION LOG
Design: 68 nr piles · 900 mm dia · rock socket min 1.5 m · as-built record to 31.07.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Pile ref | Date installed | Depth (m) | Socket (m) | Concrete (m3) | Remarks
P1-001 | 2026-06-14 | 14.6 | 1.8 | 9.7
P1-002 | 2026-06-14 | 15.0 | 2.1 | 10.3
P1-003 | 2026-06-15 | 15.4 | 2.4 | 10.9
P1-004 | 2026-06-16 | 15.8 | 1.5 | 11.5
P1-005 | 2026-06-17 | 16.2 | 1.8 | 9.1
P1-006 | 2026-06-17 | 16.6 | 2.1 | 9.7
P1-007 | 2026-06-19 | 14.2 | 2.4 | 10.3
P1-008 | 2026-06-19 | 14.6 | 1.5 | 10.9
P1-009 | 2026-06-20 | 15.0 | 1.8 | 11.5
P1-010 | 2026-06-21 | 15.4 | 2.1 | 9.1
P1-011 | 2026-06-22 | 15.8 | 2.4 | 9.7
P1-012 | 2026-06-22 | 16.2 | 1.5 | 10.3
P1-013 | 2026-06-23 | 16.6 | 1.8 | 10.9
P1-014 | 2026-06-24 | 14.2 | 2.1 | 11.5
P1-015 | 2026-06-24 | 14.6 | 2.4 | 9.1
P1-016 | 2026-06-26 | 15.0 | 1.5 | 9.7
P1-017 | 2026-06-26 | 15.4 | 1.8 | 10.3
P1-018 | 2026-06-27 | 15.8 | 2.1 | 10.9
P1-019 | 2026-06-28 | 16.2 | 2.4 | 11.5
P1-020 | 2026-06-29 | 16.6 | 1.5 | 9.1
P1-021 | 2026-06-29 | 14.2 | 1.8 | 9.7
P1-022 | 2026-07-01 | 14.6 | 2.1 | 10.3
P1-023 | 2026-07-01 | 15.0 | 2.4 | 10.9
P1-024 | 2026-07-01 | 15.4 | 1.5 | 11.5
P1-025 | 2026-07-03 | 15.8 | 1.8 | 9.1
P1-026 | 2026-07-03 | 16.2 | 2.1 | 9.7
P1-027 | 2026-07-04 | 16.6 | 2.4 | 10.3
P1-028 | 2026-07-05 | 14.2 | 1.5 | 10.9
P1-029 | 2026-07-06 | 14.6 | 1.8 | 11.5
P1-030 | 2026-07-06 | 15.0 | 2.1 | 9.1 | NW corner — obstruction encountered, reamed
P1-031 | 2026-07-08 | 15.4 | 2.4 | 9.7 | NW corner — obstruction encountered, reamed
P1-032 | 2026-07-08 | 15.8 | 1.5 | 10.3 | NW corner — obstruction encountered, reamed
P1-033 | 2026-07-08 | 16.2 | 1.8 | 10.9 | NW corner — obstruction encountered, reamed
P1-034 | 2026-07-10 | 16.6 | 2.1 | 11.5 | NW corner — obstruction encountered, reamed
P1-035 | 2026-07-10 | 14.2 | 2.4 | 9.1 | NW corner — obstruction encountered, reamed
P1-036 | 2026-07-11 | 14.6 | 1.5 | 9.7 | NW corner — obstruction encountered, reamed
P1-037 | 2026-07-12 | 15.0 | 1.8 | 10.3 | NW corner — obstruction encountered, reamed
P1-038 | 2026-07-13 | 15.4 | 2.1 | 10.9 | NW corner — obstruction encountered, reamed
P1-039 | 2026-07-13 | 15.8 | 2.4 | 11.5 | NW corner — obstruction encountered, reamed
P1-040 | 2026-07-15 | 16.2 | 1.5 | 9.1 | NW corner — obstruction encountered, reamed
P1-041 | 2026-07-15 | 16.6 | 1.8 | 9.7 | NW corner — obstruction encountered, reamed
TOTAL INSTALLED | 41 |  |  |  | of 68 nr design

## Notes and Delays
NOTES, DELAYS AND MATTERS FOR THE MAIN CONTRACTOR
Period 05 · July 2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | Date | Matter
N-01 | 2026-07-09 | NW corner of DH1 pile grid: material encountered below 3.0 m is not the glacial till shown on PDC-SS-001. Appears to be made ground with concrete and brick fragments. Reaming required, progress rate reduced from 3.0 to 1.8 piles/day in that zone.
N-02 | 2026-07-13 | Piling rig 2 (Junttan PM20) hydraulic failure. Off hire 13.07–15.07 inclusive. Parts ex Tampere. Rig returned to service 16.07.
N-03 | 2026-07-16 | Formal request for Engineer instruction re NW corner material. We consider this falls under BOQ item B.04 (excavation of unrecorded made ground, provisional). Awaiting instruction — see our letter PDC-LTR-001-014.
N-04 | 2026-07-28 | DH2 pile caps completed 28.07 against programme 26.07. Two days lost to concrete delivery on 22.07 (supplier plant breakdown, Rudus Vantaa).
N-05 | 2026-07-30 | We reserve our position on time and cost in respect of N-01 and N-03 pending the Engineer instruction.