## Progress
MAANRAKENNUS LEHTINEN OY — MONTHLY PROGRESS RETURN
Polaris DC-1 · TP-008 External Works & Security · Period 05 · data date 31.07.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Prev cum % | This period % | Cum % at 31.07 | Comment
200 | Access Roads & Parking Construction | 0 | 40 | 40 | Sub-base complete to main gate. Ahead of programme — good weather.
202 | Perimeter Fencing & Gates | 0 | 0 | 0 | Starts 17.08 per programme. Posts delivered to site 29.07.
Note: temporary parking compound remains in use by others. Car park construction to the NE cannot
commence until the temporary compound is relocated — see risk R-09.