## Labour Returns
SITE LABOUR RETURNS — GATE HEADCOUNT
Polaris DC-1 · Period 05 · recorded at turnstile, daily average per week · main contractor record
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Week | W/c | TP-001 Kallio | TP-005 Ilmatek | TP-008 Lehtinen | MC staff | Total
W27 | 2026-06-29 | 24 | 1 | 0 | 9 | 34
W28 | 2026-07-06 | 26 | 1 | 6 | 9 | 42
W29 | 2026-07-13 | 21 | 3 | 8 | 9 | 41
W30 | 2026-07-20 | 25 | 4 | 8 | 10 | 47
W31 | 2026-07-27 | 26 | 4 | 9 | 10 | 49

## Plant Returns
PLANT ON SITE — WEEKLY
Polaris DC-1 · Period 05
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Item | W27 | W28 | W29 | W30 | W31 | Remarks
Piling rig — Junttan PM20 (rig 1) | 1 | 1 | 1 | 1 | 1
Piling rig — Junttan PM20 (rig 2) | 1 | 1 | 0 | 1 | 1 | Off hire 13.07–15.07, hydraulic failure
Crawler crane 80 t | 1 | 1 | 1 | 1 | 1
Excavator 25 t | 2 | 2 | 2 | 2 | 2
Concrete pump | 0 | 1 | 1 | 1 | 1
Welding set (TP-005) | 0 | 0 | 0 | 1 | 1 | First TP-005 plant on site W30

## QS Site Measure
QUANTITY SURVEYOR — INDEPENDENT SITE MEASURE AT 31.07.2026
Measured on site 30–31.07.2026 by M. Nieminen MRICS. This measure governs for valuation.
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Measured cum % | Basis of measure
50 | DH1 — Rock-Socketed Bored Piles | 60 | 41 of 68 piles installed and concreted (pile log verified against as-built survey)
51 | DH2 — Rock-Socketed Bored Piles | 38 | 26 of 68 piles installed
52 | DH3 — Rock-Socketed Bored Piles | 22 | 15 of 68 piles installed
56 | DH3 Pile Caps & Ground Beams | 35 | Reinforcement fixed to 5 of 14 caps, 2 poured
100 | Substation Building Construction | 80 | Blockwork complete, roof deck not commenced
200 | Access Roads & Parking Construction | 40 | Sub-base 620 m of 1,550 m
59 | DH2 Foundation Waterproofing | 0 | NOT COMMENCED at 31.07. Access to DH2 caps only released 29.07.
118 | Cooling Spine — Pipework & Distribution | 5 | Setting out and 18 m of pipe rack support steel only. No pipework installed on site.