## Slide 1
Polaris DC-1
Period 06 Board Update - Rev1
Period 06 - August 2026 - Data date 31 August 2026
Issued 09 September 2026 - PDC-PR-006 Rev1 (supersedes Rev0)
Synthetic demonstration data - not a real project

## Slide 2
Executive summary
Three P05 watch items crystallised in P06. The 110 kV to Section 1 dates do not fit.
What happened
- 110 kV grid energisation slipped to 24.04.2027 (was 12.03.2027). 43 calendar days. (PDC-LTR-PMC-014, 28.08.2026)
- DH1 piling now at 85% (58/68). Activity 50 forecast 11.09.2026 - 17 cd slip, float nil. (PDC-MIN-P06 section 3.2)
- DH2 waterproofing: bay-level physical dispute (W1/W2 complete, W3 coat 1, W4 not started). No BOQ-derived quantum.
- NW corner made-ground instruction issued (PDC-EI-004). EUR 138,400 incurred. No rate agreed; Kallio cost submission in preparation.
- LT-04 UPS procurement milestone closed on time (28.07.2026). Float preserved.
- R-09 parking compound raised in three consecutive returns - blocker on 5% of Act 200.
Headline numbers
AC P06 cumulative
EUR 5,559,300
PDC-CVR-P06
Incurred in period
EUR 1,789,300
PDC-CVR-P06
BAC (P05 baseline)
EUR 92,400,000
P05 workbook
P06 SPI / CPI (indicative)
1.03 / 0.94
derived; flagged
110 kV date
24.04.2027
PDC-LTR-PMC-014
Section 1 Taking Over
02.05.2027
PDC-MS-001 MS-14
Calendar gap
8 days (~ 6 wd)
does NOT fit
Delay damages if missed
EUR 18,000/day
PDC-MS-001 MS-14
Sources: PDC-CVR-P06 - PDC-LTR-PMC-014 - PDC-MIN-P06 section 3.2 - PDC-EI-004 - PDC-MS-001
Polaris DC-1 · P06 · 2 of 10

## Slide 3
P06 cost ledger - Actual Cost incurred to date
Source: PDC-CVR-P06. Cost ledger only - no contractual EV extract in P06 source set.
Cost code | Description | P06 cumulative (EUR) | % of total
C-1000 | Preliminaries | 848,500 | 15.3%
C-1100 | TP-001 Earthworks, blasting, piling | 2,091,000 | 37.6%
C-1140 | of which: NW zone (PDC-EI-004) | 138,400 | -
C-1200 | TP-001 Substructure | 603,500 | 10.9%
C-1300 | TP-005 Mechanical cooling spine | 508,700 | 9.2%
C-1400 | TP-006 Electrical HV enabling | 275,500 | 5.0%
C-1500 | TP-008 External works | 695,200 | 12.5%
C-1900 | Design, statutory, prof fees | 398,500 | 7.2%
TOTAL | All cost codes | 5,559,300 | 100%
MEMO | P05 cumulative AC | 3,770,000 | -
MEMO | Incurred in P06 | 1,789,300 | -
Reading
AC incurred to date EUR 5,559,300 - up EUR 1,789,300 in the period. Largest cost code is C-1100 TP-001 Earthworks, blasting & piling (37.6% of total). The NW corner instruction (PDC-EI-004) has incurred EUR 138,400 within C-1100 (C-1140); the BOQ provisional B.04 is EUR 102,762.98 and NO rate has been agreed (PDC-MIN-P06 section 6; PDC-PROG-001-P06 N-09).
Source: PDC-CVR-P06_Cost_Value_Reconciliation_to_31Aug2026.xlsx
Polaris DC-1 · P06 · 3 of 10

## Slide 4
EVM - P05 baseline and P06 indicative derivation
P06 PV / EV / SPI / CPI / EAC / VAC are INDICATIVE - derived from governed physical % x BOQ line value.
Metric | P05 (31.07.2026) | P06 (31.08.2026) | Source / method
BAC | EUR 92,400,000 | EUR 92,400,000 | P05 workbook; PDC-BOQ-001 Rev A
PV (cumulative) | EUR 3,302,068 | EUR 5,082,000 | P05 workbook (P05 PV); P06 PV = baseline profile at 31.08
EV (cumulative, governed) | EUR 3,236,387 | INDICATIVE: 5,247,000 | P05 actual. P06 derived from Sections B/F/I x BOQ + 40% on prelims/design/HV
AC (cumulative, incurred) | EUR 3,770,000 | EUR 5,559,300 | PDC-CVR-P06
SPI = EV / PV | 0.98 | INDICATIVE: 1.03 | Derived from P06 indicative EV and P06 PV
CPI = EV / AC | 0.86 | INDICATIVE: 0.94 | Derived from P06 indicative EV and P06 AC
EAC | EUR 92,400,000 (PM manual) | INDICATIVE: 97,900,000 | P06 indicative = BAC / CPI
VAC (BAC - EAC) | 0 | INDICATIVE: -5,500,000 | Derived
Why indicative
P05 baseline figures (BAC, PV, EV, SPI, CPI, EAC) are actual from the P05 workbook. P06 figures are an indicative derivation - physical % x BOQ line value - NOT a contractual EV extract. The P06 SPI will diverge once the 110 kV slip is rebaselined into Section 1 commissioning (see slide 6). The P06 CPI of 0.94 means AC is running ~6% above physical progress; the indicative EAC of EUR 97.9m is ~EUR 5.5m above BAC.
Sources: P05 workbook - PDC-CVR-P06 - PDC-BOQ-001 Rev A - PDC-LAB-P06
Polaris DC-1 · P06 · 4 of 10

## Slide 5
S-curve - cumulative PV / AC / EV (EUR)
Baseline PV anchored to P05 PV at 31.07.2026. ACTUAL AC and EV where sourced; indicative where derived.
Chart: Cumulative EUR - PV baseline vs AC actual vs EV
| Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27
PV (baseline) | 462000 | 924000 | 1663200 | 2402400 | 3326400 | 5082000 | 7392000 | 10164000 | 13860000 | 20328000 | 29568000 | 41580000 | 57288000 | 75768000 | 92400000
AC (actual) | 250000 | 550000 | 900000 | 1600000 | 3770000 | 5559300
EV (actual / indicative) | 200000 | 480000 | 820000 | 1400000 | 3236387 | 5246973
Reading
PV (baseline). Anchored to P05 PV EUR 3,302,068 at 31.07 (P05 workbook) and reaching BAC EUR 92,400,000 at end May-27. Earlier months estimated from P05 prelims narrative. AC (actual). P05 cum EUR 3,770,000 and P06 cum EUR 5,559,300 (PDC-CVR-P06). AC running ~9% ahead of PV at month 6 (EUR 5,559k vs EUR 5,082k). EV (actual / indicative). P05 cum EUR 3,236,387 (P05 workbook). P06 cum EUR 5,247,000 (indicative - derived). EV ~ PV at month 6 (SPI 1.03 indicative). What it tells you. Running ~on plan in physical terms (SPI ~ 1) but ~6% over cost (CPI 0.94). The 110 kV slip will pull PV down from Q2 2027 once Section 1 commissioning rebaselines.
Sources: PDC-CVR-P06 (AC) - P05 workbook (PV Jul-26, EV Jul-26) - PDC-LAB-P06 - PDC-BOQ-001 Rev A (EV derivation)
Polaris DC-1 · P06 · 5 of 10

## Slide 6
110 kV vs Section 1 - the dates do not fit
8 calendar days between 110 kV energisation and Section 1 Taking Over is insufficient for the L4/L5 commissioning sequence.
Event / milestone | Date | Source
110 kV grid energisation (revised, firm) | 24.04.2027 | PDC-LTR-PMC-014 section 1
Section 1 L4 integrated systems testing (requires energisation) | Month 14 | PDC-MS-001 MS-11
Section 1 L5 24 h load-bank test | Month 14 | PDC-MS-001 MS-12
Section 1 occupancy inspection | Month 14 | PDC-MS-001 MS-13
Section 1 Taking Over (contractual) | 02.05.2027 | PDC-MS-001 MS-14; PDC-SC-001
Delay damages (Section 1) | EUR 18,000/day from 03.05.2027 | PDC-MS-001 MS-14
Calendar gap 110 kV to Section 1 Taking Over | 8 cd (~ 6 wd) | Derived
What has to happen between 24.04 and 02.05
1. L1-L3 commissioning of mechanical, electrical, BMS, fire/life-safety systems. 2. L4 integrated systems testing - the whole-building integration test, requires 110 kV energisation. 3. L5 24 h load-bank test - requires integrated systems operational; runs 24 h continuous plus setup/monitoring. 4. Occupancy inspection - fire, building control, employer's snagging. 5. Taking Over - handover certificate issued. 6 wd is not enough for steps 1-5 at this scale.
Conclusion
Section 1 Taking Over on 02.05.2027 cannot be achieved from the firm 110 kV date of 24.04.2027. Delay damages EUR 18,000/day (PDC-MS-001 MS-14) will accrue from 03.05.2027. The contractor is required to advise the consequence within 14 days (PDC-LTR-PMC-014 section 2 - response due 12.09.2026). P07 action: reissue PDC-SCH-001 and PDC-MS-001 to reflect the 110 kV slip, and lodge the EOT notification.
Sources: PDC-LTR-PMC-014 - PDC-MS-001 Rev A - PDC-SC-001
Polaris DC-1 · P06 · 6 of 10

## Slide 7
Progress by package - sub vs QS site vs governed
Where sub and QS disagree, QS site measure governs (main contract: FIDIC YB Sub-Cl. 14.3 + PDC-PC-001 Rev C).
Activity | P05 cum | P06 sub | P06 QS | Governed | Agree?
Activity 50 - DH1 piling (58/68 design) | 60% | 88% | 85% | 85% | No
Activity 53 - DH2 pile caps & ground beams | 100% | 100% | 100% | 100% | Yes
Activity 56 - Substructure concrete works | 8% | 22% | 22% | 22% | Yes
Activity 59 - DH2 foundation waterproofing | 0% | 100% | 55% | 55% | No
Activity 60 - Halls 3-4 pile caps & ground beams | 0% | 0% | 0% | 0% | Yes
IL-1400 - Cooling Spine pipework | 5% | 26% | 26% | 26% | Yes
IL-1500 - DH1 chiller installation & piping | 0% | 0% | 0% | 0% | Yes
I.01 - Access roads (main gate & west apron) | 40% | 95% | 90% | 90% | No
I.02 - Perimeter fencing & gates | 0% | 35% | 35% | 35% | Yes
I.03 - Landscaping & soft works | 0% | 10% | 10% | 10% | Yes
Where sub and QS disagree
Activity 50 - DH1 piling. Kallio 88% (58/68); QS pile log 85% (PDC-MIN-P06 section 3.2). 3% gap is rounding, not substantive. Real issue: forecast completion 11.09.2026 - 17 cd slip, float nil. R-16 (new). Activity 59 - DH2 waterproofing. Kallio 100% vs QS 55%. Physical status: W1+W2 complete, W3 coat 1, W4 not commenced. No BOQ-derived monetary quantum. Open item A06-02 from PDC-MIN-P06 (due 02.09.2026).
I.01 - Access roads. Lehtinen 95% vs QS 90%. QS site measure governs; sub's 95% includes NE car park blocked by temporary parking compound (R-09). Note on the basis of valuation. There is no Kallio subcontract in the project files - the Kallio package is at tender (PDC-BID-TP-001-1). Valuation is under the main contract (FIDIC YB Sub-Cl. 14.3 + PDC-PC-001 Rev C), not against any subcontract cl. 6.2.
Sources: PDC-PROG-001-P06 - PDC-PROG-005-P06 - PDC-PROG-008-P06 - PDC-LAB-P06 - PDC-MIN-P06
Polaris DC-1 · P06 · 7 of 10

## Slide 8
Risk register - movement in P06
P05 watch items where the picture has changed; R-16 (DH1 piling slip) is new.
Ref | Risk | P05 status | P06 status | Owner
R-04 | NW corner made-ground (DH1 pile grid) | Open - Engineer to instruct W32 | Closed - PDC-EI-004 issued 05.08; EUR 138,400 incurred. No rate agreed. | ER / Kallio
R-09 | Temporary parking compound relocation | Open - raised in two returns | Open - raised in three returns; blocker on Act 200 | Main Contractor
R-12 | 110 kV grid energisation date | Open - revised date expected by end of August | Open - revised date confirmed 24.04.2027; Section 1 02.05.2027 NOT achievable | ER / Vantaan Energia
R-15 | DH2 waterproofing disagreement | Open - measurement note | Open - physical bay-level dispute; no BOQ-derived quantum; A06-02 | Main Contractor / Kallio
R-16 | DH1 piling slip on Activity 50 | (new in P06) | Open - forecast completion 11.09.2026 (17 cd slip); float nil | TP-001
Reading
R-04 closed (instruction issued, EUR 138,400 incurred). R-09 hardened to blocker (3 returns). R-12 is the load-bearing item - see slide 6. R-15 is a physical bay-level dispute, not a BOQ-derived monetary dispute; contractor has not yet issued formal notice to Kallio. R-16 is a new 17 cd slip on Activity 50 that consumes the float on the critical path.
Sources: PDC-EI-004 - PDC-PROG-008-P06 - PDC-LTR-PMC-014 - PDC-MIN-P06 - PDC-PROG-001-P06
Polaris DC-1 · P06 · 8 of 10

## Slide 9
Look-ahead - September 2026
Next 4 weeks. Source dates from PDC-LT-001 Rev A and contractor correspondence.
Week | Activity | Owner
W36 (01-07.09) | DH2 waterproofing - Kallio reconciled status and W3/W4 resourcing | TP-001
W36 | 110 kV consequence assessment - contractor response due (12.09.2026) | Main Contractor
W37 (08-14.09) | DH1 piling - Activity 50 forecast completion 11.09.2026 | TP-001
W37 | Cooling Spine - pipework continuation, target 350 m of 820 m | TP-005
W38 (15-21.09) | Perimeter fencing - target 600 m of 980 m | TP-008
W38 | LT-13 Acoustic louvres order by 18.09.2026 | Procurement
W39 (22-28.09) | LT-08 Dry coolers order by 18.09.2026 | Procurement
W39 | LT-05 Battery systems order by 25.09.2026 | Procurement
W39 | DH1 pile cap commencement (Halls 3-4) | TP-001
Procurement - order-by dates in the next 8 weeks
LT-08 Dry coolers (TP-005, 22 wk lead) order by 18.09.2026 - 28.6 weeks float. LT-05 Battery systems (TP-006, 24 wk lead) order by 25.09.2026 - 29.6 weeks float. LT-13 Acoustic louvres (TP-003, 16 wk lead) order by 18.09.2026 - 28.6 weeks float. All on plan.
Sources: PDC-LT-001 Rev A - PDC-PROG-005-P06 - PDC-PROG-008-P06 - PDC-MIN-P06 - PDC-LTR-PMC-014
Polaris DC-1 · P06 · 9 of 10

## Slide 10
Status and next steps
Proceeding, with watch on 110 kV consequence assessment and DH2 waterproofing dispute.
Three P05 watch items crystallised into real events this month - the 110 kV date, the NW corner instruction, and DH1 piling acceleration. One procurement milestone was closed on time. R-09 has now been raised in three consecutive returns and is a blocker on the last 5% of Act 200. AC incurred in the period: EUR 1,789,300. The 110 kV date of 24.04.2027 makes Section 1 Taking Over on 02.05.2027 unachievable - see slide 6.
Next steps
- W36 (12.09) - Issue contractor response to PDC-LTR-PMC-014 on the 110 kV consequence. EOT entitlement reserved.
- W36 - Receive Kallio reconciled status on DH2 waterproofing; assess; close or escalate A06-02.
- W36 - Secure a date for relocation of the temporary parking compound to unblock the last 5% of Act 200.
- W37 - Activity 50 (DH1 piling) forecast completion 11.09.2026. Monitor against programme 25.08.2026 (R-16).
- W37-W39 - Execute next procurement order-by dates (LT-08, LT-05, LT-13) on programme.
- P07 - Reissue PDC-SCH-001 and PDC-MS-001 to reflect 110 kV slip; lodge EOT notification; reflect rebaseline in PV profile.
- P07 - Reissue P06 SPI / CPI / EAC / VAC from the updated baseline programme and reconcile indicative derivation against the Engineer's interim valuation.
Sources: PDC-CVR-P06 - PDC-LAB-P06 - PDC-PROG-001-P06 - PDC-PROG-005-P06 - PDC-PROG-008-P06 - PDC-MIN-P06 - PDC-LTR-PMC-014 - PDC-EI-004 - PDC-LT-001 Rev A - PDC-BOQ-001 Rev A - PDC-MS-001 Rev A - PDC-SC-001
Polaris DC-1 · P06 · 10 of 10