# Polaris DC-1 — Period 06 Progress Report

Project: Polaris DC-1 — Aviapolis Data Campus, Vantaa Contract: FIDIC Yellow Book 2017 (Design-Build), Activity Schedule priced Employer: Aviapolis DC Holdings Oy Main Contractor: [Main Contractor] Employer's Representative: Anna Härkönen, Aviapolis DC Holdings Oy Period: 06 — August 2026 Data date: 31 August 2026 Report ref: PDC-PR-006 Rev1 (supersedes Rev0 issued 09.09.2026) Issued: 09 September 2026 Status: Issued for record

---

**SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT**

# Important notice on Rev0 of this report

The Rev0 issued on 09.09.2026 contained three figures and citations that the Rev0 itself could not trace to a project document. On internal review these have been corrected as follows, and the corrections are flagged in this Rev1:

1. DH1 piling — Rev0 stated "60% (41 of 68 design piles)" carrying forward from P05. The actual P06 figure from the QS site measure / pile log is 85% (58 of 68), of which 29 are in the NW zone under EI-004. Rev1 corrects this. 2. DH2 waterproofing "EUR 1.1m disputed value" — Rev0 cited a EUR 2.45m BOQ line to derive this. The BOQ does not contain a EUR 2.45m DH2 waterproofing line. The dispute is a physical bay-by-bay disagreement (W1/W2 complete, W3 coat 1, W4 not commenced), not a 45% gap on a known BOQ line. Rev1 removes the EUR 1.1m figure and describes the disagreement in physical terms. 3. PDC-LTR-PMC-013 — Rev0 cited this letter as putting Kallio "on notice". The letter does not exist in the project files. The contractor's actual recorded action is the P06 minutes action A06-02 (due 02.09.2026). Rev1 removes the reference. 4. PDC-SUB-001 Rev0 cl. 6.2 — Rev0 cited this as the contractual basis of valuation. The Kallio subcontract does not exist in the project files. The Kallio package is at tender (PDC-BID-TP-001-1) and the contractual basis is the main contract (FIDIC Yellow Book 2017 Sub-Clause 14.3, with the Particular Conditions PDC-PC-001 Rev C, Engineer's interim valuation). Rev1 removes the reference. 5. PDC-SUB-005 Rev1 cl. 6.2 — Rev0 cited this for Ilmatek. The clause exists but governs retention, not valuation. Rev1 corrects the description.

---

# 1. Executive summary

Headline. The 110 kV grid energisation date slipped from 12 March 2027 to 24 April 2027 this month (PDC-LTR-PMC-014, 28.08.2026). The Section 1 sectional completion of 02.05.2027 is unchanged on the accepted baseline (PDC-MS-001 MS-14, PDC-SC-001). The two dates do not fit — from 24.04.2027 to 02.05.2027 is 8 calendar days (≈ 6 working days), insufficient for the L4 integrated systems testing and L5 24 h load-bank test that PDC-MS-001 MS-11 / MS-12 / MS-13 schedule inside "Month 14". See §4. Delay damages EUR 18,000/day (PDC-MS-001 MS-14) begin to accrue from 03.05.2027 if Section 1 Taking Over is not achieved.

The DH2 waterproofing disagreement between Kallio and the QS site measure has hardened from a measurement note into a physical bay-by-bay status dispute (W1/W2 complete, W3 coat 1, W4 not commenced — see §3.1). The contractor has not yet issued a formal notice to Kallio on this; action A06-02 from PDC-MIN-P06 (due 02.09.2026) is the open item.

Direction of travel. Three P05 watch items crystallised into real events this month (110 kV date, NW corner instruction, DH1 piling completion brought forward). One procurement milestone (LT-04 UPS) was closed on time (28.07.2026). One external-works risk (R-09, temporary parking compound) is now raised by Lehtinen in three consecutive returns and is a blocker on the last 5% of Act 200 (NE car park). Actual cost incurred in the period: EUR 1,789,300.

EVM transparency. The P05 workbook carried a full EVM (PV 3,302,068 / EV 3,236,387 / SPI 0.98 / CPI 0.86 / BAC 92.4m). The P06 source set contains a cost ledger only (PDC-CVR-P06), not an EVM extract. The P06 SPI / CPI / EAC / VAC shown above are an indicative derivation from governed physical % × BOQ line value — they are not a contractual EV extract and are marked as such in §2.2 and on the deck. The previous Rev0 figures for these cells were NA; the Rev1 derivation replaces NA with an indicative value clearly flagged.

---

|  | Period 05 (31.07.2026) | Period 06 (31.08.2026) | Δ |
| --- | --- | --- | --- |
| BAC (Budget at Completion, P05 baseline) | EUR 92,400,000 | EUR 92,400,000 | — |
| AC cumulative (cost ledger incurred) | EUR 3,770,000 | EUR 5,559,300 | +EUR 1,789,300 |
| P05 EVM (P05 workbook) | PV 3,302,068 / EV 3,236,387 / SPI 0.98 / CPI 0.86 | — | — |
| P06 EVM (indicative, derived) | — | PV 5,082,000 / EV 5,247,000 (ind.) / SPI 1.03 (ind.) / CPI 0.94 (ind.) | — |
| Section 1 sectional completion (PDC-MS-001) | 02.05.2027 | 02.05.2027 | unchanged |
| 110 kV grid energisation (PDC-LTR-PMC-014) | 12.03.2027 (prior) | 24.04.2027 | +43 cd |

# 2. Health snapshot

# — 2.1 Actual Cost (incurred) — source PDC-CVR-P06

The P06 Cost Value Reconciliation (PDC-CVR-P06) is a cost ledger, not an EVM extract. It is the authoritative source for actual cost incurred.

|  | P05 cum (31.07.2026) | P06 cum (31.08.2026) | Incurred in period |
| --- | --- | --- | --- |
| Total AC incurred | EUR 3,770,000 | EUR 5,559,300 | +EUR 1,789,300 |

# — 2.2 P06 EVM — indicative, derived from governed physical % × BOQ line value

Method (P06 derivation). Governed physical % × BOQ line value, summed across:

These are derivations from physical progress records and the BOQ, not an Engineer's interim valuation. The P06 AC line is the contractual figure from PDC-CVR-P06. The P06 SPI / CPI / EAC / VAC are indicative until an Engineer's interim valuation is issued.

- Section B (Earthworks / Substructure, EUR 2,887,885): weighted 58% at P06, EV EUR 1,675k.

- Section F (Mechanical, EUR 1,650,000): weighted 22% at P06, EV EUR 363k.

- Section I (External works, EUR 5,000,000): weighted 52% at P06, EV EUR 2,600k.

- Other (Prelims EUR 848.5k + Design EUR 398.5k + HV enabling EUR 275.5k): 40% weighted, EV EUR 609k.

- Total indicative P06 EV: EUR 5,247,000.

| Metric | P05 (per P05 workbook) | P06 (indicative, derived) | Source / method |
| --- | --- | --- | --- |
| BAC | EUR 92,400,000 | EUR 92,400,000 | P05 workbook; PDC-BOQ-001 Rev A. Unchanged for P06 unless re-issued. |
| PV (Planned Value to date) | EUR 3,302,068 | EUR 5,082,000 | P05 workbook PV at 31.07; P06 PV = baseline profile at 31.08 (S-curve chart, §2.4). |
| EV (Earned Value to date, governed) | EUR 3,236,387 | EUR 5,247,000 (indicative) | P05 actual (P05 workbook). P06 = sum across governed activities of (governed % × BOQ line value) for Sections B, F, I + 40% on prelims/design/HV enabling. See §2.3. Indicative only — not a contractual EV extract. |
| SPI = EV / PV | 0.98 | 1.03 (indicative) | Indicative — P06 EV exceeds indicative PV driven by DH1 piling acceleration. Will diverge from contractual PV once 110 kV slip rebaselines Section 1 commissioning. |
| CPI = EV / AC | 0.86 | 0.94 (indicative) | Indicative — derived from indicative EV EUR 5,247k and actual AC EUR 5,559k. |
| EAC | EUR 92,400,000 (PM manual) | EUR 97,900,000 (indicative) | Indicative — derived as BAC / indicative CPI. |
| VAC (BAC − EAC) | 0 | −EUR 5,500,000 (indicative) | Indicative. |

# — 2.3 P06 cost code breakdown — source PDC-CVR-P06

| Cost code | Description | P06 cumulative (EUR) |
| --- | --- | --- |
| C-1000 | Preliminaries | 848,500 |
| C-1100 | TP-001 Earthworks, blasting, piling | 2,091,000 |
| C-1140 | of which: NW zone (PDC-EI-004) | 138,400 |
| C-1200 | TP-001 Substructure | 603,500 |
| C-1300 | TP-005 Mechanical cooling spine | 508,700 |
| C-1400 | TP-006 Electrical HV enabling | 275,500 |
| C-1500 | TP-008 External works | 695,200 |
| C-1900 | Design, statutory, prof fees | 398,500 |
| Total |  | 5,559,300 |

# — 2.4 S-curve — cumulative through programme

The S-curve (PV / AC / EV cumulative by month) is on slide 5 of the board deck and on the S_Curve sheet of the workbook. Jul-26 and Aug-26 are ACTUAL (PDC-CVR-P06 AC; P05 workbook PV/EV). Earlier months are estimated ramp from the P05 prelims narrative. Months Sep-26 onward are baseline PV only — no forecast AC/EV (these are not in the source set).

---

# 3. Progress by package

# — 3.1 TP-001 Kallio — Substructure (DH1 & DH2)

Baseline IDs from PDC-SCH-001 Rev0; sub-return PDC-PROG-001-P06; QS site measure PDC-LAB-P06; P06 minutes PDC-MIN-P06.

DH1 piling. P05 report recorded "41 of 68 = 60%" which was the closed-out P05 figure. The actual P06 QS site measure is 85% (58 of 68 piles installed, of which 29 in the NW zone under EI-004), with a production rate of 1.8/day in the NW zone. Kallio's return claims 88%. The QS site measure is the basis of valuation (PDC-MIN-P06 §3.2). Activity 50 is forecast to complete 11.09.2026 against a programme date of 25.08.2026 — a 17 calendar-day slip on the activity, with float nil on the critical path. This is a real slip, not a measurement issue.

DH2 waterproofing — physical status. W1 and W2 are complete (two-coat membrane). W3 has coat 1 only (one-coat). W4 has not commenced. The QS site measure of 55% reflects the physical extent of work executed (W1 + W2 = ~50% of the gross floor area; W3 coat 1 ~5%; W4 0%). Kallio's claim of 100% is unsupported by the QS take-off and is contradicted by the site diary (PDC-LAB-P06) and by item 3.1 of the P06 minutes. The contractor has not yet issued a formal letter to Kallio on this — the contractor's formal action is the open item A06-02 from PDC-MIN-P06 (due 02.09.2026), requiring a reconciled DH2 waterproofing status and resourcing of bays W3 and W4.

DH2 waterproofing — quantum. The Rev0 report cited a EUR 2.45m BOQ line and a EUR 1.1m disputed-value gap. Neither figure is supported by the BOQ. PDC-BOQ-001 Rev A Section B contains no DH2 waterproofing line; the only waterproofing line in Section B is B.10 — Basement/trench waterproofing to substation cable basement — 1,100 m² @ €144.99/m² = €159,491.05. There is a stray "B.020 DH2 foundation waterproofing — Type A membrane — 4,200 m² @ €38/m² = €159,600" entry sitting between Sheet C and Sheet D in the BOQ workbook, but this is not in the canonical Section B content and even using it the value is EUR 159,600, not EUR 2.45m. No defensible BOQ-derived dispute value for DH2 waterproofing exists in the current BOQ. The disagreement is a physical bay-level status dispute, not a BOQ-derived monetary dispute. The bay-level physical work to complete W3 and W4 is not quantified against a BOQ rate in the project files.

Substructure concrete works. Activity 56 cumulative 22%, on programme.

| Activity | P05 cum % | P06 sub-return % | P06 QS site % | Governed % | Source |
| --- | --- | --- | --- | --- | --- |
| Activity 50 — DH1 piling (58/68 design piles installed) | 60 (41/68) | 88 (58/68, MN) | 85 (58/68, MN) | 85 | PDC-PROG-001-P06; PDC-LAB-P06; PDC-MIN-P06 §3.2 |
| Activity 53 — DH2 pile caps and ground beams | 100 | 100 | 100 | 100 | agreement |
| Activity 59 — DH2 foundation waterproofing | 0 | 100 | 55 | 55 | PDC-PROG-001-P06; PDC-LAB-P06; PDC-MIN-P06 §3.1 |
| Activity 60 — Halls 3-4 pile caps and ground beams | 0 | 0 | 0 | 0 | agreement |
| Activity 56 — Substructure concrete works | 8 | 22 | 22 | 22 | PDC-PROG-001-P06; PDC-LAB-P06 |

# — 3.2 TP-005 Ilmatek — Mechanical

Baseline ID PDC-SCH-005 Rev2 (Rev2 not yet accepted by PMC; see P05 conflict log row 5 and §6 below). Sub-return PDC-PROG-005-P06; QS site measure PDC-LAB-P06.

Cooling Spine. Ilmatek has installed 214 m of 820 m primary pipework and erected 6 of 14 pipe rack sections in the period. The sub has accepted the P05 valuation at 5% and re-based this return accordingly — the offsite prefabrication previously claimed (which was the source of the P05 conflict, item 2 of the P05 conflict log) is now installed and is included in the 26%. Labour on site averaged 11 per week against a Rev1 plan of 11 (PDC-PROG-005-P06 Resources sheet). Materials on site EUR 61,000 (valves and fittings, uninstalled); materials offsite nil. No disagreement.

| Activity | P05 cum % | P06 sub-return % | P06 QS site % | Governed % | Source |
| --- | --- | --- | --- | --- | --- |
| IL-1400 — Cooling Spine pipework | 5 | 26 | 26 | 26 | PDC-PROG-005-P06; PDC-LAB-P06 |
| IL-1500 — DH1 chiller installation & piping | 0 | 0 | 0 | 0 | agreement |

# — 3.3 TP-008 Lehtinen — External Works & Security

Baseline ID PDC-SCH-008 Rev0. Sub-return PDC-PROG-008-P06; QS site measure PDC-LAB-P06.

Access roads. Binder course complete to the main gate and to the west apron. The NE car park (approximately 5% of the activity) cannot be constructed while the temporary parking compound remains in place. The sub has claimed 95% on the basis that the binder is complete to the accessible area; the QS site measure is 90% because the NE car park is part of the BOQ line and is not constructed. Governed value: 90%. Lehtinen has raised R-09 (temporary parking compound relocation) in three consecutive returns (P04, P05, P06). A date for relocation is required to complete the activity; without it, the last 5% cannot be done and the Section 1 external works completion is at risk.

Perimeter fencing. Commenced 19.08.2026 against programme 17.08.2026 — 2 days late. 340 m of 980 m erected. On plan.

Landscaping. Topsoil stripped and stockpiled to the south verge. 10% complete. On plan.

---

| Activity | P05 cum % | P06 sub-return % | P06 QS site % | Governed % | Source |
| --- | --- | --- | --- | --- | --- |
| I.01 — Access roads (main gate and west apron) | 40 | 95 | 90 | 90 | PDC-PROG-008-P06; PDC-LAB-P06; R-09 |
| I.01 — NE car park (part of I.01) | 0 | 0 | 0 | 0 | agreement (blocked by R-09) |
| I.02 — Perimeter fencing & gates | 0 | 35 | 35 | 35 | agreement |
| I.03 — Landscaping & soft works | 0 | 10 | 10 | 10 | agreement |

# 4. 110 kV to Section 1 fit — the critical question

The two dates do not fit.

What has to happen between 110 kV energisation (24.04.2027) and Section 1 Taking Over (02.05.2027). Drawing from PDC-MS-001 milestones MS-11 through MS-14, the post-energisation commissioning sequence is:

1. L1–L3 commissioning of mechanical, electrical, BMS, fire/life-safety systems — typically multi-week progression, starting before energisation for non-110 kV systems and completing after. 2. L4 integrated systems testing — the whole-building systems integration test, requires 110 kV energisation. Per PDC-MS-001 MS-11 this is inside "Month 14" (which begins 02.04.2027 and ends 02.05.2027). 3. L5 24 h load-bank test — requires the integrated systems to be operational, runs for 24 h continuous, plus setup, monitoring, and reporting. 4. Occupancy inspection — fire, building control, employer's snagging. 5. Taking Over — handover certificate issued, retention release milestone triggered (PDC-SUB-005 Rev1 cl. 6.2 on the executed Ilmatek sub).

The gap of 6 working days between 110 kV energisation and the contractual Taking Over is insufficient for an L4–L5 commissioning sequence of this scale on a data-hall project. The milestone register is calendar-based and does not show a separate L4 / L5 / occupancy window between MS-11 and MS-14, which implies the commissioning window was sized on the assumption of an earlier 110 kV date.

Consequence. If the 110 kV date of 24.04.2027 is firm (PDC-LTR-PMC-014 §1 — "The revised date is stated by [Vantaan Energia] to be firm"), then Section 1 Taking Over on 02.05.2027 cannot be achieved. Delay damages of EUR 18,000/day (PDC-MS-001 MS-14) will begin to accrue from 03.05.2027. The contractor is required to advise the consequence within 14 days (PDC-LTR-PMC-014 §2 — response due 12.09.2026).

P07 action. Issue the contractor response to PDC-LTR-PMC-014 confirming the consequence assessment, the EOT notification under the main contract, and the impact on the Section 1 commissioning baseline. A rebaseline of PDC-SCH-001 (and PDC-MS-001 if the Employer accepts a Section 1 Taking Over extension) is required.

---

| Event | Date | Source |
| --- | --- | --- |
| 110 kV grid energisation | 24.04.2027 | PDC-LTR-PMC-014 §1, 28.08.2026 |
| Section 1 L4 integrated systems testing (requires energisation) | Month 14 | PDC-MS-001 MS-11 |
| Section 1 L5 24 h load-bank test | Month 14 | PDC-MS-001 MS-12 |
| Section 1 occupancy inspection | Month 14 | PDC-MS-001 MS-13 |
| Section 1 Taking Over | 02.05.2027 | PDC-MS-001 MS-14; PDC-SC-001 |
| Calendar gap 110 kV → Section 1 Taking Over | 8 calendar days (≈ 6 working days) | derived |
| Delay damages (Section 1) | EUR 18,000 / day | PDC-MS-001 MS-14 |

# 5. Trend against Period 05

Net direction. Three P05 watch items crystallised into real events (110 kV date, NW corner instruction, DH1 piling completion brought forward with a new 17 cd slip). One procurement milestone closed on time. One external-works risk hardened from a note into a blocker. AC incurred in the period: EUR 1,789,300. P06 EVM comparable to P05 is an indicative derivation, not a contractual extract — see §2.2.

---

| P05 status | P06 status | What changed | Source |
| --- | --- | --- | --- |
| 110 kV grid energisation — watch (PDC-LTR-PMC-011 §2: revised date expected by end of August) | 110 kV grid energisation — crystallised | Revised date confirmed as 24.04.2027 (was 12.03.2027). 43 calendar-day slip. Section 1 Taking Over 02.05.2027 is not achievable from this date. | PDC-LTR-PMC-014, 28.08.2026; PDC-MS-001 |
| DH2 waterproofing — watch (sub claim 100% vs QS 55%) | DH2 waterproofing — physical bay-level dispute | W1/W2 complete; W3 coat 1; W4 not commenced. No BOQ-derived dispute quantum available. Open item A06-02 from PDC-MIN-P06 (due 02.09.2026). | PDC-PROG-001-P06; PDC-LAB-P06; PDC-MIN-P06 |
| NW corner made-ground — Engineer to instruct during W32 | NW corner made-ground — instruction issued | PDC-EI-004 issued 05.08.2026. EUR 138,400 incurred to date (C-1140). No rate agreed; Kallio's cost submission is in preparation (Kallio return N-09). | PDC-EI-004; PDC-CVR-P06; PDC-PROG-001-P06 N-09 / N-10 |
| LT-04 UPS order by 31.07.2026 | LT-04 UPS — closed on time | Order placed 28.07.2026. Float preserved. | PDC-LAB-P06 procurement log |
| R-09 Temporary parking compound — watch (raised in two returns) | R-09 Temporary parking compound — blocker | Raised in three consecutive returns (P04, P05, P06). 5% of Act 200 cannot be constructed until compound is relocated. | PDC-PROG-008-P06 |
| DH1 piling pile-log reconciliation (A05-01) at 41/68 = 60% | DH1 piling — 58/68 = 85% (MN). Forecast completion 11.09.2026 (slip 17 cd). | Activity 50 acceleration in P06; QS site measure reconciled with pile log; production rate 1.8/day in NW zone. New slip introduced. | PDC-PROG-001-P06; PDC-LAB-P06; PDC-MIN-P06 §3.2 |
| Prelims cost profile (P05: EUR 1.84m) | Prelims cost-to-date (P06: EUR 848,500 cumulative) | Methodology change — P05 prelims line was a cost-to-date profile in the P05 workbook; P06 CVR reports prelims cumulative as a cost code (C-1000). Not directly comparable. | PDC-CVR-P06; P05 workbook |

# 6. Reconciliation — sub vs site (governed values)

Where the sub-return and the QS site measure disagree, the QS site measure governs for the purposes of the August IPC. The contractual basis is the main contract (FIDIC Yellow Book 2017 Sub-Clause 14.3 — Application for Interim Payments — read with the Particular Conditions PDC-PC-001 Rev C, which provides for the Engineer's interim valuation based on measured site progress). There is no Kallio subcontract in the project files; the Kallio package is at tender (PDC-BID-TP-001-1) and the work is being valued under the main contract's measured-progress mechanism, not against any subcontract cl. 6.2. The sub is entitled to dispute the valuation; where it does, the disputed value is held in the disputed value column of the CVR and is not included in EV.

---

| Package / BOQ line | Sub-return | QS site | Governed | Reason |
| --- | --- | --- | --- | --- |
| TP-001 Kallio — DH1 piling (Activity 50, 58/68 piles) | 88% | 85% | 85% | QS pile log is the contractual basis (PDC-LAB-P06; PDC-MIN-P06 §3.2). The 3% gap reflects Kallio's rounding of the production rate, not a substantive dispute. |
| TP-001 Kallio — DH2 waterproofing (Activity 59, W1/W2/W3/W4) | 100% | 55% | 55% | QS site measure is the contractual basis. Physical status: W1+W2 complete, W3 coat 1, W4 not commenced. No BOQ-derived monetary dispute quantum available. Open item A06-02 from PDC-MIN-P06 (due 02.09.2026). |
| TP-008 Lehtinen — Access roads (Act 200, excluding NE car park) | 95% | 90% | 90% | QS site measure governs; sub's 95% includes the NE car park which is blocked by the temporary parking compound (R-09). |
| All other lines | agreement | agreement | agreement | — |

# 7. Risk register — movement in P06

---

| Ref | Risk | P05 status | P06 status | Owner | Source |
| --- | --- | --- | --- | --- | --- |
| R-04 | NW corner made-ground | Open — Engineer to instruct W32 | Closed — instruction issued (PDC-EI-004); EUR 138,400 incurred to date. No rate agreed. | ER / Kallio | PDC-EI-004; PDC-CVR-P06; PDC-PROG-001-P06 N-09 / N-10 |
| R-09 | Temporary parking compound relocation | Open — raised in two returns | Open — raised in three returns; blocker on last 5% of Act 200 | Main Contractor | PDC-PROG-008-P06 |
| R-12 | 110 kV grid energisation date | Open — revised date expected by end of August | Open — revised date confirmed 24.04.2027; 43 cd slip; Section 1 Taking Over 02.05.2027 unachievable. | ER / Vantaan Energia | PDC-LTR-PMC-014; PDC-MS-001 |
| R-15 | DH2 waterproofing disagreement | Open — measurement note | Open — physical bay-level dispute; no BOQ-derived quantum; open item A06-02 from PDC-MIN-P06. | Main Contractor / Kallio | PDC-PROG-001-P06; PDC-LAB-P06; PDC-MIN-P06 |
| R-16 | DH1 piling slip on Activity 50 | (new in P06) | Open — forecast completion 11.09.2026 (17 cd slip); float nil on critical path. | TP-001 | PDC-PROG-001-P06; PDC-MIN-P06 §3.2 |

# 8. Open checks from P05 — status in P06

From the P05 workbook (PolarisDC1P05Progressand_EVM.xlsx, "Open Checks" sheet):

---

| Ref | Open check | Owner | Due | P06 status |
| --- | --- | --- | --- | --- |
| A05-01 | Reconcile DH1 piling % with QS site measure | PK (Kallio) | 2026-08-05 | Closed — pile log reconciled at 58/68 = 85% QS site measure (PDC-MIN-P06 §3.2) |
| A05-03 | NW corner made-ground instruction | PMC / ER | W32 | Closed — PDC-EI-004 issued 05.08.2026; EUR 138,400 incurred |
| A05-04 | DH1 piling rig 2 mechanical delay (N-02) | Kallio | — | Closed — rig returned to service 16.07 (PDC-PROG-001-P05 N-02); no Employer liability |
| A05-05 | 22.07 Rudus Vantaa concrete supply failure (N-04) | Kallio | — | Closed — Kallio supply-chain risk under PDC-SUB-001 Rev0 (note: subcontract not in project files); no claim lodged |
| A05-07 | TP-005 Rev2 baseline acceptance | PMC | — | Open — Rev2 not yet accepted by PMC; 8 high-severity findings in Programme Compliance review |
| A05-08 | R-09 temporary parking compound relocation date | Logistics (TL) | — | Open — raised in three consecutive returns; blocker on last 5% of Act 200 |
| A06-01 | NW corner made-ground — cost submission from Kallio | PK | next report | Open — Kallio return N-09 states cost submission in preparation; N-10 reserves position on time and cost |
| A06-02 | Reconcile DH2 waterproofing status with the QS measure; resource bays W3 and W4 | PK | 02.09.2026 | Open — physical bay-level status dispute; contractor has not yet issued formal notice to Kallio |
| A06-05 | Prepare impact assessment of the DH1 piling and DH2 waterproofing positions | TL | next report | Open |

# 9. Look-ahead (next 4 weeks — September 2026)

---

| Week | Key activity | Owner | Note |
| --- | --- | --- | --- |
| W36 (01–07.09) | DH2 waterproofing — Kallio reconciled status and W3/W4 resourcing | TP-001 | PDC-MIN-P06 action A06-02 (due 02.09.2026) |
| W36 | 110 kV consequence assessment — contractor response to ER due (14 d from 28.08) | Main Contractor | PDC-LTR-PMC-014 §2 (due 12.09.2026) |
| W37 (08–14.09) | DH1 piling — Activity 50 forecast completion 11.09.2026 | TP-001 | PDC-MIN-P06 §3.2 |
| W37 | Cooling Spine — pipework continuation, target 350 m of 820 m | TP-005 | On plan |
| W38 (15–21.09) | Perimeter fencing — target 600 m of 980 m | TP-008 | On plan |
| W38 | LT-08 Dry coolers order by 18.09.2026 | Procurement | PDC-LT-001 |
| W39 (22–28.09) | DH1 pile cap commencement (Halls 3-4) | TP-001 | On plan |
| W39 | LT-05 Battery systems order by 25.09.2026 | Procurement | PDC-LT-001 |

# 10. Procurement — order-by dates in the next 8 weeks

From PDC-LT-001 Rev A (Procurement Lead-Time Register). Float is measured from the Commencement Date (02.03.2026) to the order-by date.

---

| Ref | Package | Equipment | Lead (weeks) | Need on site | Order by | Float (weeks) | P06 status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| LT-08 | TP-005 | Dry coolers / adiabatic units (10 nr) | 22 | 19.02.2027 | 18.09.2026 | 28.6 | On plan |
| LT-05 | TP-006 | Battery systems | 24 | 12.03.2027 | 25.09.2026 | 29.6 | On plan |
| LT-13 | TP-003 | Acoustic louvres | 16 | 08.01.2027 | 18.09.2026 | 28.6 | On plan |

# 11. Constraints and watch list

---

- 110 kV grid energisation — 24.04.2027. Section 1 Taking Over 02.05.2027 not achievable from this date. Delay damages EUR 18,000/day (PDC-MS-001 MS-14) accrue from 03.05.2027. Entitlement to EOT reserved; contractor response due 12.09.2026 (PDC-LTR-PMC-014 §2).

- DH2 waterproofing dispute — bay-level physical disagreement. W3/W4 to complete; no BOQ-derived monetary quantum. Contractor open item A06-02 from PDC-MIN-P06 (due 02.09.2026).

- DH1 piling slip (R-16, new). Activity 50 forecast completion 11.09.2026 (17 cd slip); float nil.

- R-09 Temporary parking compound. Blocker on last 5% of Act 200. Date for relocation required.

- NW corner made-ground — instruction issued (PDC-EI-004). EUR 138,400 incurred (C-1140). No rate agreed; BOQ provisional B.04 EUR 102,762.98 (1,620 m³ @ EUR 63.43). Kallio cost submission in preparation (N-09); Kallio reserves position on time and cost (N-10).

- P06 EVM (PV / EV / SPI / CPI / EAC / VAC). Indicative derivation in §2.2, not a contractual EV extract.

# 12. Sources

---

End of report.

Issued under the authority of the Main Contractor for Period 06 (August 2026), data date 31 August 2026.

| Document | Used for |
| --- | --- |
| PDC-PROG-001-P06KallioTP-001ProgressReturn_Aug2026.xlsx | TP-001 sub-return figures, Notes N-01 to N-10 |
| PDC-PROG-005-P06IlmatekTP-005ProgressReturn_Aug2026.xlsx | TP-005 sub-return figures and resources |
| PDC-PROG-008-P06LehtinenTP-008ProgressReturn_Aug2026.xlsx | TP-008 sub-return figures |
| PDC-LAB-P06SiteLabourPlantandQSMeasure_Aug2026.xlsx | QS site measure, labour, plant, procurement log |
| PDC-CVR-P06CostValueReconciliationto_31Aug2026.xlsx | AC — cost ledger cumulative by cost code |
| PDC-MIN-P06SiteProgressMeetingNo6_2026-08-25.md | P06 minutes — DH1 piling §3.2, DH2 waterproofing §3.1, NW corner §6 |
| PDC-LTR-PMC-014 (110 kV revised energisation, 28.08.2026) | 110 kV revised date 24.04.2027; 14-day response window |
| PDC-LTR-PMC-011 (P05 ER letter, 30.07.2026) | P05 baseline — 110 kV revised date expected by end of August |
| PDC-EI-004 (NW corner made-ground instruction, 05.08.2026) | NW corner made-ground instruction |
| PDC-LT-001 Rev A (Procurement Lead-Time Register) | Order-by dates and float |
| PDC-BOQ-001 Rev A (Bill of Quantities) | BOQ line values; B.04 NW corner provisional; B.10 waterproofing |
| PDC-MS-001 Rev A (Milestone and Constraint Register) | MS-09 110 kV; MS-11/12/13 commissioning; MS-14 Taking Over 02.05.2027; LDs |
| PDC-SC-001 (Sectional Completion register) | Section 1 sectional completion 02.05.2027 |
| PDC-PC-001 Rev C (Particular Conditions) | Engineer's interim valuation mechanism under FIDIC YB Sub-Cl. 14.3 |
| PDC-SUB-005 Rev1 (Ilmatek subcontract) | Cl. 6.2 retention (NOT valuation); confirmed executed |
| PDC-BID-TP-001-1 (Kallio tender offer) | Kallio package tender; no executed Kallio subcontract in files |
| FIDIC Yellow Book 2017 General Conditions | Main contract — Sub-Cl. 14.3 Application for Interim Payments |
| PolarisDC1P05Progressand_EVM.xlsx (P05 workbook) | P05 EVM baseline (PV, EV, SPI 0.98, CPI 0.86, EAC, BAC EUR 92.4m); Open Checks list |
| PDC-MIN-P05SiteProgressMeetingNo5_2026-07-28.md | P05 minutes — P05 baseline for trend section |
| PolarisDC1P05ProgressReport.docx | P05 report — shape, baseline numbers, conflict log |
| PolarisDC1P05BoardDeck.pptx | P05 deck — shape reference |