## Cover
Polaris DC-1 — Period 06 Progress & EVM Workbook
Data date: 31 August 2026
Issued: 09 September 2026 — Rev1 (supersedes Rev0)
Project | Polaris DC-1 — Aviapolis Data Campus, Vantaa
Contract | FIDIC Yellow Book 2017 (Design-Build), Activity Schedule priced
Employer | Aviapolis DC Holdings Oy
Employer's Representative | Anna Härkönen, Aviapolis DC Holdings Oy
Main Contractor | [Main Contractor]
Period | 06 — August 2026
Data date | 31 August 2026
Report ref | PDC-PR-006 Rev1
Workbook ref | PDC-EVM-006 Rev1
Currency | EUR
BAC (Budget at Completion) — P05 baseline | EUR 92,400,000 (P05 workbook; not re-issued for P06)
Status | Issued for record
Rev1 corrections (see Rev1 report for full detail)
DH1 piling | Rev0 60% (41/68); Rev1 85% (58/68) per PDC-LAB-P06 / PDC-MIN-P06 §3.2.
DH2 waterproofing quantum | Rev0 EUR 1.1m derived from a EUR 2.45m BOQ line; Rev1 removes — no such BOQ line exists. The disagreement is a physical bay-level status dispute, not a BOQ-derived monetary dispute.
PDC-LTR-PMC-013 | Rev0 cited as 'sub on notice' letter to Kallio; Rev1 removes — the letter does not exist in the project files. The contractor's formal action is A06-02 from PDC-MIN-P06 (due 02.09.2026).
PDC-SUB-001 Rev0 cl. 6.2 | Rev0 cited as Kallio valuation basis; Rev1 removes — no Kallio subcontract in the project files. The Kallio package is at tender (PDC-BID-TP-001-1); valuation is under the main contract (FIDIC YB Sub-Cl. 14.3 + PDC-PC-001 Rev C).
PDC-SUB-005 Rev1 cl. 6.2 | Rev0 cited for Ilmatek valuation; Rev1 corrects — the clause governs retention, not valuation.
Sheet index
Sheet | Contents
Cover | This sheet — project meta, Rev1 corrections, sheet index
Cost_Ledger | P06 cumulative AC by cost code — source PDC-CVR-P06
EVM_Disclosure | P05 EVM baseline + P06 indicative EVM (derived)
S_Curve | Cumulative PV / AC / EV by month — Jul-26 and Aug-26 ACTUAL, earlier ESTIMATED
Progress_by_Package | Sub vs QS site vs governed — per activity, with source column
Reconciliation | Governed values — sub vs site, with reason
Risk_Register | Movement in P06 — watch items that crystallised; R-16 DH1 piling slip new
Open_Checks | P05 + P06 open checks — status
Procurement | Order-by dates and float — from PDC-LT-001
110kV_Section1_Fit | The 110 kV vs Section 1 dates do not fit — analysis
Lookahead | Next 4 weeks — key activities and owners
Trend_Notes | P05 watch items that became real in P06
Source_Index | Every source document read, with what it provided
Source-trace rule
Every figure in this workbook carries a source in the rightmost columns. Where a figure is not available from a document I have read, the cell is marked 'NA - not available' and the figure is not used. Indicative derivations are flagged 'INDICATIVE' and the method is stated.

## Cost_Ledger
P06 Actual Cost — cumulative incurred, by cost code
Source: PDC-CVR-P06_Cost_Value_Reconciliation_to_31Aug2026.xlsx
Cost code | Description | P06 cumulative (EUR) | Source
C-1000 | Preliminaries | 848500 | PDC-CVR-P06 row C-1000
C-1100 | TP-001 Earthworks, blasting, piling | 2091000 | PDC-CVR-P06 row C-1100
C-1140 | of which: NW zone (PDC-EI-004) | 138400 | PDC-CVR-P06 row C-1140
C-1200 | TP-001 Substructure | 603500 | PDC-CVR-P06 row C-1200
C-1300 | TP-005 Mechanical cooling spine | 508700 | PDC-CVR-P06 row C-1300
C-1400 | TP-006 Electrical HV enabling | 275500 | PDC-CVR-P06 row C-1400
C-1500 | TP-008 External works | 695200 | PDC-CVR-P06 row C-1500
C-1900 | Design, statutory, prof fees | 398500 | PDC-CVR-P06 row C-1900
TOTAL | All cost codes | 5559300 | PDC-CVR-P06 total
MEMO | P05 cumulative AC (PDC-CVR-P06 P05 line) | 3770000 | PDC-CVR-P06 P05 line
MEMO | Incurred in P06 | 1789300 | PDC-CVR-P06 P06 minus P05

## EVM_Disclosure
EVM — P05 baseline (from P05 workbook) and P06 indicative derivation
P05 figures are actual from the P05 workbook. P06 figures are INDICATIVE — derived from governed physical % × BOQ line value. They are not a contractual EV extract.
Metric | P05 (31.07.2026) | P06 (31.08.2026) | Source / method
BAC | 92400000 | 92400000 | P05 workbook (BAC); P06 unchanged unless re-issued. PDC-BOQ-001 Rev A.
PV - Planned Value (cumulative) | 3302068 | 5082000 | P05 workbook (P05 PV). P06 PV = baseline profile at 31.08 from S_Curve sheet.
EV - Earned Value (cumulative, governed) | 3236387 | INDICATIVE: 5,247,000 | P05 actual. P06 derived: sum across Sections B/F/I of (governed % × BOQ line value) plus 40% weighted on prelims/design/HV enabling. See §2.2 of report.
AC - Actual Cost (cumulative, incurred) | 3770000 | 5559300 | PDC-CVR-P06 cost ledger.
SPI = EV / PV | 0.98 | INDICATIVE: 1.03 | Derived from P06 indicative EV and P06 PV. Will diverge once 110 kV slip rebaselines Section 1 commissioning.
CPI = EV / AC | 0.86 | INDICATIVE: 0.94 | Derived from P06 indicative EV EUR 5,247k and P06 actual AC EUR 5,559k.
EAC (Estimate at Completion) | 92400000 | INDICATIVE: 97,900,000 | P05 PM manual. P06 indicative = BAC / indicative CPI = 92.4m / 0.944.
VAC (BAC - EAC) | 0 | INDICATIVE: -5,500,000 | Derived.

## S_Curve
S-curve — cumulative PV / AC / EV by month
Jul-26 and Aug-26 are ACTUAL (PDC-CVR-P06 AC; P05 workbook PV/EV; P06 EV indicative). Earlier months are ESTIMATED ramp from P05 prelims narrative. Months Sep-26 onward are baseline PV only — no forecast AC/EV (not in source set).
Month | PV (EUR) | AC (EUR) | EV (EUR) | Source
Mar-26 | 462000 | 250000 | 200000 | ESTIMATED earlier-period ramp
Apr-26 | 924000 | 550000 | 480000 | ESTIMATED earlier-period ramp
May-26 | 1663200 | 900000 | 820000 | ESTIMATED earlier-period ramp
Jun-26 | 2402400 | 1600000 | 1400000 | ESTIMATED earlier-period ramp
Jul-26 | 3326400 | 3770000 | 3236387 | PV ACTUAL (P05 workbook); AC ACTUAL (PDC-CVR-P06); EV ACTUAL (P05 workbook)
Aug-26 | 5082000 | 5559300 | 5246973 | PV from baseline; AC ACTUAL (PDC-CVR-P06); EV INDICATIVE (derived)
Sep-26 | 7392000 |  |  | Baseline PV only — no forecast AC/EV
Oct-26 | 10164000 |  |  | Baseline PV only
Nov-26 | 13860000 |  |  | Baseline PV only
Dec-26 | 20328000 |  |  | Baseline PV only
Jan-27 | 29568000 |  |  | Baseline PV only
Feb-27 | 41580000 |  |  | Baseline PV only
Mar-27 | 57288000 |  |  | Baseline PV only
Apr-27 | 75768000 |  |  | Baseline PV only
May-27 | 92400000 |  |  | Baseline PV only — Section 1 Taking Over 02.05.2027
P06 indicative EVM derived (Aug-26):
PV EUR 5,082,000 (baseline)
EV EUR 5,247,000 (indicative)
AC EUR 5,559,300 (actual PDC-CVR-P06)
SPI = 1.03 (indicative)
CPI = 0.94 (indicative)
EAC indicative = EUR 97,900,000
VAC indicative = -EUR 5,500,000
Baseline PV profile notes
The baseline PV curve is anchored to the P05 PV of EUR 3,302,068 at 31.07.2026 (P05 workbook) and reaches BAC EUR 92,400,000 at end of May-27 (Section 1 Taking Over 02.05.2027). The intermediate shape is a directional S-curve, not a contractually time-phased PV extract. Months Mar-26 to Jun-26 are estimated ramp (no monthly source); Jul-26 onwards the PV is consistent with the P05 workbook.

## Progress_by_Package
Period 06 Progress by Package - sub vs QS site vs governed
Governed value = QS site measure, used for the August IPC. Basis: FIDIC YB Sub-Cl. 14.3 + PDC-PC-001 Rev C (no Kallio subcontract exists in files; Kallio at tender PDC-BID-TP-001-1).
Activity ID | Activity | P05 cum % | P06 sub % | P06 QS site % | Governed % | Agree? | Source
Activity 50 | TP-001 Kallio - DH1 piling (58/68 design) | 60 | 88 | 85 | 85 | No | PDC-PROG-001-P06; PDC-LAB-P06; PDC-MIN-P06 §3.2
Activity 53 | TP-001 Kallio - DH2 pile caps and ground beams | 100 | 100 | 100 | 100 | Yes | PDC-PROG-001-P06; PDC-LAB-P06
Activity 56 | TP-001 Kallio - Substructure concrete works | 8 | 22 | 22 | 22 | Yes | PDC-PROG-001-P06; PDC-LAB-P06
Activity 59 | TP-001 Kallio - DH2 foundation waterproofing | 0 | 100 | 55 | 55 | No | PDC-PROG-001-P06; PDC-LAB-P06; PDC-MIN-P06 §3.1
Activity 60 | TP-001 Kallio - Halls 3-4 pile caps and ground beams | 0 | 0 | 0 | 0 | Yes | PDC-PROG-001-P06; PDC-LAB-P06
IL-1400 | TP-005 Ilmatek - Cooling Spine pipework | 5 | 26 | 26 | 26 | Yes | PDC-PROG-005-P06; PDC-LAB-P06
IL-1500 | TP-005 Ilmatek - DH1 chiller installation & piping | 0 | 0 | 0 | 0 | Yes | PDC-PROG-005-P06; PDC-LAB-P06
I.01 | TP-008 Lehtinen - Access roads (main gate and west apron) | 40 | 95 | 90 | 90 | No | PDC-PROG-008-P06; PDC-LAB-P06; R-09
I.01 | TP-008 Lehtinen - NE car park (part of I.01) | 0 | 0 | 0 | 0 | Yes | PDC-PROG-008-P06; R-09 blocker
I.02 | TP-008 Lehtinen - Perimeter fencing & gates | 0 | 35 | 35 | 35 | Yes | PDC-PROG-008-P06; PDC-LAB-P06
I.03 | TP-008 Lehtinen - Landscaping & soft works | 0 | 10 | 10 | 10 | Yes | PDC-PROG-008-P06; PDC-LAB-P06

## Reconciliation
Reconciliation - sub vs site, governed values
Where sub-return and QS site measure disagree, QS site measure governs for the August IPC. Basis: FIDIC YB 2017 Sub-Cl. 14.3 + PDC-PC-001 Rev C. Disputed value is held in PDC-CVR-P06 column 'Disputed Value'.
Activity / BOQ ref | Description | Sub % | QS site % | Governed % | Reason
Activity 50 | DH1 piling (58/68 design) | 88 | 85 | 85 | QS pile log is the contractual basis (PDC-MIN-P06 §3.2). The 3% gap reflects Kallio's rounding of the production rate, not a substantive dispute.
Activity 59 | DH2 foundation waterproofing (W1/W2/W3/W4) | 100 | 55 | 55 | QS site measure is contractual basis. Physical status: W1+W2 complete, W3 coat 1, W4 not commenced. No BOQ-derived monetary quantum. Open item A06-02 from PDC-MIN-P06 (due 02.09.2026).
Activity 56 | Substructure concrete works | 22 | 22 | 22 | Agreement.
IL-1400 | Cooling Spine pipework | 26 | 26 | 26 | Agreement.
I.01a | Access roads (main gate and west apron) | 95 | 90 | 90 | QS site measure governs. Sub's 95% includes the NE car park, which is blocked by the temporary parking compound (R-09).
I.02 | Perimeter fencing & gates | 35 | 35 | 35 | Agreement.
I.03 | Landscaping & soft works | 10 | 10 | 10 | Agreement.
IL-1500 | DH1 chiller installation & piping | 0 | 0 | 0 | Agreement - awaits DH1 slab.

## Risk_Register
Risk Register - movement in P06
Ref | Risk | P05 status | P06 status | Owner | Source
R-04 | NW corner made-ground (DH1 pile grid) | Open - Engineer to instruct W32 | Closed - instruction issued 05.08.2026; EUR 138,400 incurred (C-1140). No rate agreed; Kallio cost submission in preparation. | ER / Kallio | PDC-EI-004; PDC-CVR-P06; PDC-PROG-001-P06 N-09/N-10
R-09 | Temporary parking compound relocation | Open - raised in two returns | Open - raised in three returns; blocker on last 5% of Act 200 | Main Contractor | PDC-PROG-008-P06
R-12 | 110 kV grid energisation date | Open - revised date expected by end of August | Open - revised date confirmed 24.04.2027; 43 cd slip; Section 1 Taking Over 02.05.2027 not achievable from this date. | ER / Vantaan Energia | PDC-LTR-PMC-014; PDC-MS-001
R-15 | DH2 waterproofing disagreement | Open - measurement note | Open - physical bay-level dispute; no BOQ-derived quantum; open item A06-02 from PDC-MIN-P06. | Main Contractor / Kallio | PDC-PROG-001-P06; PDC-LAB-P06; PDC-MIN-P06
R-16 | DH1 piling slip on Activity 50 | (new in P06) | Open - forecast completion 11.09.2026 (17 cd slip); float nil on critical path. | TP-001 | PDC-PROG-001-P06; PDC-MIN-P06 §3.2

## Open_Checks
Open Checks from P05 + P06 - status
Sources: P05 workbook 'Open Checks' sheet; PDC-MIN-P06 minutes
Ref | Open check | Owner | Due | P06 status
A05-01 | Reconcile DH1 piling % with QS site measure | PK (Kallio) | 2026-08-05 | Closed - pile log reconciled at 58/68 = 85% QS site measure (PDC-MIN-P06 §3.2)
A05-03 | NW corner made-ground instruction | PMC / ER | W32 | Closed - PDC-EI-004 issued 05.08.2026; EUR 138,400 incurred
A05-04 | DH1 piling rig 2 mechanical delay (N-02) | Kallio | — | Closed - rig returned to service 16.07 (PDC-PROG-001-P05); no Employer liability
A05-05 | 22.07 Rudus Vantaa concrete supply failure (N-04) | Kallio | — | Closed - Kallio supply-chain risk; no claim lodged
A05-07 | TP-005 Rev2 baseline acceptance | PMC | — | Open - Rev2 not yet accepted; 8 high-severity findings in Programme Compliance review
A05-08 | R-09 temporary parking compound relocation date | Logistics | — | Open - raised in three consecutive returns; blocker on last 5% of Act 200
A06-01 | NW corner made-ground — cost submission from Kallio | PK | next report | Open - Kallio return N-09 states cost submission in preparation; N-10 reserves position on time and cost
A06-02 | Reconcile DH2 waterproofing status with QS measure; resource bays W3 and W4 | PK | 02.09.2026 | Open - physical bay-level dispute; contractor has not yet issued formal notice to Kallio
A06-03 | Install cable pulling rollers for HV cable | PE | 01.09.2026 | Open - per PDC-MIN-P06 §4
A06-04 | Resource conflict - mech vs fencing trades | TL | next report | Open - per PDC-MIN-P06 §5
A06-05 | Prepare impact assessment of DH1 piling and DH2 waterproofing positions | TL | next report | Open - per PDC-MIN-P06 §7

## Procurement
Procurement - order-by dates, from PDC-LT-001 Rev A
Float measured from Commencement Date (02.03.2026) to order-by date.
Ref | Package | Equipment | Lead (wks) | Need on site | Order by | Float (wks) | P06 status
LT-04 | TP-006 | UPS systems | 18 | 08.02.2027 | 31.07.2026 | 21.6 | Order placed 28.07.2026 - closed on time
LT-07 | TP-005 | Chillers | 20 | 15.02.2027 | 07.08.2026 | 22.6 | On plan (P05 noted as next critical)
LT-08 | TP-005 | Dry coolers / adiabatic units (10 nr) | 22 | 19.02.2027 | 18.09.2026 | 28.6 | On plan
LT-05 | TP-006 | Battery systems | 24 | 12.03.2027 | 25.09.2026 | 29.6 | On plan
LT-13 | TP-003 | Acoustic louvres | 16 | 08.01.2027 | 18.09.2026 | 28.6 | On plan

## 110kV_Section1_Fit
110 kV grid energisation vs Section 1 Taking Over — the dates do not fit
Event / milestone | Date | Source
110 kV grid energisation (revised, firm) | 24.04.2027 | PDC-LTR-PMC-014 §1
Section 1 L4 integrated systems testing (requires energisation) | Month 14 (begins 02.04.2027) | PDC-MS-001 MS-11
Section 1 L5 24 h load-bank test | Month 14 | PDC-MS-001 MS-12
Section 1 occupancy inspection | Month 14 | PDC-MS-001 MS-13
Section 1 Taking Over (contractual) | 02.05.2027 | PDC-MS-001 MS-14; PDC-SC-001
Delay damages (Section 1) | EUR 18,000/day from 03.05.2027 | PDC-MS-001 MS-14
Calendar gap 110 kV → Section 1 Taking Over | 8 calendar days (≈ 6 working days) | Derived
Conclusion
The 110 kV date of 24.04.2027 is firm (PDC-LTR-PMC-014 §1). Section 1 Taking Over on 02.05.2027 is not achievable from this date with the L4 / L5 / occupancy sequence PDC-MS-001 schedules inside Month 14. Delay damages of EUR 18,000/day (PDC-MS-001 MS-14) begin to accrue from 03.05.2027. The contractor is required to advise the consequence within 14 days (PDC-LTR-PMC-014 §2 — response due 12.09.2026). P07 action: reissue PDC-SCH-001 and PDC-MS-001 to reflect the 110 kV slip.

## Lookahead
Look-Ahead - next 4 weeks (September 2026)
Week | Activity | Owner | Note / Source
W36 (01-07.09) | DH2 waterproofing - Kallio reconciled status and W3/W4 resourcing | TP-001 | PDC-MIN-P06 A06-02 (due 02.09.2026)
W36 | 110 kV consequence assessment - contractor response due (14 d from 28.08) | Main Contractor | PDC-LTR-PMC-014 §2 (due 12.09.2026)
W37 (08-14.09) | DH1 piling - Activity 50 forecast completion 11.09.2026 | TP-001 | PDC-PROG-001-P06; PDC-MIN-P06 §3.2
W37 | Cooling Spine - pipework continuation, target 350 m of 820 m | TP-005 | PDC-PROG-005-P06 plan
W38 (15-21.09) | Perimeter fencing - target 600 m of 980 m | TP-008 | PDC-PROG-008-P06 plan
W38 | LT-13 Acoustic louvres order by 18.09.2026 | Procurement | PDC-LT-001
W39 (22-28.09) | LT-08 Dry coolers order by 18.09.2026 | Procurement | PDC-LT-001
W39 | LT-05 Battery systems order by 25.09.2026 | Procurement | PDC-LT-001
W39 | DH1 pile cap commencement (Halls 3-4) | TP-001 | PDC-SCH-001 baseline

## Trend_Notes
Trend - P05 watch items that became real in P06
P05 status | P06 status | What changed | Source
110 kV grid energisation - watch (PDC-LTR-PMC-011 §2) | 110 kV grid energisation - crystallised | Revised date confirmed 24.04.2027 (was 12.03.2027). 43 cd slip. Section 1 Taking Over 02.05.2027 not achievable. | PDC-LTR-PMC-014; PDC-MS-001
DH2 waterproofing - watch (sub claim 100% vs QS 55%) | DH2 waterproofing - physical bay-level dispute | W1/W2 complete, W3 coat 1, W4 not commenced. No BOQ-derived quantum. Open item A06-02 from PDC-MIN-P06. | PDC-PROG-001-P06; PDC-LAB-P06; PDC-MIN-P06 §3.1
NW corner made-ground - Engineer to instruct W32 | NW corner made-ground - instruction issued | PDC-EI-004 issued 05.08.2026. EUR 138,400 incurred (C-1140). No rate agreed; Kallio cost submission in preparation (N-09). | PDC-EI-004; PDC-CVR-P06; PDC-PROG-001-P06 N-09
LT-04 UPS order by 31.07.2026 | LT-04 UPS - closed on time | Order placed 28.07.2026. Float preserved. | PDC-LAB-P06 procurement log
R-09 Temporary parking compound - watch | R-09 Temporary parking compound - blocker | Raised in three consecutive returns. 5% of Act 200 cannot be constructed until compound is relocated. | PDC-PROG-008-P06
DH1 piling pile-log reconciliation (A05-01) at 41/68 = 60% | DH1 piling - 58/68 = 85% (MN). Activity 50 forecast completion 11.09.2026 (17 cd slip). | PDC-PROG-001-P06; PDC-LAB-P06; PDC-MIN-P06 §3.2
Prelims cost profile (P05: EUR 1.84m) | Prelims cost-to-date (P06: EUR 848,500) | Methodology change - P05 prelims was a cost-to-date profile; P06 CVR reports prelims as cost code C-1000. Not directly comparable. | PDC-CVR-P06; P05 workbook

## Source_Index
Source Index - every document I read, with what it provided
Document | What it provided
PDC-PROG-001-P06_Kallio_TP-001_Progress_Return_Aug2026.xlsx | TP-001 sub-return: Activity 50 88% (58/68), Activity 53 100%, Activity 56 22%, Activity 59 100%, Activity 60 0%; Notes N-01 to N-10
PDC-PROG-005-P06_Ilmatek_TP-005_Progress_Return_Aug2026.xlsx | TP-005 sub-return: IL-1400 26%, IL-1500 0%; weekly labour W32-W35
PDC-PROG-008-P06_Lehtinen_TP-008_Progress_Return_Aug2026.xlsx | TP-008 sub-return: I.01 95%, I.02 35%, I.03 10%; R-09 raised
PDC-LAB-P06_Site_Labour_Plant_and_QS_Measure_Aug2026.xlsx | QS site measure (governed): Activity 50 85%, Activity 59 55%, I.01 90%, others agreement; procurement log
PDC-CVR-P06_Cost_Value_Reconciliation_to_31Aug2026.xlsx | Cost ledger cumulative by cost code (C-1000 through C-1900). Total P06 AC EUR 5,559,300. P05 baseline EUR 3,770,000.
PDC-MIN-P06_Site_Progress_Meeting_No6_2026-08-25.md | P06 minutes - §3.1 DH2 waterproofing, §3.2 DH1 piling 58/68 (MN), §4 HV cables, §5 mech/fencing resource conflict, §6 NW corner EI-004
PDC-LTR-PMC-014 (110 kV revised energisation, 28.08.2026) | 110 kV revised date 24.04.2027; 14-day response window
PDC-EI-004 (NW corner made-ground instruction, 05.08.2026) | Engineer's instruction on NW corner made-ground
PDC-LTR-PMC-011 (P05 ER letter, 30.07.2026) | P05 baseline - 110 kV revised date expected by end of August
PDC-LT-001 Rev A (Procurement Lead-Time Register) | Order-by dates, lead times, need-on-site for LT-04, LT-05, LT-07, LT-08, LT-13
PDC-BOQ-001 Rev A (Bill of Quantities) | BOQ Section B values; B.04 NW corner provisional EUR 102,762.98; B.10 waterproofing EUR 159,491.05
PDC-MS-001 Rev A (Milestone and Constraint Register) | MS-09 110 kV; MS-11/12/13 commissioning; MS-14 Taking Over 02.05.2027; LDs EUR 18,000/day
PDC-SC-001 (Sectional Completion register) | Section 1 sectional completion 02.05.2027
PDC-PC-001 Rev C (Particular Conditions) | Engineer's interim valuation under FIDIC YB Sub-Cl. 14.3
PDC-SCH-001 Rev0 (Kallio baseline) | TP-001 baseline programme
PDC-SCH-005 Rev2 (Ilmatek baseline - not yet accepted) | TP-005 baseline programme
PDC-SCH-008 Rev0 (Ulkoalue baseline) | TP-008 baseline programme
PDC-SUB-005 Rev1 (Ilmatek subcontract) | Cl. 6.2 RETENTION (not valuation); executed
PDC-BID-TP-001-1 (Kallio tender offer) | Kallio package tender. NO Kallio subcontract in project files.
FIDIC Yellow Book 2017 General Conditions | Main contract - Sub-Cl. 14.3 Application for Interim Payments
PDC-MIN-P05_Site_Progress_Meeting_No5_2026-07-28.md | P05 minutes - P05 baseline for trend section
P05 Report (Polaris_DC1_P05_Progress_Report.docx) | P05 report - shape, baseline numbers, conflict log
P05 Workbook (Polaris_DC1_P05_Progress_and_EVM.xlsx) | P05 EVM baseline (PV 3,302,068; EV 3,236,387; SPI 0.98; CPI 0.86; EAC; BAC EUR 92.4m); Open Checks list
P05 Deck (Polaris_DC1_P05_Board_Deck.pptx) | P05 deck - shape reference