## Progress
ILMATEK LVI OY — MONTHLY PROGRESS RETURN
Polaris DC-1 · TP-005 Mechanical · Period 06 · data date 31.08.2026 · programme ref PDC-SCH-005 Rev1
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Prev cum % | This period % | Cum % at 31.08 | Basis of claim
118 | Cooling Spine — Pipework & Distribution | 5 | 21 | 26 | Installed on site: 214 m of 820 m primary pipework, 6 of 14 pipe rack sections, all spool sections previously prefabricated now delivered and erected
140 | DH1 — Chiller Installation & Piping | 0 | 0 | 0 | Not started — awaits DH1 slab
We accept the Period 05 valuation at 5% and have re-based this return accordingly. The offsite
prefabrication previously claimed is now installed and is included in the 26% above.
Materials on site: EUR 61,000 (valves and fittings, uninstalled). Materials offsite: nil.

## Resources
LABOUR AND SUPERVISION — TP-005
Period 06 · weekly average on Polaris DC-1 site
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Week | W/c | Pipefitters | Welders | Supervision | Total on site | Planned (Rev1)
W32 | 2026-08-03 | 6 | 2 | 1 | 9 | 11
W33 | 2026-08-10 | 8 | 2 | 1 | 11 | 11
W34 | 2026-08-17 | 8 | 3 | 1 | 12 | 11
W35 | 2026-08-24 | 8 | 3 | 1 | 12 | 11