## Progress Summary
KALLIO MAANRAKENNUS OY — MONTHLY PROGRESS RETURN
Polaris DC-1 · TP-001 Earthworks, Blasting, Piling & Substructure · Period 06 · data date 31.08.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Prev cum % | This period % | Cum % at 31.08 | Status | Comment
100 | Substation Building Construction | 80 | 20 | 100 | Complete | Roof deck complete 11.08.2026
56 | DH3 Pile Caps & Ground Beams | 35 | 65 | 100 | Complete | Completed 13.08.2026
59 | DH2 Foundation Waterproofing | 0 | 100 | 100 | Complete | Commenced 10.08, complete. Ready for slab.
50 | DH1 — Rock-Socketed Bored Piles | 64 | 24 | 88 | In progress | NW corner reaming continues under EI-004. Completion now forecast 11.09.
51 | DH2 — Rock-Socketed Bored Piles | 38 | 36 | 74 | In progress | On programme
52 | DH3 — Rock-Socketed Bored Piles | 22 | 36 | 58 | In progress | Ahead of programme
53 | DH4 — Rock-Socketed Bored Piles | 0 | 14 | 14 | In progress | Started 02.08 per programme
60 | DH3 Foundation Waterproofing | 0 | 20 | 20 | In progress | Commenced 24.08
54 | DH1 Pile Caps & Ground Beams | 0 | 0 | 0 | Not started | Awaits completion of DH1 piling

## DH1 Pile Log
DH1 — ROCK-SOCKETED BORED PILE INSTALLATION LOG
Design: 68 nr piles · 900 mm dia · rock socket min 1.5 m · as-built record to 31.08.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Pile ref | Date installed | Depth (m) | Socket (m) | Concrete (m3) | Zone | Remarks
P1-001 | 2026-06-14 | 14.6 | 1.8 | 9.7 | Main
P1-002 | 2026-06-14 | 15.0 | 2.1 | 10.3 | Main
P1-003 | 2026-06-15 | 15.4 | 2.4 | 10.9 | Main
P1-004 | 2026-06-16 | 15.8 | 1.5 | 11.5 | Main
P1-005 | 2026-06-17 | 16.2 | 1.8 | 9.1 | Main
P1-006 | 2026-06-17 | 16.6 | 2.1 | 9.7 | Main
P1-007 | 2026-06-19 | 14.2 | 2.4 | 10.3 | Main
P1-008 | 2026-06-19 | 14.6 | 1.5 | 10.9 | Main
P1-009 | 2026-06-20 | 15.0 | 1.8 | 11.5 | Main
P1-010 | 2026-06-21 | 15.4 | 2.1 | 9.1 | Main
P1-011 | 2026-06-22 | 15.8 | 2.4 | 9.7 | Main
P1-012 | 2026-06-22 | 16.2 | 1.5 | 10.3 | Main
P1-013 | 2026-06-23 | 16.6 | 1.8 | 10.9 | Main
P1-014 | 2026-06-24 | 14.2 | 2.1 | 11.5 | Main
P1-015 | 2026-06-24 | 14.6 | 2.4 | 9.1 | Main
P1-016 | 2026-06-26 | 15.0 | 1.5 | 9.7 | Main
P1-017 | 2026-06-26 | 15.4 | 1.8 | 10.3 | Main
P1-018 | 2026-06-27 | 15.8 | 2.1 | 10.9 | Main
P1-019 | 2026-06-28 | 16.2 | 2.4 | 11.5 | Main
P1-020 | 2026-06-29 | 16.6 | 1.5 | 9.1 | Main
P1-021 | 2026-06-29 | 14.2 | 1.8 | 9.7 | Main
P1-022 | 2026-07-01 | 14.6 | 2.1 | 10.3 | Main
P1-023 | 2026-07-01 | 15.0 | 2.4 | 10.9 | Main
P1-024 | 2026-07-01 | 15.4 | 1.5 | 11.5 | Main
P1-025 | 2026-07-03 | 15.8 | 1.8 | 9.1 | Main
P1-026 | 2026-07-03 | 16.2 | 2.1 | 9.7 | Main
P1-027 | 2026-07-04 | 16.6 | 2.4 | 10.3 | Main
P1-028 | 2026-07-05 | 14.2 | 1.5 | 10.9 | Main
P1-029 | 2026-07-06 | 14.6 | 1.8 | 11.5 | Main
P1-030 | 2026-07-06 | 15.0 | 2.1 | 9.1 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-031 | 2026-07-09 | 15.4 | 2.4 | 9.7 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-032 | 2026-07-09 | 15.8 | 1.5 | 10.3 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-033 | 2026-07-10 | 16.2 | 1.8 | 10.9 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-034 | 2026-07-13 | 16.6 | 2.1 | 11.5 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-035 | 2026-07-13 | 14.2 | 2.4 | 9.1 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-036 | 2026-07-15 | 14.6 | 1.5 | 9.7 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-037 | 2026-07-17 | 15.0 | 1.8 | 10.3 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-038 | 2026-07-18 | 15.4 | 2.1 | 10.9 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-039 | 2026-07-19 | 15.8 | 2.4 | 11.5 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-040 | 2026-07-21 | 16.2 | 1.5 | 9.1 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-041 | 2026-07-22 | 16.6 | 1.8 | 9.7 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-042 | 2026-07-24 | 14.2 | 2.1 | 10.3 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-043 | 2026-07-25 | 14.6 | 2.4 | 10.9 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-044 | 2026-07-27 | 15.0 | 1.5 | 11.5 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-045 | 2026-07-28 | 15.4 | 1.8 | 9.1 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-046 | 2026-07-29 | 15.8 | 2.1 | 9.7 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-047 | 2026-07-31 | 16.2 | 2.4 | 10.3 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-048 | 2026-07-31 | 16.6 | 1.5 | 10.9 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-049 | 2026-08-03 | 14.2 | 1.8 | 11.5 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-050 | 2026-08-04 | 14.6 | 2.1 | 9.1 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-051 | 2026-08-05 | 15.0 | 2.4 | 9.7 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-052 | 2026-08-07 | 15.4 | 1.5 | 10.3 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-053 | 2026-08-09 | 15.8 | 1.8 | 10.9 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-054 | 2026-08-09 | 16.2 | 2.1 | 11.5 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-055 | 2026-08-11 | 16.6 | 2.4 | 9.1 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-056 | 2026-08-12 | 14.2 | 1.5 | 9.7 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-057 | 2026-08-13 | 14.6 | 1.8 | 10.3 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
P1-058 | 2026-08-16 | 15.0 | 2.1 | 10.9 | NW (EI-004) | Made ground to 3.0-4.2 m, reamed. Instructed work under EI-004.
TOTAL INSTALLED | 58 |  |  |  |  | of 68 nr design
OF WHICH IN NW ZONE | 29 |  |  |  |  | instructed under EI-004 dated 05.08.2026

## DH2 Waterproofing Record
DH2 FOUNDATION WATERPROOFING — APPLICATION RECORD
Activity 59 · 4 nr bays · two-coat bituminous membrane to underside slab and upstands
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Bay | Area (m2) | Coat 1 applied | Coat 2 applied | Inspected | Status
W1 | 1180 | 2026-08-10 | 2026-08-13 | Yes | Complete
W2 | 1180 | 2026-08-17 | 2026-08-20 | Yes | Complete
W3 | 1180 | 2026-08-27 | — | No | Coat 1 only
W4 | 1180 | — | — | No | Not commenced

## Notes and Delays
NOTES, DELAYS AND MATTERS FOR THE MAIN CONTRACTOR
Period 06 · August 2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | Date | Matter
N-06 | 2026-08-05 | Engineer's Instruction EI-004 received. Excavation and disposal of made ground in the NW zone of the DH1 pile grid is instructed under BOQ item B.04. We are keeping separate records of plant, labour and output within the instructed zone as required.
N-07 | 2026-08-14 | DH1 piling: production within the NW zone remains at 1.8 piles/day against 3.0 elsewhere. 58 of 68 piles installed at 31.08, of which 29 within the instructed zone. Completion of activity 50 is now forecast 11.09.2026 against a programme date of 25.08.2026.
N-08 | 2026-08-10 | DH2 foundation waterproofing commenced 10.08.2026. The programmed start was 29.07.2026. Access was not available: the DH2 pile caps were completed 28.07 and required curing and backfill before the membrane could be applied.
N-09 | 2026-08-21 | Our cost submission in respect of the EI-004 works is in preparation and will follow. We are not in a position to state a sum at this date. Records to 31.08 are appended to this return.
N-10 | 2026-08-28 | We reserve our position on time and cost in respect of the EI-004 works and of the matters notified in N-01, N-03 and N-05 of our Period 05 return.