## Progress
MAANRAKENNUS LEHTINEN OY — MONTHLY PROGRESS RETURN
Polaris DC-1 · TP-008 External Works & Security · Period 06 · data date 31.08.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Prev cum % | This period % | Cum % at 31.08 | Comment
200 | Access Roads & Parking Construction | 40 | 55 | 95 | Binder course complete to main gate and to the west apron. The NE car park (approx. 5% of the activity) cannot be constructed while the temporary parking compound remains in place.
202 | Perimeter Fencing & Gates | 0 | 35 | 35 | Commenced 19.08.2026 against programme 17.08. 340 m of 980 m erected.
203 | Landscaping & Soft Works | 0 | 10 | 10 | Topsoil stripped and stockpiled to the south verge.
Risk R-09 remains open. We have now raised this in three consecutive returns. We require a date
for relocation of the temporary parking compound in order to complete activity 200.