## Cost Summary
COST VALUE RECONCILIATION — CUMULATIVE ACTUAL COST TO 31.08.2026
Polaris DC-1 · Period 06 · main contractor cost ledger · committed and incurred, excluding retention
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Cost code | Description | Cum AC to 31.07 (EUR) | Incurred in period (EUR) | Cum AC to 31.08 (EUR)
C-1000 | Preliminaries and site establishment | 742500 | 106000 | 848500
C-1100 | TP-001 Earthworks, blasting and piling | 1486200 | 604800 | 2091000
C-1140 | TP-001 NW zone — instructed works (EI-004) | 0 | 138400 | 138400
C-1200 | TP-001 Substructure — caps, beams, waterproofing | 388900 | 214600 | 603500
C-1300 | TP-005 Mechanical — cooling spine | 96400 | 412300 | 508700
C-1400 | TP-006 Electrical — HV enabling | 214000 | 61500 | 275500
C-1500 | TP-008 External works and security | 486300 | 208900 | 695200
C-1900 | Design, statutory and professional fees | 355700 | 42800 | 398500
| TOTAL CUMULATIVE ACTUAL COST | 3770000 | 1789300 | 5559300

## C-1140 NW Zone Detail
COST CODE C-1140 — NW ZONE INSTRUCTED WORKS (EI-004)
Opened 05.08.2026 on receipt of EI-004. Records kept separately as instructed.
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Element | Basis | Quantity | Unit | Amount (EUR)
Excavation of made ground, NW zone | Plant and labour, recorded daily | 1840 | m3 | 61400
Disposal off site incl. tipping | Weighbridge tickets | 1840 | m3 | 44900
Additional reaming, piles P1-030 to P1-058 | Rig hours over base rate | 118 | hr | 21200
Supervision and records | Time related | 4 | wk | 10900
TOTAL INCURRED TO 31.08.2026 |  |  |  | 138400
Note: BOQ item B.04 (excavation of unrecorded made ground) is a PROVISIONAL sum of EUR 102,762.98.
No rate has been agreed for the instructed works. The subcontractor cost submission has not been
received (TP-001 return, note N-09). The figures above are our incurred cost, not a valuation.