## Labour Returns
SITE LABOUR RETURNS — GATE HEADCOUNT
Polaris DC-1 · Period 06 · recorded at turnstile, daily average per week · main contractor record
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Week | W/c | TP-001 Kallio | TP-005 Ilmatek | TP-008 Lehtinen | MC staff | Total
W32 | 2026-08-03 | 27 | 9 | 9 | 10 | 55
W33 | 2026-08-10 | 28 | 11 | 10 | 10 | 59
W34 | 2026-08-17 | 28 | 12 | 11 | 11 | 62
W35 | 2026-08-24 | 26 | 12 | 11 | 11 | 60

## Plant Returns
PLANT ON SITE — WEEKLY
Polaris DC-1 · Period 06
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Item | W32 | W33 | W34 | W35 | Remarks
Piling rig — Junttan PM20 (rig 1) | 1 | 1 | 1 | 1
Piling rig — Junttan PM20 (rig 2) | 1 | 1 | 1 | 1
Crawler crane 80 t | 1 | 1 | 1 | 1
Excavator 25 t | 3 | 3 | 3 | 2 | Third machine on hire 03.08-28.08 for the NW zone (EI-004)
Concrete pump | 1 | 1 | 1 | 1
Welding set (TP-005) | 2 | 3 | 3 | 3
Muck-away lorries (NW zone) | 4 | 4 | 4 | 2 | Disposal of made ground, EI-004. Tickets in the CVR.

## QS Site Measure
QUANTITY SURVEYOR — INDEPENDENT SITE MEASURE AT 31.08.2026
Measured on site 28-31.08.2026 by M. Nieminen MRICS. This measure governs for valuation.
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Measured cum % | Basis of measure
50 | DH1 — Rock-Socketed Bored Piles | 85 | 58 of 68 piles installed and concreted (pile log verified against as-built survey)
51 | DH2 — Rock-Socketed Bored Piles | 74 | 50 of 68 piles installed
52 | DH3 — Rock-Socketed Bored Piles | 58 | 39 of 68 piles installed
53 | DH4 — Rock-Socketed Bored Piles | 14 | 10 of 68 piles installed
54 | DH1 Pile Caps & Ground Beams | 0 | Not commenced — DH1 piling incomplete
56 | DH3 Pile Caps & Ground Beams | 100 | All 14 caps poured and stripped. Completed 13.08.2026 against programme 11.08.2026.
59 | DH2 Foundation Waterproofing | 55 | Bays W1 and W2 complete (2 coats, inspected). W3 coat 1 only, W4 not commenced. NOT complete. Slab cannot follow on bays W3-W4.
60 | DH3 Foundation Waterproofing | 20 | Bay 1 coat 1 only
63 | DH2 Ground Floor Slab | 0 | Not commenced — waterproofing incomplete to W3 and W4
100 | Substation Building Construction | 100 | Roof deck complete. Handed over to TP-006 for HV plant installation 12.08.2026.
118 | Cooling Spine — Pipework & Distribution | 24 | 198 m of 820 m primary pipework installed and supported; 6 of 14 rack sections
200 | Access Roads & Parking Construction | 95 | Binder course 1,470 m of 1,550 m. NE car park not constructable — temporary compound in place.
202 | Perimeter Fencing & Gates | 35 | 340 m of 980 m erected
203 | Landscaping & Soft Works | 10 | Topsoil strip only

## Site Diary Extract
SITE DIARY — EXTRACT, MATERIAL ENTRIES ONLY
Polaris DC-1 · Period 06 · main contractor record
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Date | Entry
2026-08-05 | Engineer's Instruction EI-004 received and issued to TP-001. Separate cost code opened (C-1140 NW zone).
2026-08-05 | Third 25 t excavator and 4 nr muck-away lorries mobilised to the NW zone.
2026-08-10 | DH2 waterproofing commenced, bay W1. 12 working days later than programme.
2026-08-11 | Substation roof deck poured. Activity 100 complete.
2026-08-12 | Substation building handed to TP-006 Voima Electric for HV plant installation.
2026-08-13 | DH3 pile caps complete.
2026-08-19 | Perimeter fencing commenced, 2 days later than programme. Non-critical.
2026-08-25 | Progress meeting No. 6. See minutes.
2026-08-27 | DH2 waterproofing bay W3 coat 1 applied. Bay W4 not commenced — TP-001 labour redeployed to DH1 piling.
2026-08-28 | Employer's Representative letter PDC-LTR-PMC-014 received — revised 110 kV energisation date.
2026-08-31 | QS site measure taken 28-31.08. DH1 piling 58 of 68.