## Progress
ILMATEK LVI OY — MONTHLY PROGRESS RETURN
Polaris DC-1 · TP-005 Mechanical · Period 07 · data date 30.09.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Prev cum % | This period % | Cum % at 30.09 | Basis of claim
118 | Cooling Spine — Pipework & Distribution | 26 | 22 | 48 | 392 m of 820 m primary pipework installed; 11 of 14 rack sections
140 | DH1 — Chiller Installation & Piping | 0 | 0 | 0 | Not started — awaits DH1 slab

## Notice of Delay
ILMATEK LVI OY — NOTICE OF DELAY AND APPLICATION FOR EXTENSION OF TIME
Reference ILM-NOT-003 · 24 September 2026 · TP-005 subcontract PDC-SUB-005 Rev1
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Para | Text
1 | We give notice of delay to activity 118 (cooling spine pipework and distribution) arising from late release of the DH2 slab working area to us.
2 | The DH2 ground floor slab was programmed to complete 13.09.2026. It commenced 21.09.2026 and remains incomplete at the date of this notice.
3 | We are delayed by 22 working days and we apply for an extension of time of 22 working days to our subcontract completion date, together with the associated prolongation cost, quantum to follow.
4 | We consider this delay to be neither our fault nor our risk under the subcontract.

## Resources
LABOUR AND SUPERVISION — TP-005
Period 07 · weekly average on site
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Week | W/c | Pipefitters | Welders | Supervision | Total on site | Planned (Rev1)
W36 | 2026-08-31 | 8 | 3 | 1 | 12 | 11
W37 | 2026-09-07 | 9 | 3 | 1 | 13 | 11
W38 | 2026-09-14 | 9 | 3 | 1 | 13 | 11
W39 | 2026-09-21 | 8 | 3 | 1 | 12 | 11
W40 | 2026-09-28 | 8 | 3 | 1 | 12 | 11