## Cost Submission
KALLIO MAANRAKENNUS OY — COST SUBMISSION, ENGINEER’S INSTRUCTION EI-004
Polaris DC-1 · TP-001 · NW zone made ground · works executed 05.08.2026 to 31.08.2026 · submitted 16.09.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Item | Description | Quantity | Unit | Rate (EUR) | Amount (EUR)
1 | Excavation of made ground, NW zone, below 3.0 m | 1840 | m3 | 42.5 | 78200
2 | Disposal off site including tipping charges | 1840 | m3 | 28.48 | 52400
3 | Additional reaming, piles P1-030 to P1-058 | 118 | hr | 270.34 | 31900
4 | Site supervision and contemporaneous records | 4 | wk | 4650 | 18600
5 | Standing time, piling rig 2 | 6 | day | 2450 | 14700
6 | Prolongation preliminaries | 4 | wk | 4700 | 18800
| TOTAL SUBMITTED |  |  |  | 214600
Submitted under Sub-Clause 13.3.1 for agreement. No rate has been agreed to date.
Quantities are as recorded contemporaneously and separately identified per PDC-LTR-PMC-011.