## Progress Summary
KALLIO MAANRAKENNUS OY — MONTHLY PROGRESS RETURN
Polaris DC-1 · TP-001 · Period 07 · data date 30.09.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Prev cum % | This period % | Cum % at 30.09 | Status | Comment
50 | DH1 — Rock-Socketed Bored Piles | 85 | 15 | 100 | Complete | All 68 piles installed. Completed 11.09.2026 as forecast in our Period 06 return.
51 | DH2 — Rock-Socketed Bored Piles | 74 | 26 | 100 | Complete | Completed 15.09.2026, on programme
59 | DH2 Foundation Waterproofing | 55 | 45 | 100 | Complete | Bays W3 and W4 completed. Inspection certificate KMO-QC-0219 attached.
60 | DH3 Foundation Waterproofing | 20 | 80 | 100 | Complete | Completed 09.09.2026
52 | DH3 — Rock-Socketed Bored Piles | 58 | 30 | 88 | In progress | On programme
53 | DH4 — Rock-Socketed Bored Piles | 14 | 32 | 46 | In progress | On programme
54 | DH1 Pile Caps & Ground Beams | 0 | 35 | 35 | In progress | Commenced 14.09 following completion of DH1 piling
57 | DH4 Pile Caps & Ground Beams | 0 | 20 | 20 | In progress
61 | DH4 Foundation Waterproofing | 0 | 30 | 30 | In progress
63 | DH2 Ground Floor Slab | 0 | 25 | 25 | In progress | Commenced 21.09. See our revised programme PDC-SCH-001 Rev1.
64 | DH3 Ground Floor Slab | 0 | 10 | 10 | In progress

## Certificate KMO-QC-0219
CERTIFICATE OF COMPLETION AND INSPECTION — KMO-QC-0219
Activity 59 · DH2 foundation waterproofing · two-coat bituminous membrane
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Field | Entry
Bays certified | W3, W4 (W1 and W2 previously certified KMO-QC-0207, 20.08.2026)
Membrane | Two coats applied and holiday-tested to specification
Works completed | 2026-09-18
Inspected and signed | 2026-09-20
Inspector | J. Salminen, Kallio Maanrakennus Oy — site QC
Witnessed by | (not witnessed — main contractor representative unavailable)
Remarks | Bays W3 and W4 accepted. Ground floor slab may proceed.

## Notes and Delays
NOTES, DELAYS AND MATTERS FOR THE MAIN CONTRACTOR
Period 07 · September 2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | Date | Matter
N-11 | 2026-09-11 | DH1 piling complete, all 68 piles. Completion achieved on the date forecast in our Period 06 return.
N-12 | 2026-09-16 | Our cost submission in respect of the EI-004 works is attached (PDC-COST-001-EI004). This discharges action A06-06.
N-13 | 2026-09-18 | DH2 foundation waterproofing complete to all four bays. Certificate KMO-QC-0219 attached.
N-14 | 2026-09-22 | Revised programme PDC-SCH-001 Rev1 submitted, updated for actual progress to 18.09.2026.
N-15 | 2026-09-28 | We maintain our reservation of position on time and cost in respect of the EI-004 works.