## Programme Rev1
KALLIO MAANRAKENNUS OY — PDC-SCH-001 Rev1
Polaris DC-1 · TP-001 works · updated for actual progress to 18.09.2026 · issued 22.09.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Duration (wd) | Start | Finish | Predecessor | Change from Rev0
50 | DH1 — Rock-Socketed Bored Piles | 53 | 2026-06-14 | 2026-09-11 | 41FS | Actual finish 11.09 (Rev0 25.08)
51 | DH2 — Rock-Socketed Bored Piles | 53 | 2026-07-05 | 2026-09-15 | 50SS+15 | Actual finish 15.09
52 | DH3 — Rock-Socketed Bored Piles | 53 | 2026-07-19 | 2026-10-09 | 51SS+10 | Progressed
53 | DH4 — Rock-Socketed Bored Piles | 53 | 2026-08-02 | 2026-10-23 | 52SS+10 | Progressed
54 | DH1 Pile Caps & Ground Beams | 14 | 2026-09-14 | 2026-10-01 | 50FS | Progressed
59 | DH2 Foundation Waterproofing | 11 | 2026-08-10 | 2026-09-18 | 55FS | Actual finish 18.09
63 | DH2 Ground Floor Slab | 15 | 2026-09-21 | 2026-10-09 | 59SS+5
64 | DH3 Ground Floor Slab | 22 | 2026-09-28 | 2026-10-27 | 60SS+15 | Progressed
Section 1 completion is unaffected by this revision.

## Covering Note
COVERING NOTE — PDC-SCH-001 Rev1
Kallio Maanrakennus Oy · 22 September 2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Para | Text
1 | We attach Rev1 of our programme, updated to reflect actual progress achieved to 18 September 2026.
2 | DH1 piling completed 11.09.2026 and DH2 piling completed 15.09.2026. DH2 foundation waterproofing completed 18.09.2026 and is certified.
3 | The revision reflects progress only. There is no change to the date for completion of Section 1 and no extension of time is sought by this submission.
4 | We would be grateful for the Contractor’s acceptance of Rev1 as the programme of record for TP-001.