## Progress
MAANRAKENNUS LEHTINEN OY — MONTHLY PROGRESS RETURN
Polaris DC-1 · TP-008 External Works & Security · Period 07 · data date 30.09.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Prev cum % | This period % | Cum % at 30.09 | Comment
200 | Access Roads & Parking Construction | 95 | 3 | 98 | Temporary compound relocated 14.09 following the Contractor’s instruction. NE car park sub-base now in progress.
202 | Perimeter Fencing & Gates | 35 | 65 | 100 | Complete 23.09.2026
203 | Landscaping & Soft Works | 10 | 25 | 35 | Ongoing
Risk R-09 is closed. We record our thanks for the relocation, which was five working days later than
the date given in the Period 06 minutes (action A06-03, due 09.09.2026). We make no claim in respect of it.