## Cost Summary
COST VALUE RECONCILIATION — CUMULATIVE ACTUAL COST TO 30.09.2026
Polaris DC-1 · Period 07 · committed and incurred, excluding retention
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Cost code | Description | Cum AC to 31.08 (EUR) | Incurred in period (EUR) | Cum AC to 30.09 (EUR)
C-1000 | Preliminaries and site establishment | 848500 | 112400 | 960900
C-1100 | TP-001 Earthworks, blasting and piling | 2091000 | 688300 | 2779300
C-1140 | TP-001 NW zone — instructed works (EI-004) | 138400 | 14400 | 152800
C-1200 | TP-001 Substructure — caps, beams, waterproofing | 603500 | 412700 | 1016200
C-1300 | TP-005 Mechanical — cooling spine | 508700 | 486200 | 994900
C-1400 | TP-006 Electrical — HV enabling | 275500 | 98600 | 374100
C-1500 | TP-008 External works and security | 695200 | 341800 | 1037000
C-1900 | Design, statutory and professional fees | 398500 | 44100 | 442600
| TOTAL CUMULATIVE ACTUAL COST | 5559300 | 2198500 | 7757800

## C-1140 NW Zone Detail
COST CODE C-1140 — NW ZONE INSTRUCTED WORKS (EI-004)
Our incurred cost. The subcontractor cost submission of 16.09.2026 covers the SAME works and period.
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Element | Basis | Quantity | Unit | To 31.08 (EUR) | In period (EUR) | Total (EUR)
Excavation of made ground, NW zone | Plant and labour, recorded daily | 1840 | m3 | 61400 | 0 | 61400
Disposal off site incl. tipping | Weighbridge tickets | 1840 | m3 | 44900 | 0 | 44900
Additional reaming, P1-030 to P1-058 | Rig hours over base rate | 118 | hr | 21200 | 0 | 21200
Supervision and records | Time related | 4 | wk | 10900 | 0 | 10900
Reinstatement and making good | Instructed, September | 1 | item | 0 | 14400 | 14400
TOTAL INCURRED TO 30.09.2026 |  |  |  | 138400 | 14400 | 152800
Note: the works instructed by EI-004 were executed 05.08-31.08.2026. The quantities above are
the same quantities the subcontractor has now submitted a build-up for. This is one liability, not two.
BOQ item B.04 remains a provisional sum of EUR 102,762.98. No rate has been agreed.