## Labour Returns
SITE LABOUR RETURNS — GATE HEADCOUNT
Polaris DC-1 · Period 07 · recorded at turnstile · DAILY for weeks 38 and 39, weekly average otherwise
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Week | W/c | TP-001 Kallio | TP-005 Ilmatek | TP-008 Lehtinen | MC staff | Total
W36 | 2026-08-31 | 27 | 12 | 11 | 11 | 61
W37 | 2026-09-07 | 26 | 13 | 12 | 11 | 62
W38 | 2026-09-14 | 25 | 13 | 12 | 11 | 61
W39 | 2026-09-21 | 24 | 12 | 11 | 11 | 58
W40 | 2026-09-28 | 24 | 12 | 10 | 11 | 57
Daily detail, weekend of 19-20.09.2026 (site access log):
Date | Day | TP-001 | TP-005 | TP-008 | MC staff | Total
2026-09-18 | Friday | 25 | 13 | 12 | 11 | 61
2026-09-19 | Saturday | 0 | 0 | 0 | 1 | 1
2026-09-20 | Sunday | 0 | 0 | 0 | 1 | 1
2026-09-21 | Monday | 24 | 12 | 11 | 11 | 58
Weekend cover is one security officer. No trade access was granted on 19 or 20.09.2026.

## QS Site Measure
QUANTITY SURVEYOR — INDEPENDENT SITE MEASURE AT 30.09.2026
Measured 28-30.09.2026 by M. Nieminen MRICS. This measure governs for valuation.
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act ID | Activity | Measured cum % | Basis of measure
50 | DH1 — Rock-Socketed Bored Piles | 100 | 68 of 68 piles installed and concreted. Complete 11.09.2026, as forecast last period.
51 | DH2 — Rock-Socketed Bored Piles | 100 | 68 of 68 installed. Complete 15.09.2026.
52 | DH3 — Rock-Socketed Bored Piles | 88 | 60 of 68 installed
53 | DH4 — Rock-Socketed Bored Piles | 46 | 31 of 68 installed
54 | DH1 Pile Caps & Ground Beams | 35 | Reinforcement fixed to 6 of 14 caps, 3 poured
57 | DH4 Pile Caps & Ground Beams | 20 | 3 of 14 caps
59 | DH2 Foundation Waterproofing | 90 | W1-W3 complete and holiday-tested. W4 membrane laid, UPSTANDS INCOMPLETE at the north edge (approx. 24 m). Not accepted as complete.
60 | DH3 Foundation Waterproofing | 100 | Complete 09.09.2026
61 | DH4 Foundation Waterproofing | 30 | Bay 1 complete
63 | DH2 Ground Floor Slab | 25 | Commenced 21.09. Pour 1 of 4 complete. NOTE: slab is proceeding over bay W4 where the waterproofing upstands are incomplete.
64 | DH3 Ground Floor Slab | 10 | Reinforcement commenced
118 | Cooling Spine — Pipework & Distribution | 46 | 378 m of 820 m installed and supported; 11 of 14 rack sections
200 | Access Roads & Parking Construction | 98 | NE car park sub-base commenced following relocation of the temporary compound on 14.09
202 | Perimeter Fencing & Gates | 100 | 980 m complete, gates hung and tested
203 | Landscaping & Soft Works | 35 | Topsoil placed to south and west verges

## Site Diary Extract
SITE DIARY — EXTRACT, MATERIAL ENTRIES ONLY
Polaris DC-1 · Period 07 · main contractor record
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Date | Entry
2026-09-11 | DH1 piling complete, 68 of 68. Achieved on the date TP-001 forecast last period.
2026-09-14 | Temporary parking compound relocated (action A06-03, due 09.09). NE car park released to TP-008.
2026-09-14 | DH1 pile caps commenced.
2026-09-15 | DH2 piling complete, 68 of 68.
2026-09-16 | TP-001 cost submission for EI-004 received (PDC-COST-001-EI004).
2026-09-18 | TP-001 report DH2 waterproofing complete. QS to measure.
2026-09-19 | Site closed. Weekend security cover only.
2026-09-20 | Site closed. Weekend security cover only.
2026-09-21 | DH2 ground floor slab commenced, pour 1.
2026-09-22 | TP-001 revised programme PDC-SCH-001 Rev1 received.
2026-09-22 | Engineer's Instruction EI-005 received — main gate security provision.
2026-09-23 | Perimeter fencing complete.
2026-09-24 | TP-005 notice of delay ILM-NOT-003 received.
2026-09-29 | Progress meeting No. 7. See minutes.
2026-09-30 | QS site measure taken 28-30.09.

## Outgoing Correspondence
OUTGOING CORRESPONDENCE REGISTER — CONTRACTOR TO EMPLOYER
Polaris DC-1 · all outgoing formal correspondence, project to date
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | Date sent | Subject | Clause relied on
PDC-LTR-001-012 | 2026-07-16 | NW corner material, DH1 pile grid — notification | Sub-Clause 20.2.1
PDC-LTR-001-014 | 2026-07-30 | NW corner material — request for instruction | —
PDC-LTR-001-017 | 2026-08-12 | EI-004 — acknowledgement and records undertaking | —
PDC-LTR-001-019 | 2026-09-08 | Period 06 progress report — issue | —
PDC-LTR-001-020 | 2026-09-24 | EI-005 — acknowledgement, quotation to follow | —
Register maintained by the document controller. Nothing is issued outside this register.