## Statement of Claim
ILMATEK LVI OY — CLAIM FOR EXTENSION OF TIME AND ADDITIONAL PAYMENT
Reference ILM-CLM-001 · 16 October 2026 · Subcontract PDC-SUB-005 Rev1 (TP-005 Mechanical)
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Para | Text
1 | This claim is submitted under Clause 4 of the Subcontract. We claim an extension of time of 42 working days to the Section 1 Sectional Date of 2 April 2027, and additional payment of EUR 486,000.
2 | The claim comprises four heads, set out in the Delay Analysis sheet and particularised in the Windows sheet. Heads A, B and C are claims for time and money. Head D is a claim for money only, the time being subsumed within the Head A window.
3 | HEAD A — LATE RELEASE OF THE DH2 SLAB WORKING AREA. The DH2 ground floor slab was programmed to complete 13.09.2026. It commenced 21.09.2026. Our cooling spine pipework (activity 118 / IL-1400) could not proceed at the planned rate. We claim 22 working days. Notice was given by ILM-NOT-003 on 24.09.2026.
4 | HEAD B — REVISED 110 kV ENERGISATION DATE. The Employer has confirmed the 110 kV grid energisation as 24.04.2027, revised from 02.03.2027. Our commissioning activities IL-1510 and IL-1600 depend upon energisation and cannot be performed before it. We claim 14 working days. Notice was given by ILM-NOT-004 on 02.10.2026.
5 | HEAD C — RESTRICTED ACCESS, NORTH-WEST ZONE. Instruction EI-004 required excavation of unrecorded made ground in the north-west zone. Our pipe route through that zone was unavailable to us and our resources were redeployed. We claim 6 working days.
6 | HEAD D — TOWER CRANE TC-02 OUT OF SERVICE. The Contractor's tower crane TC-02 was out of service from 05.10.2026 to 07.10.2026 inclusive. Our pipefitting gang stood down for three working days. We claim EUR 12,400. Notice was given by ILM-NOT-005 on 08.10.2026. We do not claim these days separately as time, the period falling within the Head A window.
7 | We have at all times complied with our obligations under Clause 3 to plan and resource the works to the Sectional Dates, and none of the four events was within our control or our risk under the Subcontract.
8 | We reserve the right to particularise further and to claim finance charges accruing under Clause 6.3 on any sum found due and paid late.

## Delay Analysis
DELAY ANALYSIS — SUMMARY BY HEAD
As-planned versus as-built, TP-005 programme Rev1 · working days
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Head | Event | Activity affected | Window | Working days | Basis
A | Late release of DH2 slab working area | 118 / IL-1400 Cooling spine | 21.09.2026 – 22.10.2026 | 22 | As-planned v as-built on the affected activity
B | 110 kV energisation revised to 24.04.2027 | IL-1510, IL-1600 Commissioning | 06.04.2027 – 23.04.2027 | 14 | Prospective impact on the commissioning sequence
C | EI-004 made ground — NW zone access | 118 / IL-1400 (NW leg) | 12.08.2026 – 19.08.2026 | 6 | Resource redeployment record
D | Tower crane TC-02 out of service | IL-1400 pipefitting gang | 05.10.2026 – 07.10.2026 | 3 | Money only — time subsumed in Head A
| TOTAL EXTENSION OF TIME CLAIMED |  |  | 42 | Heads A + B + C
Note: the Head D period falls within the Head A window and is therefore not added to the time claimed.
Note: our subcontract Sectional Date for Section 1 is 2 April 2027, one month before the Main Contract date of 2 May 2027.

## Windows
PARTICULARS BY WINDOW
Each head, with the record we rely upon
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Head | Date | Event / record relied upon
A | 2026-09-13 | DH2 ground floor slab programmed complete (Kallio programme PDC-SCH-001 Rev0, activity 63)
A | 2026-09-21 | Slab commenced. Our gang stood down from the north bay working area
A | 2026-09-24 | Notice ILM-NOT-003 served on the Contractor
A | 2026-10-22 | End of the window relied upon
B | 2026-08-28 | Employer's Representative letter PDC-LTR-PMC-014 — 110 kV revised to 24.04.2027
B | 2026-09-29 | Position minuted at Site Progress Meeting No 7
B | 2026-10-02 | Notice ILM-NOT-004 served on the Contractor
C | 2026-08-12 | NW zone withdrawn from our working area following instruction EI-004. Acknowledged by our site supervisor on the Contractor's access register the same day
C | 2026-08-19 | NW zone returned to us
C | 2026-10-16 | Particularised in this claim
D | 2026-10-05 | Tower crane TC-02 reported out of service by the Contractor
D | 2026-10-07 | TC-02 returned to service
D | 2026-10-08 | Notice ILM-NOT-005 served on the Contractor

## Quantum
QUANTUM — BUILD-UP
Prolongation, disruption and standing time · EUR
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | Item | Basis | Period | EUR
Q1 | Prolongation — Head A | 4.4 weeks at EUR 11,200 per week | 21.09 – 22.10.2026 | 49280
Q2 | Prolongation — Head B | 2.8 weeks at EUR 11,200 per week | 06.04 – 23.04.2027 | 31360
Q3 | Prolongation — Head C | 1.2 weeks at EUR 11,200 per week | 12.08 – 19.08.2026 | 13440
Q4 | Standing time — Head D | 3 days, 8 pipefitters, 2 welders, supervision | 05.10 – 07.10.2026 | 12400
Q5 | Extended site establishment | 15.5 weeks at EUR 11,200 per week | 01.07 – 16.10.2026 | 173600
Q6 | Additional supervision | 2 staff, 15.5 weeks at EUR 2,400 per week | 01.07 – 16.10.2026 | 74400
Q7 | Plant, welfare and small tools standing | Schedule of rates | 01.07 – 16.10.2026 | 45520
Q8 | Disruption to prefabrication sequence, Hyvinkää works | Measured mile against our tender allowance | 01.07 – 16.10.2026 | 39000
Q9 | Head office overhead and profit | 8% on the above | — | 31680
Q10 | Finance charges to date | Clause 6.3, ECB main refinancing rate plus 2% | — | 15320
| TOTAL CLAIMED |  |  | 486000
The weekly prolongation rate of EUR 11,200 is derived from our tender site establishment allowance.

## Appendix — Procurement
APPENDIX — PROCUREMENT STATUS, KEY PLANT
Submitted in support of Head B
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Item | Order placed | Programmed delivery | Confirmed delivery | Variance (wd) | Note
Chiller sets CH-01 to CH-04 | 2026-05-18 | 2027-02-25 | 2027-03-04 | 5 | Supplier rescheduled. Our order was placed to the lead time in PDC-LT-001
Primary pumps P-01 to P-06 | 2026-05-18 | 2026-11-30 | 2026-11-30 | 0 | On programme
AHU sets, DH1 | 2026-06-02 | 2027-01-15 | 2027-01-15 | 0 | On programme
BMS panels | 2026-07-14 | 2027-01-29 | 2027-01-29 | 0 | On programme
Note: the chiller variance of 5 working days is absorbed within our own float to IL-1510 and does not form part of this claim.