## Zone Access Register
WORKING AREA ACCESS REGISTER — TP-005
Signed by the subcontractor's supervisor on withdrawal and on return
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Zone | Withdrawn | Reason | Acknowledged by | Returned | Working days
NW zone, pipe route | 2026-08-12 | Instruction EI-004 — excavation of unrecorded made ground | J. Virtanen (Ilmatek), 12.08.2026 | 2026-08-19 | 6
DH2 north bay | 2026-09-21 | Slab pour 1 in progress | J. Virtanen (Ilmatek), 21.09.2026 | 2026-10-22 | 22
DH1 plant room | 2026-10-05 | Tower crane TC-02 out of service — no lifting | J. Virtanen (Ilmatek), 05.10.2026 | 2026-10-07 | 3

## Plant Log — TC-02
TOWER CRANE TC-02 — OUT OF SERVICE RECORD
Contractor-owned plant · Period 08
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Date | Status | Cause | Responsibility | Trades affected
2026-10-05 | Out of service | Slew ring bearing replacement — scheduled maintenance overran | Contractor | TP-005 pipefitting, TP-001 steel
2026-10-06 | Out of service | Awaiting parts ex Helsinki | Contractor | TP-005 pipefitting, TP-001 steel
2026-10-07 | Out of service to 14:00 | Recommissioning and load test | Contractor | TP-005 pipefitting
2026-10-08 | In service | — | — | —
Note: the outage was the Contractor's own maintenance and is accepted as the Contractor's risk.

## Baseline Float — TP-005
ACCEPTED BASELINE — TOTAL FLOAT AND LOGIC, TP-005 ACTIVITIES
Extract from the accepted TP-005 baseline programme · working days
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act | Description | Duration | Predecessor | Total float | On critical path
102 | DH2 plant room builders work openings | 15 | 96FS | 61 | No
118 | Cooling spine — pipework and distribution | 90 | 102FS | 87 | No
124 | DH1 chilled water risers | 40 | 118FS | 87 | No
140 | DH1 chiller installation and piping | 55 | 124FS, 131FS | 42 | No
IL-1510 | Chiller commissioning, DH1 | 20 | 140FS | 12 | No
IL-1600 | L4 integrated systems testing support | 15 | IL-1510FS, MS-11 | 0 | Yes
Note: activity 118 takes its predecessor from activity 102, the plant room builders work openings. The DH2 ground floor slab is activity 63 and is not a predecessor to 118 in the accepted baseline.

## Labour Returns — TP-005
LABOUR AND SUPERVISION — TP-005
Period 08 · weekly average on site, gate-verified
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Week | W/c | Pipefitters | Welders | Supervision | Total on site | Planned (Rev1)
W41 | 2026-10-05 | 8 | 3 | 1 | 12 | 11
W42 | 2026-10-12 | 9 | 3 | 1 | 13 | 11
W43 | 2026-10-19 | 9 | 4 | 1 | 14 | 11
W44 | 2026-10-26 | 9 | 4 | 1 | 14 | 11
Note: TP-005 has been at or above the Rev1 histogram in every week of Period 08.

## QS Site Measure
QUANTITY SURVEYOR SITE MEASURE
M. Niemi · walked 27–29 October 2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Act | Description | Sub claims % | QS measure % | Note
118 | Cooling spine — pipework and distribution | 62 | 61 | Not material. 508 m of 820 m installed and supported
102 | DH2 plant room builders work openings | 100 | 100 | Complete 2026-09-04
124 | DH1 chilled water risers | 8 | 8 | Commenced 2026-10-19

## Outgoing Correspondence
OUTGOING CORRESPONDENCE REGISTER
Contractor to Employer's Representative and to subcontractors · to 31.10.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | Date | To | Subject
PDC-LTR-001-018 | 2026-09-24 | Employer's Representative | EI-005 main gate security — acknowledgement and quotation timetable
PDC-LTR-005-009 | 2026-10-06 | Ilmatek LVI Oy | TC-02 out of service — notification and revised lifting schedule
PDC-LTR-005-010 | 2026-10-19 | Ilmatek LVI Oy | ILM-CLM-001 — acknowledgement of receipt, assessment to follow
Note: no response to PDC-LTR-PMC-014 (110 kV programme consequence) has been issued as at 31.10.2026.