## Cover
PDC-CLM-001 — 110 kV EOT & Prolongation Claim
Quantum workbook — Period 09 update — engine-computed EOT
Source: PDC-PROG-P09_Impact_Records_and_Preliminaries_Nov2026.xlsx
Contract: PDC-PC-001 Rev C (FIDIC Yellow Book 2017, Particular Conditions as amended)
Contractor: Suomen Betoni-Infra Oy ¦ Employer: Aviapolis DC Holdings Oy ¦ Engineer: A. Halonen
Headline numbers (engine-computed, no SP-7 apportionment)
EOT sought: 30 working days (engine-computed slip; L4 slip absorbed by ST-1300 float, see Annex J)
Prolongation: 30 wd × EUR 4,492.68/wd = EUR 134,780
Cost incurred: EUR 18,400 (expressly excludes Ilmatek Head D EUR 12,400, see Head 7)
TOTAL: EUR 153,180
How to read this workbook
• Every EUR figure on this workbook is a formula. Cells are sourced to PDC-PROG-P09.
• Yellow rows are subtotals. Gold rows are totals. Strike-through rows are NOT claimed.
• If a source-cell value changes, every downstream figure recalculates on file open.
• Notice arithmetic (Head 1) is on a separate sheet for clarity.
• ST-1300 float geometry (Annex J in the narrative) is summarised in the 'Float Geometry' sheet.

## Head 2 - EOT
Head 2 — EOT and Slip (TIA, engine-computed; no SP-7 apportionment)
Source: PDC-PROG-P09, sheet '110 kV Impact Window'; Annex TIA engine output
Item | Value | Source
110 kV energisation (EN-110) — contract | 2027-03-12 | PDC-LTR-PMC-014, 28.08.2026, paragraph 1
110 kV energisation (EN-110) — revised | 2027-04-24 | PDC-LTR-PMC-014, 28.08.2026, paragraph 1
Calendar slip (cal days) |  | Sheet '110 kV Impact Window', row 1 — Difference = 43
Working-day slip (wd) | 30 | Sheet '110 kV Impact Window', row 2 — Difference = 30
TIA engine output
Baseline makespan (EN-110 at contract date) | 186 | Annex TIA §13.1 — engine
Scenario makespan (EN-110 at revised date) | 216 | Annex TIA §13.2 — engine
Engine-computed Employer-attributable slip (wd) |  | B12 − B11 = 30 wd (matches B8 above)
Contractor-side slip on ST-1300 (recorded)
ST-1300 L4 handover slip (wd) | 9 | PDC-PROG-P09, sheet 'Concurrent Delay Record', ref C-01
ST-1300 baseline total float (wd) | 55 | Annex J §16.2 — engine + add_wd boundary check
ST-1300 scenario total float (wd) | 85 | Annex J §16.2 — engine + add_wd boundary check
L4 slip forecast finish (wd from project start) |  | ST-1300 planned finish (day 30) + L4 slip (9 wd) = day 39
L4 slip absorbed by float? |  | Day 39 forecast finish < day 85 latest permissible finish
Apportionment under Rev C SP-7
Engine-computed Employer slip (wd) |  | Same as B13 (no apportionment earned)
Deduction under SP-7 (wd) | 0 | L4 slip is on float; SP-7 does not reach a slip on float
EOT sought (wd) |  | Engine slip (B23) − SP-7 deduction (0) = 30 wd

## Head 3 - Prolongation
Head 3 — Prolongation rate build-up
Source: PDC-PROG-P09, sheet 'Preliminaries — BOQ Section A'
Ref | Item | Basis | EUR
A.01 | Site establishment, offices, welfare | 82 | 947000
A.02 | Site management and supervision staff | 82 | 612000
A.03 | Site services, power, water, telecoms | 82 | 168000
A.04 | Common plant, access and small tools | 82 | 115000
TOTAL TIME-RELATED PRELIMINARIES |  | 82
WEEKLY RATE
DAILY RATE (working day, /5)
Compensable working days (from Head 2, no SP-7 deduction)
PROLONGATION COST (EUR)

## Head 4 - Incurred
Head 4 — Cost incurred to 30.11.2026 (excludes Ilmatek Head D EUR 12,400)
Source: PDC-PROG-P09, sheet 'Incurred to Date'
Ref | Item | Evidence | EUR
I-01 | Commissioning engineer mobilisation deferred — cancellation fee | Invoice CX-2211, 14.11.2026 | 8400
I-02 | Temporary power hire extended, 6 weeks | Order VP-0417 variation | 6800
I-03 | Re-planning and re-issue of the commissioning sequence | Timesheets wk 45–47 | 3200
TOTAL INCURRED — IN HEAD 4
Expressly excluded (NOT claimed here)
I-D | Ilmatek TP-005 Head D — TC-02 outage standing time | PDC-LAB-P08 plant log; PDC-LTR-005-009, 06.10.2026; settled under A09-03 (MIN-P09) | 12400
REASON | Contractor-risk plant outage on SBI's own TC-02; settled separately via Ilmatek November valuation under Meeting No. 9 action A09-03. See Head 7 of PDC-CLM-001.

## Total
PDC-CLM-001 — Total Claim
Item | Value | Source
EOT sought |  | Head 2 sheet, cell B25
Prolongation |  | Head 3 sheet, prolongation row
Cost incurred to date (Head 4) |  | Head 4 sheet, total incurred row
TOTAL CLAIM — COST
Reserved pass-through (Ilmatek Head B) | to be assessed under Subcontract PDC-SUB-005 Rev 1 Cl 1.3 | Claim Head 6
Expressly excluded (Ilmatek Head D) | EUR 12,400 settled via November valuation under A09-03 | Claim Head 7

## Head 1 - Notice validity
Head 1 — Notice validity arithmetic (Rev C 20.2.2)
Item | Date / days | Source
Contractor aware of event | 2026-08-28 | PDC-LTR-PMC-014, header
Notice of Claim served | 2026-10-09 | PDC-NOT-009; PMC-021 §1
Engineer non-compliance response | 2026-10-28 | PDC-LTR-PMC-021, header
Days, aware → Notice |  | PMC-021 §3: '42 days'
Days, Notice → Engineer |  | arithmetic
20.2.2 window (days) | 14 | Rev C operative text, PDC-CX-009
Engineer response late by (days)
Notice status under Rev C 20.2.2 | DEEMED VALID

## Float Geometry (Annex J)
ST-1300 float geometry — Annex J summary
Source: Annex TIA engine output + add_wd boundary check
Activity | Early start (wd) | Early finish (wd) | Latest permissible finish (wd, baseline) | Total float (wd)
ST-1300 | 0 | 30
IL-1600 |  |  | 130
ST-1310 | 130 |  | 130
EN-110 | 130 | 130 | 130
ST-1400
MS_END
L4 slip forecast finish on ST-1300
L4 slip forecast finish (day 39) < latest finish (day 85)?

## Sources
Sourcing
Code | Document
PDC-PROG-P09 | PDC-PROG-P09_Impact_Records_and_Preliminaries_Nov2026.xlsx — Period 09 progress pack
PDC-LAB-P08 | Period 08 site records + plant log TC-02 + TP-005 baseline float
PDC-LTR-PMC-014 | Letter, Employer's Representative, 28.08.2026 — 110 kV revised energisation
PDC-NOT-009 | Notice of Claim, 09.10.2026 — Sub-Clause 20.2.1
PDC-LTR-PMC-021 | Letter, Engineer, 28.10.2026 — Notice validity (response)
PDC-CX-009 | Operative-text file note, 25.11.2026 — Sub-Clauses 20.2.1 and 20.2.2 reinstated in full under Rev C
PDC-PC-001 Rev C | Particular Conditions, Rev C, issued for execution 24.02.2026
PDC-MIN-P09 | Site Progress Meeting No. 9, 24.11.2026 — actions A09-01, A09-03
PDC-SUB-005 Rev 1 | Ilmatek TP-005 Subcontract, Rev 1 — Clauses 1.3 and 4.3
PDC-CLM-005-001 | Ilmatek ILM-CLM-001 claim workbook, 16.10.2026 — Statement of Claim paragraphs 4 and 6; Quantum rows Q2 and Q4