## Critical Path — Nov 2026
CRITICAL PATH AND FLOAT — DATA DATE 30.11.2026
Contractor's current working programme, period 09 update · working days
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Activity | Description | Duration | Predecessor | Total float | Critical
ST-1300 | L4 structural handover to MEP (TP-001 Kallio) | 30 | ST-1210FS | 0 | Yes
IL-1600 | Mechanical commissioning, DH1–DH4 | 45 | ST-1300FS | 0 | Yes
ST-1310 | Integrated systems testing, L4 | 35 | IL-1600FS, EN-110FS | 0 | Yes
EN-110 | 110 kV grid energisation (Employer-provided) | 0 | — | 0 | Yes
ST-1400 | Client witness testing and handover | 20 | ST-1310FS | 0 | Yes
124 | DH1 chilled water risers | 40 | 118FS | 87 | No
Note: ST-1310 cannot commence before EN-110. Energisation is Employer-provided under the Contract.
Note: Contract Time for Completion 2 May 2027. Section 1 Sectional Date 2 April 2027.

## 110 kV Impact Window
ENERGISATION SLIP — IMPACT ON ST-1310
Dates taken from PDC-LTR-PMC-014, 28.08.2026 — the Employer's own notification
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Item | Contract | Revised | Difference
110 kV energisation (EN-110) | 2027-03-12 | 2027-04-24 | 43 calendar days
Working days across the window | — | — | 30 working days
ST-1310 planned start | 2027-03-15 | 2027-04-26 | 30 wd later
ST-1400 planned finish | 2027-04-30 | 2027-06-11 | 30 wd later
Time for Completion | 2027-05-02 | — | Exceeded by 30 wd unless extended
Source of the contract date | PDC-LTR-PMC-014, 28.08.2026 | — | Employer notification: "previously confirmed as 12 March 2027 in the grid connection offer PDC-GC-001"

## Concurrent Delay Record
OUR OWN DELAY TO THE SAME ACTIVITY
TP-001 Kallio L4 structural handover · from our site records
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | Event | Activity affected | Planned | Forecast | Working days
C-01 | L4 structural handover late — TP-001 rebar revision and pour sequence | ST-1300 | 2027-02-15 | 2027-02-26 | 9
| Effect on ST-1310 start, independent of energisation | ST-1310 | 2027-03-15 | 2027-03-26 | 9
Note: this delay is at the Contractor's risk under the Contract. It overlaps the energisation window and delays the same successor.
Note: 9 of the 30 working days are therefore concurrent. Recorded here so the position is stated before the Engineer states it for us.

## Preliminaries — BOQ Section A
TIME-RELATED PRELIMINARIES
Extract, priced Bill of Quantities Section A · the contract rate
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | Item | Basis | EUR
A.01 | Site establishment, offices, welfare | 82 weeks | 947000
A.02 | Site management and supervision staff | 82 weeks | 612000
A.03 | Site services, power, water, telecoms | 82 weeks | 168000
A.04 | Common plant, access and small tools | 82 weeks | 115000
| TOTAL TIME-RELATED PRELIMINARIES | 82 weeks | 1842000
| WEEKLY RATE (1,842,000 / 82) | per week | 22463
Note: this is the measured, contract-priced rate. It is not a tender allowance.

## Incurred to Date
COST INCURRED TO 30.11.2026 ON THE ENERGISATION SLIP
Resequencing already carried out — invoiced or committed
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | Item | Evidence | EUR
I-01 | Commissioning engineer mobilisation deferred — cancellation fee | Invoice CX-2211, 14.11.2026 | 8400
I-02 | Temporary power hire extended, 6 weeks | Order VP-0417 variation | 6800
I-03 | Re-planning and re-issue of the commissioning sequence | Timesheets wk 45–47 | 3200
| TOTAL INCURRED |  | 18400

## Ilmatek Position
TP-005 ILMATEK — OUR ASSESSED POSITION ON ILM-CLM-001
Issued 13.11.2026, PDC-LTR-005-011
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Head | Their claim | Our assessment | Bearing on this claim
A | 22 wd / Q1 49,280 | 0 wd / EUR 0 | Rejected on causation. Nothing to pass on.
B | 14 wd / Q2 31,360 | 0 wd now, reserved | Same 110 kV event as this claim. Their entitlement is bound to ours under Subcontract Clause 1.3 — it follows what we recover, and follows nothing if we recover nothing.
C | 6 wd / Q3 13,440 | 0 wd / EUR 0 | Time-barred under Subcontract Clause 4.3. Nothing to pass on.
D | 0 wd / Q4 12,400 | EUR 12,400 accepted | TC-02 is our own tower crane and the outage is recorded in our plant log as our own maintenance. This sum is ours to bear.

## Correspondence Register
CORRESPONDENCE — 110 kV THREAD
Outgoing and incoming, in date order
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Date | Reference | From → To | Subject
2026-08-28 | PDC-LTR-PMC-014 | Engineer → SBI | 110 kV energisation revised to 24.04.2027
2026-09-29 | PDC-MIN-P07 §5 | Meeting No. 7 | AH asks when the Contractor will respond. A07-05 raised.
2026-10-09 | PDC-NOT-009 | SBI → Engineer | Notice of Claim under Sub-Clause 20.2.1
2026-10-27 | PDC-MIN-P08 §5 | Meeting No. 8 | AH records no response received; reminds on notice provisions
2026-10-28 | PDC-LTR-PMC-021 | Engineer → SBI | Notice asserted out of time; particulars will not be reviewed
2026-11-13 | PDC-LTR-005-011 | SBI → Ilmatek | ILM-CLM-001 assessment issued — 0 wd, EUR 12,400