## Quotation
QUOTATION — VARIATION UNDER PDC-EI-007
Ilmatek LVI Oy · Ref ILM-QUO-007 · 14 December 2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | Description | Unit | Qty | Rate (EUR) | Amount (EUR)
V1 | Additional CRAH units to DH4, N+1 configuration | nr | 4 | 96400 | 385600
V2 | Chilled water pipework, welded and pre-insulated | m | 180 | 812 | 146160
V3 | Heat-recovery pipework extension to boundary chamber | m | 40 | 1239.59 | 49583.6
V4 | CDU connection kits for future liquid-cooled racks | nr | 4 | 14750 | 59000
V5 | Commissioning of the additional plant | item | 1 | 40000 | 40000
V6 | Extended site preliminaries, 6 weeks at EUR 11,200 per week | wk | 6 | 11200 | 67200
| SUBTOTAL |  |  |  | 747543.6
| Overhead and profit at 8% |  |  |  | 59803.49
| TOTAL QUOTED |  |  |  | 807347.09
Note: the weekly preliminaries rate is taken from our tender site establishment allowance.
Note: Subcontract Clause 7.2 provides that the value of a variation shall be agreed between the parties.

## V4 Build-up
CDU CONNECTION KITS — BUILD-UP
Supporting Ref V4 · not an item in the Bill of Quantities
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Component | Basis | EUR per kit
Manifold set, stainless, 2 x DN50 with isolation | supplier quote SF-2291, 12.12.2026 | 8100
Flexible hose set and quick-disconnect couplings | supplier quote SF-2291 | 3250
Installation labour, 14 h at EUR 68/h | subcontract labour rate | 952
Pressure test, flush and certification | measured allowance | 1180
Sub-total per kit |  | 13482
Contingency at 9.4% | supplier lead-time risk | 1268
TOTAL PER KIT |  | 14750