## BOQ Extract — Section F
BILL OF QUANTITIES — SECTION F EXTRACT
PDC-BOQ-001, the accepted contract bill · TP-005 Mechanical
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Item | Description | Unit | Qty | Rate (EUR) | Amount (EUR)
F.03 | CRAH units, 7 per hall (N+1) | nr | 28 | 80057.06 | 2241597.68
F.06 | Chilled water pipework, welded and pre-insulated | m | 2850 | 662.84 | 1889094
F.09 | Heat recovery pipework to site boundary chamber | m | 260 | 1239.59 | 322293.4
Note: Section J — Commissioning & Handover — is priced to the MAIN CONTRACT, not to TP-005. See the BOQ Summary sheet.
Note: there is no bill item for coolant distribution units. Liquid cooling was not in the Employer's Requirements at tender.

## Variation Register
VARIATION REGISTER — TP-005
Instructed, valued and certified to date
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | Instruction | Instructed | Status | Certified (EUR)
EI-004 | NW corner made ground — additional excavation | 2026-08-05 | Valued and certified P08 | 88400
EI-005 | Main gate security — revised barrier | 2026-09-22 | Valued and certified P09 (TP-008) | 41250
EI-007 | DH4 high-density cooling provision | 2026-12-03 | Quotation received, not yet valued | 0

## Programme Impact
EI-007 — PROGRAMME POSITION
Contractor working programme, period 10 update · working days
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Activity | Description | Duration | Total float | Critical
IL-1420 | DH4 CRAH installation (EI-007 works) | 18 | 26 | No
IL-1430 | DH4 pipework connections (EI-007 works) | 12 | 26 | No
IL-1600 | Mechanical commissioning, DH1–DH4 | 45 | 0 | Yes
Note: the instructed work sits on activities carrying 26 wd of float and does not touch IL-1600 or the Time for Completion.
Note: PDC-EI-007 paragraph 5 states the instruction does not extend the Time for Completion.

## QS Measure
QS MEASURE — EI-007 WORKS
Measured from the issued drawings, 18.12.2026
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | Item | Quoted qty | Measured qty | Agreed
V1 | Additional CRAH units | 4 | 4 | Yes
V2 | Chilled water pipework (m) | 180 | 180 | Yes
V3 | Heat-recovery pipework (m) | 40 | 40 | Yes
V4 | CDU connection kits | 4 | 4 | Yes
Note: quantities are not in dispute. The question on this variation is rate and entitlement, not measure.